## instructions1
INSTRUCTIONS ON COMPLETION OF PROJECT STOCK TAKE TEMPLATE
1. All fields are mandatory and should be populated.
2. DO NOT EDIT the CONFIGURATION worksheet.
3. ONLY populate rows applicable in your respective Counties &Ward Location(s) and Hide the rest of the rows (DO NOT DELETE the Rows).
4. The scope of this exercise is projects started between the year 2013 and 30th June, 2024
5.Remember to SAVE the document after populating the required details in the worksheet.

## Project Stocktaking Template
PROJECT DETAILS | [6 empty] | PROJECT LOCATION |  |  | IMPLEMENTATION DETAILS | [6 empty] | FINANCIAL INFORMATION |  |  |  |  | DISBURSMENT |  |  |  | EXPENDITURE |  |  | PROJECT STATUS |  |  | ACTIONS FOR STALLED |  |  |  | RISKS AND RECOMMENDATIONS |  |  | CLIMATE & DISASTER RISK SCREENING |  | ENVIRONMENTAL , SOCIAL AND OCCUPATIONAL HEALTH, SAFETY AND GENDER SCREENING |  | TECHNICAL, FINANCIAL, AND ECONOMIC VIABILITY SCREENING |  | ADDITIONAL REMARKS
S/No. | Project Name/Title | Project Description | Project Goal/Objective | Project Output | Project Code (Budget line) | Budget Item Name | Sub-County | Ward | Geographic Location (Latitude & Longitude) | Sector/ Vote Name | Department, Directorate, Units, Agencies | Implementing Department/Agency / Muncipalities | Date of Approval/Financial Approval | Project Start Date | Expected Project Completion Date | Actual Project Completion Date | Estimated Project Cost (Kshs.) | Approved Project Cost | Funds available in the specific year | Project Funding Source | If Development Partners, Please specify . | County Government component in the Project Cost (Kshs.) | Development Partner component in the Project Cost (Kshs.) | Total Disbursed Funds as at 30th June 2024 (Kshs.) | Percentage (%) Disbursed Amount = (Disbursed/ Approved) | Expenditure to date | Pending Bill/Outstanding commitment not paid but work done | Project Balance (Kshs.) i.e (Approved Project Cost - Disbursed Amount) | Project Status at the time of the Exercise (i.e Completed, Ongoing, Stalled) | % completion for ongoing/stalled projects | If Stalled, what is the percentage (%) completion at the time of stalling (Physical completion status) | If stalled give reasons; | Year the project stalled | Time required to complete the stalled project (in months) | Estimated cost required to complete the stalled project (in Kshs.) | Is the project still appering in the budget or is it still receiving funds in the annual budgets? (Yes/No) | Recommendation for the Stalled Project (Complete/ Cancel/ Defer) | Identify the Risks associated with the stalled/completed/ongoing project ie. (Contractual/legal/Financial/Environmental etc.) | Has this project been screened for Climate & Disaster Risks? Yes/No | If yes, what action has been taken to mitigate? IF Not, give reasons and the immediate plans for conducting the screening. | Has the project been screened for Environmental, Social, Occupational Health, Safety and gender risks | If yes, what action has been taken to mitigate? IF Not, give reasons and the immediate plans for conducting the screening. | Has the project been screened for Technical, Financial, and Economic Viability and a fesibility report been prepared? (yes/No) | If yes, what action has been taken to mitigate? IF Not, what is being used to measure viability of the project? Additionally, indicate immediate plans on when the screening and feasibility study will be undertaken | REMARKS
HQ
1 | County Spatial Plan | Development of the County Spatial Plan | Promote susatainable development and guide land use and settlement partnerns | Spatial plan document,spatial data maps and development framework guidelines |  | Development of the County Spatial Plan | all | all | HQ | Lands | Lands | Lands | 2017-03-01 | 2017-03-01 | 2019-03-01 | 2023-03-01 | 139000000 | 139000000 | 118000000 | CGK | N/A | 139000000 | N/A | 118000000 | 90% | 118000000 | 21000000 | 21000000 | Completed | 100% | N/A | N/A | N/A | N/A |  | No | N/A | N/A | N/A | N/A | NO | N/A | NA | NA | CSP is in its implementation stages
2 | County Valuation roll | Development of the county Valuation roll | Facilitate revenue collection | Valuation roll document and property database & Maps | 4672100500 | Development of the County valuation roll | all | all |  | Lands | Lands/Finance | Lands | 2015-03-01 | 2015-03-01 |  |  | 120000000 | 120000000 | 69000000 | CGK | N/A | 120000000 | N/A |  | 90% | 69000000 | 51000000 | 51000000 | Completed | 100% | N/A | N/A | N/A | N/A |  |  | N/A | N/A | N/A | N/A | NO | N/A | NA | NA | Cabinet & county assembly approval stages
3 | Construction of Roads and Footpaths to bitumen standard; Installation of Solar Street Lights; Construction of Stormwater Drainages | Kajiado Majengo-construction of 1.209kms roads,footpaths,drainages and 64 solar streetlights. Ngong-Mathare-1.17kms roads,footpaths,drainages 62 solar streetlights | Upgrading of informal settlements | murramed roads,street lighting and construction of storm water drainages | 4683100100 | Grants | Kajiado Central & Kajiado North | Dalalekutuk,Dalalekutuk and Ngong |  | Lands | Urban development | Lands & Urban development | 15th March 2024 | 10th September 2024 | 9th September 2025 | 9th September 2026 | 203448691.38 | 203448691.38 | 61695439.5 | World bank | Kenya Informal setllement program | 0 | 203448691.38 | 61695439.5 | 73% |  |  |  | Ongoing | 100% | [14 empty] | fully funded by workd bank
4 | GIS Lab | Equipping of the GIS Lab | to enhance spatial data | GIS Lab equiped |  | GIS lab | all |  |  | Lands |  | Lands |  |  |  |  | N/A | N/A | N/A | Partners | FAO | N/A | N/A | [6 empty] | 100% | [6 empty] | N/A | N/A | N/A | N/A | NO | N/A | NA | NA | donated & equiped by FAO
5 | Land management System | development of a land management system | Improve efficiency in Land Administration | Land management system developed & operational |  | system maintainance | kajaido central | Ildamat |  | Lands | Lands | Lands |  |  |  |  | 3000000 | 3000000 | 3000000 | CGK |  |  |  | 3000000 | [5 empty] | 100% | [6 empty] | N/A | N/A | N/A | N/A | NO | N/A | NA | NA | recurrent expenditure
6 | County Valuation roll | Development of the county Valuation roll | Facilitate revenue collection for allotment plots | Valuation roll document, property database & Maps and georefrence aerial images | 4672100500 | valuation roll | all | all | County wide | Lands | Lands/Finance | Lands | 2016 | 2016 | [10 empty] | 100% |  | 0 | 0 | Completed | 100% | [6 empty] | N/A | N/A | N/A | N/A
KAJIADO MUNICIPALITY
9 | Tarmacking of Total-Catholic Church-KCB Junction-Nyambene Road | Construction of Roads and Footpaths to bitumen standard; Installation of Solar Street Lights; Construction of Stormwater Drainages | i. 1.405km of Roads ii. 1.405km of Footpaths iii. 1.405km of Stormwater drainages iv. 5no. Solar treet lights | i. 1.0km of Roads ii. 1.0km of Footpaths iii. 1.0km of Stormwater drainages iv. 5no. Solar treet lights | 4683100100 | Kenya Urban Support Programme (KUSP-UDG) | Kajiado Central | Ildamat & Dalalekutuk | 1°50'40.0"S 36°47'21.6"E | Kajiado Municipality | Municipality of Kajiado | Municipality of Kajiado | 2018 | 8th August, 2019 | 8th February, 2020 | 31st March, 2020 | 50000000 | 50000000 | 50000000 | WorldBank throught KUSP | WorldBank | 0 | 50000000 | 50000000 | 100% | 49324707.1 | 0 | 0 | Completed | 100% Complete |  | N/A | N/A | N/A | N/A | No |  | N/A | Yes | i. Interconnecting the road drainage system with existing ones to mitigate urban flooding risk ii. Installation of solar street lights to reduce reliance on grid power | Yes | i. Construction of dedicated footpaths to reduce human-vehicular conflict ii. Construction of ramps to footpaths for ease of access for PWDs iii. Installation of street lights to curb insecurity | Yes | i. Compliance with national environmental and planning standards ii. Socio-economic viability analysis for the society as a whole iii. Incorporation of planning and engineering resilience and sustainability iv. Utilization of international and national construction best practices and design standards.
10 | Construction of Kajiado Public Square and Cultural High Street in Kajiado Municipality | Construction of a Recreational Urban Green Space; Construction of a Trading Street; Construction of Roads and Footpaths to Concrete Paving Blocks Standard; Construction Storm Water Drainages; Installation of Solar Street Lights; Installation of Water Storage Tanks. | i. 0.56km of Roads ii. 0.81km of Footpaths iii. 0.56km of Stormwater drainage iv. 30 Solar street lights v. 2,695 square meters of urban green space vi. 1no. Ablution Block vii. 4no. 24,000lts plastic water tanks | i. 0.66km of Roads ii. 0.91km of Footpaths iii. 0.66km of Stormwater drainage iv. 10 street lights v. 2,695 square meters of urban green space vi. 1no. Ablution Block vii. 8no. 10,000lts plastic water tanks | 4683100100 | Kenya Urban Support Programme (KUSP-UDG) | Kajiado Central | Ildamat | 1°50'33.6"S 36°47'11.9"E | Kajiado Municipality | Municipality of Kajiado | Municipality of Kajiado | 2019 | 2nd August, 2021 | 2nd February, 2022 | 6th May, 2022 | 50000000 | 50000000 | 50000000 | WorldBank throught KUSP | WorldBank | 0 | 50000000 | 50000000 | 100% | 46512362.24 | 0 | 0 | Completed | 100% Complete | N/A | N/A | N/A | N/A | N/A | No |  | N/A | Yes | i. Interconnecting the road drainage system with existing ones to mitigate urban flooding risk ii. Installation of solar street lights to reduce reliance on grid power iii. Construction of urban green space to improve air and water quality, regulate temperature and social inclusivity iv. Rainwater harvesting to enhance water security | Yes | i. Construction of dedicated footpaths to reduce human-vehicular conflict ii. Construction of ramps to footpaths for ease of access for PWDs iii. Installation of street lights to curb insecurity iv. Urban greenery to imrpove air and water quality v. Construction of a public sanitation facility to preventing the spread of diseases and promoting overall hygiene | Yes | i. Compliance with national environmental and planning standards ii. Socio-economic viability analysis for the society as a whole iii. Incorporation of planning and engineering resilience and sustainability iv. Utilization of international and national construction best practices and design standards.
11 | Construction of Kajiado Market and other Works at Kajiado Town | Construction of Market Infrastructure; Construction of Roads and Footpaths to Concrete Paving Blocks Standard; Construction Storm Water Drainages; Installation of Solar Street Lights | i. 1no. Open-air Market ii. 24no. Market Stalls iii. 0.4km of Roads iv. 0.551km of Footpaths v. 0.454km of Stormwater drainage vi. 10no. Solar street lights | i. 1no. Open-air Market ii. 24no. Market Stalls iii. 0.4km of Roads iv. 0.551km of Footpaths v. 0.454km of Stormwater drainage vi. 10no. Solar street lights | 4683100100 | Kenya Urban Support Programme (KUSP-UDG) | Kajiado Central | Ildamat & Dalalekutuk | 1°50'29.5"S 36°47'17.6"E | Kajiado Municipality | Municipality of Kajiado | Municipality of Kajiado | 2020 | 17th March, 2022 | 16th September, 2022 | 16th March, 2023 | 60105054.8 | 60105054.8 | 60105054.8 | WorldBank throught KUSP | World Bank | 0 | 60105054.8 | 60105054.8 | 100% | 56214411.77 | 0 | 0 | Completed | 100% Complete | N/A | N/A | N/A | N/A | N/A | No |  | N/A | Yes | i. Interconnecting the road drainage system with existing ones to mitigate urban flooding risk ii. Installation of solar street lights to reduce reliance on grid power iii. Rainwater harvesting to enhance water security | Yes | i. Construction of dedicated footpaths to reduce human-vehicular conflict ii. Construction of ramps to footpaths for ease of access for PWDs iii. Installation of street lights to curb insecurity iv. Construction of open-air market and market stalls that provide traders with clean safe and dignified trading spaces v. Rainwater harvesting to improve public health, hygiene, and community well-being | Yes | i. Compliance with national environmental and planning standards ii. Socio-economic viability analysis for the society as a whole iii. Incorporation of planning and engineering resilience and sustainability iv. Utilization of international and national construction best practices and design standards.
12 | Construction of On-Street Parking in Kajiado Municipality | Construction, Demarcation and Designation of 100 On-Street Parking Lots | i. 100no. Parking Lots | i. 100no. Parking Lots | 4683100100 |  | Kajiado Central | Ildamat & Dalalekutuk |  | Kajiado Municipality |  | Municipality of Kajiado |  |  |  |  | 10000000 | 10000000 | 10000000 | CGK | CGK | 10000000 | N/A | 10000000 |  |  |  |  | Ongoing
13 | Rehabilitatin of Kajiado Dumpsite in Kajiado Town | Construction of boundary wall around the dumpsite; Construction of gravel access roads to and within the dumpsite; Waste spreading, segragation and compaction; Installation of solar street lights | i. 400meters of boundary wall ii. 700meters of gravelled and murramed road iii. 2,400cubic meters of waste spread, segragated and compacted iv. 5no. Solar streetlights v. 2no. CCTV Cameras | i. 400meters of boundary wall ii. 700meters of gravelled and murramed road iii. 2,400cubic meters of waste spread, segragated and compacted iv. 5no. Solar streetlights v. 2no. CCTV Cameras | 4683100101 |  | Kajiado Central | Dalalekutuk |  | Kajiado Municipality | Environment | Municipality of Kajiado |  |  |  |  | 10000000 | 10000000 | 10000000 | CGK | CGK | 10000000 | N/A | 10000000 |  |  |  |  | Ongoing | 80%
14 | Construction Of Outpatient Department Block And Toilet At Oloomunyi Dispensary In Dalalekutuk Ward | Construction Of Outpatient Department Block And Toilet At Oloomunyi Dispensary | i. 1no. Outpatient Department Block ii. 1no. Toilet | i. 1no. Outpatient Department Block ii. 1no. Toilet | 4683100200 |  | Kajiado Central | Dalalekutuk |  | 4682100100 | Health | Municipality of Kajiado |  |  |  |  | 5000000 | 5000000 | 5000000 | CGK | CGK | 5000000 | N/A | 5000000 |  |  |  |  | Ongoing | 90%
15 | Orinie sandpan | Fencing of Orinie sandpan | Fencing of Orinie sandpan | Fencing of Orinie sandpan | 4683100300 |  | Kajiado Central | Dalalekutuk |  | Kajiado Municipality | Water | Municipality of Kajiado |  |  |  |  | 2000000 | 2000000 | 2000000 | CGK | CGK | 2000000 | N/A | 2000000 |  |  |  |  | ongoing
16 | Ole Narau borehole | Fencing of borehole | Fencing of borehole | Fencing of borehole | 4683100300 |  | Kajiado Central | Dalalekutuk |  | Kajiado Municipality | Road, Public Works, Energy and Transport | Municipality of Kajiado |  |  |  |  | 1000000 | 1000000 | 1000000 | CGK | CGK | 1000000 | N/A | 1000000 |  |  |  |  | Completed | 100%
17 | Tikoishi road | Grading and Murraming | Grading and Murraming | Grading and Murraming | 4683100400 |  | Kajiado Central | Ildamat |  | Kajiado Municipality | Road, Public Works, Energy and Transport | Municipality of Kajiado |  |  |  |  | 7000000 | 7000000 | 7000000 | CGK | CGK | 7000000 | N/A | 7000000 |  |  |  |  | ongoing | 80%
18 | Oloosuyian - Esukuta road | Grading and Murraming | Grading and Murraming | Grading and Murraming | 4683100400 |  | Kajiado Central | Ildamat |  | Kajiado Municipality | Road, Public Works, Energy and Transport | Municipality of Kajiado |  |  |  |  | 6000000 | 6000000 | 6000000 | CGK | CGK | 6000000 | N/A | 6000000 |  |  |  |  | ongoing | 80%
19 | Naningoi road | Grading and Murraming | Grading and Murraming | Grading and Murraming | 4683100400 |  | Kajiado Central | Ildamat |  | Kajiado Municipality | Road, Public Works, Energy and Transport | Municipality of Kajiado |  |  |  |  | 7000000 | 7000000 | 7000000 | CGK | CGK | 7000000 | N/A | 7000000 |  |  |  |  | ongoing | 80%
20 | Olkiloriti road | Grading and Murraming | Grading and Murraming | Grading and Murraming | 4683100400 |  | Kajiado Central | Ildamat |  | Kajiado Municipality | Road, Public Works, Energy and Transport | Municipality of Kajiado |  |  |  |  | 5500000 | 5500000 | 5500000 | CGK | CGK | 7000000 | N/A | [5 empty] | ongoing | 80%
21 | Cemetry | Construction of cemetry site house | Construction of cemetry site house | Construction of cemetry site house | 4683100200 |  | Kajiado Central | Ildamat |  | Kajiado Municipality | Health | Municipality of Kajiado |  |  |  |  | 1000000 | 1000000 | 1000000 | CGK | CGK | 5500000 | N/A | [5 empty] | ongoing | 80%
22 | Ildamat Stadium toilets | Construction of toilets and septic tank | Construction of toilets and septic tank | Construction of toilets and septic tank | 4683100300 |  | Kajiado Central | Ildamat |  | Kajiado Municipality | Road, Public Works, Energy and Transport | Municipality of Kajiado |  |  |  |  | 1500000 | 1500000 | 1500000 | CGK | CGK | 1000000 | N/A | [5 empty] | ongoing | 80%
23 | Kwa Meja- Sajiloni road | Grading and Murraming | Grading and Murraming | Grading and Murraming | 4683100400 |  | Kajiado Central | Dalalekutuk |  | Kajiado Municipality | Road, Public Works, Energy and Transport | Municipality of Kajiado |  |  |  |  | 4000000 | 4000000 | 4000000 | CGK | CGK | 1500000 | N/A | [5 empty] | ongoing | 80%
24 | Impiro dairy | Construction of dairy house | Construction of dairy house | Construction of dairy house | 4683100700 |  | Kajiado Central | Dalalekutuk |  | Kajiado Municipality | Road, Public Works, Energy and Transport | Municipality of Kajiado |  |  |  |  | 5000000 | 5000000 | 5000000 | CGK | CGK | 4000000 | N/A | [5 empty] | ongoing | 80%
25 | Motor bike shades | Construction of motor bikes shades at Inkinye, Kitengela Medical, Curio and Blue Sky | Construction of motor bikes shades at Inkinye, Kitengela Medical, Curio and Blue Sky | Construction of motor bikes shades at Inkinye, Kitengela Medical, Curio and Blue Sky | 4683100400 |  | Kajiado Central | Dalalekutuk |  | Kajiado Municipality | Road, Public Works, Energy and Transport | Municipality of Kajiado |  |  |  |  | 2000000 | 2000000 | 2000000 | CGK | CGK | 5000000 | N/A |  | 80% |  |  |  | completed | 100%
26 | Nenkashe primary | Construction of 1 ECDE Classroom | i. 1ECDE Classroom | i. 1ECDE Classroom | 4683100500 |  | Kajiado Central | Dalalekutuk |  | 3110200 | Education Youth and Sports | Municipality of Kajiado |  |  |  |  | 1800000 | 1800000 | 1800000 | CGK | CGK | 2000000 | N/A | [5 empty] | ongoing | 75%
27 | Iseuri primary school | Construction of 1 ECDE Classroom | i. 1ECDE Classroom | i. 1ECDE Classroom | 4683100500 |  | Kajiado Central | Dalalekutuk |  | 3110200 | Education Youth and Sports | Municipality of Kajiado |  |  |  |  | 1800000 | 1800000 | 1800000 | CGK | CGK | 1800000 | N/A | [5 empty] | ongoing | 90%
28 | Saina Annex | Construction of 1 ECDE Classroom | i. 1ECDE Classroom | i. 1ECDE Classroom | 4683100500 |  | Kajiado Central | Dalalekutuk |  | 3110200 | Education Youth and Sports | Municipality of Kajiado |  |  |  |  | 1800000 | 1800000 | 1800000 | CGK | CGK | 1800000 | N/A | [5 empty] | ongoing | 90%
29 | Nalala ECDE | Construction of 1 ECDE Classroom | i. 1ECDE Classroom | i. 1ECDE Classroom | 4683100500 |  | Kajiado Central | Dalalekutuk |  | 3110200 | Education Youth and Sports | Municipality of Kajiado |  |  |  |  | 1800000 | 1800000 | 1800000 | CGK | CGK | 1800000 | N/A | [5 empty] | ongoing | 90%
30 | Isilale primay school | Construction of 1 ECDE Classroom | i. 1ECDE Classroom | i. 1ECDE Classroom | 4683100500 |  | Kajiado Central | Dalalekutuk |  | 3110200 | Education Youth and Sports | Municipality of Kajiado |  |  |  |  | 1800000 | 1800000 | 1800000 | CGK | CGK | 1800000 | N/A | [5 empty] | Ongoing | 90%
31 |  | NGONG MUNICIPALITY | [20 empty] | N/A
32 | Tarmacking of Kobil-Olooloua road cathedrol JNC B50 | Road Infrastructure and Storm water Drainage | •Road Construction to Bitumen Standards – 1.0km,storm water drainage,solar street lighting,NMTs- 1.0km | road tarmacked and drainage control | 4683100100 | Kenya Urban Support Programme (KUSP-UDG) | Kajiado North | Oloolua |  | Ngong Municipality | Municipality of Ngong | Municipality of Ngong | 2019-02-01 | 2019-02-01 | 2020-08-01 |  | 51067828.4 | 51067828.4 | 51067828.4 | WorldBank throught KUSP | World Bank | N/A | 51067828.4 | 51067828.4 |  |  |  |  | Completed | 100%
33 | Tarmacking of 1.4 JNC B50 Kiserian Primary JNC Magadi | Road Infrastructure and Storm water Drainage | •Road Construction to Bitumen Standards – 1.4kms,Storm water drainage-1.4km,Solar street lighting,NMTs 1.4kms | road tarmacked and drainage control | 4683100100 | Kenya Urban Support Programme (KUSP-UDG) | Kajiado North | Keekonyokie |  | Ngong Municipality | Municipality of Ngong | Municipality of Ngong | 2019-03-01 | 2019-08-01 | 2020-02-01 |  | 53,208,855.48. | 53,208,855.48. | 53,208,855.48. | WorldBank throught KUSP | World Bank | N/A | 53,208,855.48. | 53,208,855.48. |  |  |  |  | Completed | 100%
34 | Tarmacking of 1km Kenol Kobi-Wama dispensary Mechanic parcking land road | Road Infrastructure | •Road Construction to Bitumen Standards – 1.0kms,Storm water drainage-1.0kms,Solar street lighting,NMTs-1.0kms | road tarmacked and drainage control | 4683100100 | Kenya Urban Support Programme (KUSP-UDG) | Kajiado North | ONgata rongai | ONgata rongai | Ngong Municipality | Municipality of Ngong | Municipality of Ngong | 2019-04-01 | 2019-04-01 | 2020-02-01 |  | 69117700.65 | 69117700.65 | 69117700.65 | WorldBank throught KUSP | World Bank | N/A | 69117700.65 | 69117700.65 |  |  |  |  | Completed | 100%
35 | Decomposing of Ngong dumpsite phase 1 | Waste management | Environmental protection,reduce risk and restore land for safe use | reduced environmental hazards and land restoration | 4683100100 | Kenya Urban Support Programme (KUSP-UDG) | Kajiado North | Ngong | Ngong | Ngong Municipality | Municipality of Ngong | Municipality of Ngong | 2019-08-01 | 2019-08-01 | 2020-02-01 |  | 48784380 | 48784380 | 48784380 | WorldBank throught KUSP | World Bank | 10784380 | 38000000 | 48784380 | 100% |  |  |  | Completed | 100% | [10 empty] | yes
36 | Tarmacking of 1.1km Juanco-Olepolos road | Road Infrastruture & Storm water drainage | •Road Construction to Bitumen Standards – 1.1kms,Storm water drainage,Solar street lighting,NMTs-1.1kms | benefited 5,000+ people and 400+ formal and informal business | 4683100100 | Kenya Urban Support Programme (KUSP-UDG) | Kajiado North | Oloolua | Oloolua | Ngong Municipality | Municipality of Ngong | Municipality of Ngong |  | 2021-06-01 | 2021-12-01 |  | Kshs. 57,378,472.00. | Kshs. 57,378,472.00. | Kshs. 57,378,472.00. | WorldBank throught KUSP | World Bank | 0 | 57,378,472.00. | 57,378,472.00. | 100% | 0 | 0 |  | Completed | 100%
37 | Upgrading of 800M Kiserian market roads | Road Infrastruture & Storm water drainage | •Road upgrade to Cabro Standards – 800 Meters.Storm water drainage-800meters,Solar street lighting,NMTs-800meters | benefited 20,000+ kiserian residents and 5,000 +formal & informal business | 4683100100 | Kenya Urban Support Programme (KUSP-UDG) | Kajiado West | Keekonyokie | Kiserian | Ngong Municipality | Municipality of Ngong | Municipality of Ngong |  |  |  |  | 62327588.8 | 62327588.8 | 62327588.8 | WorldBank throught KUSP | World Bank | 0 | 62327588.8 | 62327588.8 | 100% | 0 | 0 |  | Completed | 100%
38 | Tamarking of 1.5 Clean Shelf Saitoti Hospital gataka road | Road Infrastruture | •Road Construction to Bitumen Standards – 1.5kms,Storm water drainage 1.5kms,Solar street lighting,NMTs 1.5kms | benefited 18,000 Ongata rongai residents and 10,000+ formal & informal business | 4683100100 | Kenya Urban Support Programme (KUSP-UDG) | Kajiado North | Ongata rongai |  | Ngong Municipality | Municipality of Ngong | Municipality of Ngong | 2022-03-01 | 2023-03-01 | 2023-03-01 |  | 82817654.8 | 82817654.8 | 82817654.8 | WorldBank throught KUSP | World Bank |  | 82817654.8 | 82817654.8 | 100% | 0 | 0
39 | Construction of box culvert Ngong public toilet & beautification partk | Road Infrastructur & Sanitation | Box Culvert ,Public Toilet,Beautification park | benefited 23,000 Ngong residents and 1000+ formal & informal business | 4683100100 | Kenya Urban Support Programme (KUSP-UDG) | Kajiado North | Ngong |  | Ngong Municipality | Municipality of Ngong | Municipality of Ngong | 2022-03-01 | 2023-03-01 | 2023-03-01 |  | 26610881.4 | 26610881.4 | 26610881.4 | WorldBank throught KUSP | World Bank | 0 | 26610881.4 | 26610881.4 | 100% | 0 | 0
40 | Oloika Valley & Nosim link road | Construction of Culverts and drainage | Oloika valley road constructed | road maintained and drainage control | 4683100400 |  | Kajiado North | Ngong |  | Ngong Municipality |  | Municipality of Ngong |  |  |  |  | 3500000
41 | PCEA- Kimani road | Construction of cabros | Construction of cabros | road maintained and drainage control | 4683100400 |  | Kajiado North | Nkaimurunya |  | Ngong Municipality |  | Municipality of Ngong |  | 2025-07-24 | 2025-06-25 |  | 3500000 | 5000000 | 5000000 | CGK | CGK
42 | Vicadec/Simba road | Construction of Culverts and drainage | Construction of Culverts and drainage | road maintained and drainage control | 4683100400 |  | Kajiado North | Nkaimurunya |  | Ngong Municipality | roads | Municipality of Ngong |  | 2025-07-24 | 2025-06-25 |  | 3500000 | 3000000 | 3000000 | CGK | CGK
43 | Umeme road | Grading and Murraming | Grading and Murraming | road gradded and murramed | 4683100400 |  | Kajiado North | Nkaimurunya |  | Ngong Municipality | roads | Municipality of Ngong |  | 2025-07-24 | 2025-06-25 |  | 1000000 | 1000000 | 1000000 | CGK | CGK
44 | Bondeni salvation | construction of drainage | construction of drainage | road gradded and murramed | 4683100400 |  | Kajiado North | Nkaimurunya |  | Ngong Municipality | roads | Municipality of Ngong |  | 2025-07-24 | 2025-06-25 |  | 3500000 | 3500000 | 3500000 | CGK | CGK
45 | Ole Sakuda road | Grading and Murraming | Grading and Murraming | road gradded and murramed | 4683100400 |  | Kajiado North | Nkaimurunya |  | Ngong Municipality | roads | Municipality of Ngong |  | 2025-07-24 | 2025-06-25 |  | 1500000 | 1500000 | 1500000 | CGK | CGK
46 | Free pentecoastal /Hanest | Construction of drainage & culverts | Construction of drainage & culverts | drainage and culverts maintained | 4683100400 |  | Kajiado North | Nkaimurunya |  | Ngong Municipality | roads | Municipality of Ngong |  | 2025-07-24 | 2025-06-25 |  | 1500000 | 1500000 | 1500000 | CGK | CGK
47 | Kanyiriri Road | Grading and Murraming | Grading and Murraming | kanyiri road graded & murramed | 4683100400 |  | Kajiado North | Nkaimurunya |  | Ngong Municipality | roads | Municipality of Ngong |  | 2025-07-24 | 2025-06-25 |  | 3000000 | 3000000 | 3000000 | CGK | CGK
48 | Mayor Road No.22 | Grading and Murraming | Grading and Murraming | Mayor road graded & murramed | 4683100400 |  | Kajiado North | Nkaimurunya |  | Ngong Municipality | roads | Municipality of Ngong |  | 2025-07-24 | 2025-06-25 |  | 1500000 | 1500000 | 1500000 | CGK | CGK
49 | Gituguta water project | Fencing & piping | Fencing & piping | water project fenced & piped | 4683100300 |  | Kajiado North | Nkaimurunya |  | Ngong Municipality | roads | Municipality of Ngong |  | 2025-07-24 | 2025-06-25 |  | 3000000 | 3000000 | 3000000 | CGK | CGK | [7 empty] | Ongoing | 100%
50 | Ngong Hospital borehole | Drilling | Drilling | Ngong hospital borehole drilled | 4683100200 |  | Kajiado North | Nkaimurunya | Gataka | Ngong Municipality | roads | Municipality of Ngong |  | 2025-07-24 | 2025-06-25 |  | 3000000 | 3000000 | 3000000 | CGK | CGK | [7 empty] | Ongoing | 85% | [14 empty] | complete but not equiped
51 | Social Hall | Renovation of Ngong social hall | Renovation of Ngong social hall | Ngong hospital social hall renovated | 4683100400 |  | Kajiado North | Ngong | Laiser Hills View | Ngong Municipality | roads | Municipality of Ngong |  | 2025-07-24 | 2025-06-25 |  | 1000000 | 1000000 | 1000000 | CGK | CGK | [7 empty] | Ongoing | 68%
52 | Mathare River | Placement of gabbions along Mathare river | drainage management | mathare river gabions placed | 4685100200 |  | Kajiado North | Ngong | Empakasi | Ngong Municipality | roads | Municipality of Ngong |  | 2025-07-24 | 2025-06-25 |  | 3000000 | 3000000 | 3000000 | CGK | CGK | [7 empty] | Ongoing | 70%
53 | Jua Kali Shades | construction of jua kali shades | Provide shades for boda boda riders | boda boda shades constructed | 4685100300 |  | Kajiado North | Ngong | Kware | Ngong Municipality | roads | Municipality of Ngong |  | 2025-07-24 | 2025-06-25 |  | 2000000 | 2000000 | 2000000 | CGK | CGK | [7 empty] | Ongoing
54 | Riverside road | Grading and Murraming | Improve road accesibility and support economic activities | riverside road graded | 4685100300 |  | Kajiado North | Ngong | Empakasi | Ngong Municipality | roads | Municipality of Ngong |  | 2025-07-24 | 2025-06-25 |  | 2000000 | 2000000 | 2000000 | CGK | CGK | [7 empty] | Ongoing | 90%
55 | PEC - Kipepeo road | Grading and Murraming | Improve road accesibility and support economic activities | PEC-Kipepo road graded | 4685100300 |  | Kajiado North | Ngong | Kware | Ngong Municipality | roads | Municipality of Ngong |  | 2025-07-24 | 2025-06-25 |  | 2000000 | 2000000 | 2000000 | CGK | CGK | [7 empty] | Ongoing | 90%
56 | Ololaiser gate | Construction of modern gate at Ololaiser High Sc | enhance security | gate constructed | 4685100300 |  | Kajiado North | Ngong | Kware | Ngong Municipality | roads | Municipality of Ngong |  | 2025-07-24 | 2025-06-25 |  | 2000000 | 2000000 | 2000000 | CGK | CGK | [7 empty] | Ongoing | 90%
57 | Prof Saitoti primary school | Construction of 2 ECDE classrooms at Prof Saito | improve ECDE enrollment | enrollment | 4685100300 |  | Kajiado North | Ngong | Kware | Ngong Municipality | roads | Municipality of Ngong |  | 2025-07-24 | 2025-06-25 |  | 3000000 | 3000000 | 3000000 | CGK | CGK | [7 empty] | Ongoing | 90%
58 | Gichagi water project | Installation of elavated steel tank | Increase access to water | Gichagi water tank installed | 4685100200 |  | Kajiado North | Ngong | Empakasi | Ngong Municipality | roads | Municipality of Ngong |  | 2025-07-24 | 2025-06-25 |  | 4000000 | 4000000 | 4000000 | CGK | CGK | [7 empty] | Ongoing | 90%
59 | Ngong CBD roads | Installation of cabro 300 meters within Ngong CB | Improve road accesibility and support economic activities | Ngong CBD roads maintained | 4685100300 |  | Kajiado North | Ngong | Ngong Township | Ngong Municipality | roads | Municipality of Ngong |  | 2025-07-24 | 2025-06-25 |  | 5000000 | 5000000 | 5000000 | CGK | CGK | [7 empty] | Ongoing | 90%
60 | Riverside road improvement | Construction of box culvert and drainage | Improve road accesibility and support economic activities | riverside road graded | 4685100300 |  | Kajiado North | Ngong | Umoja | Ngong Municipality | roads | Municipality of Ngong |  | 2025-07-24 | 2025-06-25 |  | 1000000 | 1000000 | 1000000 | CGK | CGK | [7 empty] | Ongoing
61 | Bulbul /Kariobangi- Forest view | Construction of box culvert and drainage | Construction of box culvert and drainage | culverts constructed | 4685100300 |  | Kajiado North | Ngong | Umoja | Ngong Municipality | roads | Municipality of Ngong |  | 2025-07-24 | 2025-06-25 |  | 4000000 | 4000000 | 4000000 | CGK | CGK
62 | Kangawa - Kihiko - Inspector road | Repair of Kihiko road | Improve road accesibility and support economic activities | kihiko road repaired | 4685100300 |  | Kajiado North | Ngong | Jua Kali | Ngong Municipality | roads | Municipality of Ngong |  | 2025-07-24 | 2025-06-25 |  | 7500000 | 7500000 | 7500000 | CGK | CGK
63 | Kangawa olepolos | Murraming, Drainage & lighting | Improve road accesibility ,drainage & security |  | 4685100300 |  | Kajiado North | Ngong | Elpaso | Ngong Municipality | roads | Municipality of Ngong |  | 2025-07-24 | 2025-06-25 |  | 2500000 | 2500000 | 2500000 | CGK | CGK
65 | Bulbul Cemetry | Construction of shade, toilets and fencing of cemetery | Construction of shade, toilets and fencing of cemetery | bulbul cemetry shades & toilets constructed | 4685100100 |  | Kajiado North | Olkeri | Ngong Township | Ngong Municipality | Education | Municipality of Ngong | 2024 | 2025-07-24 | 2025-06-25 |  | 3500000 | 1500000 | 1500000 | CGK | CGK
66 | Enoomatasiani ECDE | Construction of 4 toilets,kitchen & painting of ECDE | Construction of 4 toilets,kitchen & painting of ECDE | ECDE,toilets,kitchen & painting complete | 4685100400 |  | Kajiado North | Olkeri | Maasai/Bondeni | Ngong Municipality | Roads & transport | Municipality of Ngong |  | 2025-07-24 | 2025-06-25 |  | 3500000 | 1500000 | 1500000 | CGK | CGK | [7 empty] | Ongoing
67 | Oloika Valley & Nosim link roa | Grading and Murraming & Culverts | Improve road accesibility and support economic activities | oloika valley road graded & murramed | 4685100300 |  | Kajiado North | Olkeri | Gichagi |  | Roads & transport | Municipality of Ngong |  | 2025-07-24 | 2025-06-25 |  | 3500000 | 4500000 | 4500000 | CGK | CGK | [7 empty] | Ongoing
68 | Memusi councillor - Rapasi road | Grading , Murraming , Expansion and drainage | Improve road accesibility and support economic activities | memusi rapasi road graded & murramed | 4685100300 |  | Kajiado North | Olkeri | Ngong Township |  | Roads & transport | Municipality of Ngong |  | 2025-07-24 | 2025-06-25 |  | 3500000 | 2500000 | 2500000 | CGK | CGK | [7 empty] | Ongoing
69 | Tajiri - Rhino road | Laying of foundation stones grading, murraming | Improve road accesibility and support economic activities | road gradded and murramed | 4685100300 |  | Kajiado North | Olkeri | Ngong Township |  | Roads & transport | Municipality of Ngong |  | 2025-07-24 | 2025-06-25 |  | 3500000 | 3500000 | 3500000 | CGK | CGK | [7 empty] | Ongoing
70 | PCEA - Nalepo upper Matasia r | Grading , Murraming & Culverts | Improve road accesibility and support economic activities | road gradded and murramed | 4685100300 |  | Kajiado North | Olkeri | Zambia -Hiltop |  | Roads & transport | Municipality of Ngong |  | 2025-07-24 | 2025-06-25 |  | 2000000 | 3500000 | 3500000 | CGK | CGK | [7 empty] | Ongoing
71 | Kisoronye forest road | Grading , Murraming & Culverts | Improve road accesibility and support economic activities | road gradded and murramed | 4685100300 |  | Kajiado North | Olkeri | Forest view- Kangaw |  | Roads & transport | Municipality of Ngong |  | 2025-07-24 | 2025-06-25 |  | 3500000 | 3500000 | 3500000 | CGK | CGK | [7 empty] | completed
72 | Ruben Wamea Road | Purchase of a fedder road | Improve road accesibility and support economic activities | road gradded and murramed | 4685100300 |  | Kajiado North | Olkeri | Kangawa - Kihiko |  | Roads & transport | Municipality of Ngong |  | 2025-07-24 | 2025-06-25 |  | 1500000 | 1500000 | 1500000 | CGK | CGK | [7 empty] | completed
73 | Ruguru baraka road | Grading , Murraming & Culverts | Improve road accesibility and support economic activities | road gradded and murramed | 4685100300 |  | Kajiado North | Olkeri | Karei /Sisters road |  | Roads & transport | Municipality of Ngong |  | 2025-07-24 | 2025-06-25 |  | 1500000 | 1500000 | 1500000 | CGK | CGK | [7 empty] | completed
74 | Kwa Njega - Lemelepo,Ole Kis | Grading , Murraming & Culverts | Improve road accesibility and support economic activities | road gradded and murramed | 4685100300 |  | Kajiado North | Olkeri | Bulbul |  | Roads & transport | Municipality of Ngong |  | 2025-07-24 | 2025-06-25 |  | 2000000 | 2000000 | 2000000 | CGK | CGK | [7 empty] | completed
75 | Arap Moi ECDE | Construction of 4 in one toilets | Improve sanitation | Arap moi ECDE toilets constructed | 4685100300 |  | Kajiado North | Olkeri | OLoolua | Education | Education | Municipality of Ngong |  | 2025-07-24 | 2025-06-25 |  | 1500000 | 1500000 | 1500000 | CGK | CGK | [7 empty] | completed
76 | Buffalo close road | Grading, Murraming & culverts | Improve road accesibility and support economic activities |  | 4685100300 |  | Kajiado North | Olkeri | Bulbul |  |  | Municipality of Ngong |  | 2025-07-24 | 2025-06-25 |  | 2000000 | 1500000 | 1500000 | CGK | CGK | [7 empty] | completed
77 | 5 Bodaboda shades with a side | Construction of bodaboda shades across the ward | Provide shades for boda boda riders |  | 4685100300 |  | Kajiado North | Olkeri | wardwide | Public works | Public works | Municipality of Ngong |  | 2025-07-24 | 2025-06-25 |  | 1000000 | 2500000 | 2500000 | CGK | CGK | [7 empty] | completed
78 | Sungura close | Installation of high mast | Improve security | sungura road maintained | 4685100300 |  | Kajiado North | Ongata rongai | Lower Matasia | Public works | Public works | Municipality of Ngong |  | 2025-07-24 | 2025-06-25 |  | 2000000 | 1500000 | 1000000 | CGK | CGK | [7 empty] | completed
79 | Chui lane | Grading ,Murraming & Drainage | Improve road accesibility and support social & economic activities | Chui road maintained | 4685100300 |  | Kajiado North |  | Upper Nkoroi | Roads | Roads | Municipality of Ngong |  | 2025-07-24 | 2025-06-25 |  | 2000000 | 2000000 | 2000000 | CGK | CGK | [7 empty] | completed |  | Completed
80 | Simba drive road | Grading ,Murraming & Drainage | Improve road accesibility and support social & economic activities | Simba road maintainive roadd | 4685100300 |  | Kajiado North |  | Olkeri | Roads | Roads | Municipality of Ngong |  | 2025-07-24 | 2025-06-25 |  | 2000000 | 1000000 | 1000000 | CGK | CGK | [7 empty] | completed |  | Completed
81 | 4th Avenue road | Grading ,Murraming & Drainage | Improve road accesibility and support social & economic activities | 4th road maintainue roadd | 4685100300 |  | Kajiado North |  | Lekurruki | Roads | Roads | Municipality of Ngong |  | 2025-07-24 | 2025-06-25 |  | 2000000 | 2000000 | 2000000 | CGK | CGK | [7 empty] | completed |  | Completed
82 | Mugaa road | Grading ,Murraming & Drainage | Improve road accesibility and support social & economic activities | Mugaa road maintainadd | 4685100300 |  | Kajiado North |  | Lekurruki | Roads | Roads | Municipality of Ngong |  | 2025-07-24 | 2025-06-25 |  | 2000000 | 1500000 | 1500000 | CGK | CGK | [7 empty] | completed |  | Completed
83 | Kingdom hall road | Grading ,Murraming & Drainage | Improve road accesibility and support social & economic activities | Kingdom road maintainhall roadd | 4685100300 |  | Kajiado North |  | Upper Matasia | Roads | Roads | Municipality of Ngong |  | 2025-07-24 | 2025-06-25 |  | 4000000 | 1500000 | 1500000 | CGK | CGK | [7 empty] | completed |  | Completed
84 | Olarro- Masai gate road | Grading ,Murraming & Drainage | Improve road accesibility and support social & economic activities | Olarro road maintainMasai gate roadd | 4685100300 |  | Kajiado North |  | Ilmerijo | Roads | Roads | Municipality of Ngong |  | 2025-07-24 | 2025-06-25 |  | 3000000 | 2000000 | 2000000 | CGK | CGK | [7 empty] | completed
85 | Ole Pasha ECDE | Equipping of the ECDE | Improve learning environment | Ole learning he Ene Ea ECDEi | 4685100400 |  | Kajiado North |  | Ilmerijo | Roads | Roads | Municipality of Ngong |  | 2025-07-24 | 2025-06-25 |  | 1000000 | 2000000 | 2000000 | CGK | CGK | [7 empty] | completed
86 | Talanta Social Hall Boxing ring | Purchase of a boxing ring at talanta hall | promote sports and enhance safety | boxing ring purchased | 4685100400 |  | Kajiado North |  | Lemelepo | Youth and Sports | Youth and Sports | Municipality of Ngong |  | 2025-07-24 | 2025-06-25 |  | 1500000 | 2000000 | 2000000 | CGK | CGK | [7 empty] | completed
87 | Olekasasi Stadium | Purchase of goal post | Encourage youth engagement and promote sports | Goal post purchased | 4685100400 |  | Kajiado North |  | Lemelepo | Youth and Sports | Youth and Sports | Municipality of Ngong |  | 2025-07-24 | 2025-06-25 |  | 500000 | 4000000 | 4000000 | CGK | CGK | [7 empty] | Ongoin
88 | Ole Kasasi hospital maternity wing | Renovation of maternity wing | Improve access to health services | complete maternity wing | 4685100100 |  | Kajiado North | Ongata rongai | Lekurruki | Health | Health | Municipality of Ngong |  | 2025-07-24 | 2025-06-25 |  | 2959160 | 3000000 | 3000000 | CGK | CGK | [7 empty] | ongoin
89 | Kongoni road | Installation of street light | Imrove security | Street light installed | 4685100300 |  | Kajiado North | Ongata rongai | a cross the ward |  |  | Municipality of Ngong |  | 2025-07-24 | 2025-06-25 |  | 1000000 | 1000000 | 1000000 | CGK | CGK | [7 empty] | Not started
90 | Ole motondo Road | Installation of street light | Imrove security | Street light installed | 4685100300 |  | Kajiado North | Ongata rongai | Scheme 6 |  |  | Municipality of Ngong |  | 2025-07-24 | 2025-06-25 |  | 1500000 | 1500000 | 1500000 | CGK | CGK | [7 empty] | Not started
91 | Ole Pere road | Grading ,Murraming & Drainage | Improve road accesibility and support social & economic activities | Ole pere road murramed & drainage maintained | 4685100300 |  | Kajiado North | Ongata rongai | Endumoto |  | Roads | Municipality of Ngong |  | 2025-07-24 | 2025-06-25 |  | 500000 | 500000 | 500000 | CGK | CGK | [7 empty] | Not started
92 | Academy close road | Excavation and backfilling | Improve road accesibility and support social & economic activities | road backfilled and excavated | 4685100300 |  | Kajiado North | Ongata rongai | Endumoto |  |  | Municipality of Ngong |  | 2025-07-24 | 2025-06-25 |  | 3000000 | 3000000 | 3000000 | CGK | CGK | [7 empty] | Not started
93 | Integrated waste recovery centre | construction of a waste recovery centre fully established with the requisite instalation of recycling equipment for value addition | Improve waste management and value adition | Integrated waste management plan constructed | 4685100300 |  | Kajiado North | Ngong | Rongai |  | Environment | Municipality of Ngong |  | 2025-07-24 | 2025-06-25 |  | 150000000 | 150000000 | 150000000 | CGK | CGK | 150000000 | [6 empty] | Not started
94 | Nkaimurunya - Rongai Market | Land acquisition and construction of market | Improve business space | land purchased and market constructed | 4685100300 |  | Kajiado North | Ngong | Laiser |  | Trade | Municipality of Ngong |  | 2025-07-24 | 2025-06-25 |  | 50000000 | 50000000 | 50000000 | CGK | CGK | [7 empty] | Not started
95 | Ngong Stadium | Leveling and maintenance works for ngong stadium | Ngong Stadium maintainance | Ngong Stadium leveled maintained | 4685100300 |  | Kajiado North | Ngong | Rongai |  | youth & sports | Municipality of Ngong |  | 2025-07-24 | 2025-06-25 |  | 1500000 | 1500000 | 1500000 | CGK | CGK | [7 empty] | Not started
96 |  | KITENGELA MUNICIPALITY | [6 empty] | Maasai lodge |  |  |  |  | 2025-07-24 | 2025-06-25 |  |  |  |  | CGK | CGK
97 | Ole Mesoongo-Karaine road | Grading and Murraming; | Improve road accesibility and support social & economic activities | ole mesoongo road graded | 4685100300 |  | kajiado East |  | Ole Kasasi B |  | Roads & transport |  |  | 2025-07-24 | 2025-06-25 |  | 8000000 | 8000000 |  | CGK | CGK
98 | Kajiado East Technical Drift | Construction of a drift | Improve road accesibility and support social & economic activities | Technical road drift constructed | 4685100300 |  | kajiado East |  | Ole Kasasi |  | Roads & transport | Municipality of Kitengela |  | 2025-07-24 | 2025-06-25 |  | 2000000 | 2000000 |  | CGK | CGK
99 | Baraka, Sixes-Eastmart, Treewa Road | Grading & Murraming | Improve road accesibility and support social & economic activities | baraka Eastmart road graded | 4685100300 |  | kajiado East |  | Rongai |  | Roads & transport | Municipality of Kitengela |  | 2025-07-24 | 2025-06-25 |  | 11000000 | 20000000 |  | CGK | CGK
100 | Treewa Drive | Grading & Murraming | Improve road accesibility and support social & economic activities | treewa road graded | 4685100300 |  | kajiado East |  | Rongai |  | Roads & transport | Municipality of Kitengela |  | 2025-07-25 | 2025-06-26 |  | 2000000 | 2000000 |  | CGK | CGK
101 | Kyangombe High Mast | Installation of a high mast | Improve security | High security mast installatigh o | 4685100300 |  | kajiado East |  | Ole Kasasi |  | Public works | Municipality of Kitengela |  | 2025-07-26 | 2025-06-27 |  | 2000000 | 2000000 |  | CGK | CGK
102 | Kimalat via Kilakirr | Murraming, Grading & Culvating | Improve road accesibility and support social & economic activities |  | 4685100300 |  | kajiado East |  | Scheme 6 |  | Roads & transport | Municipality of Kitengela |  | 2025-07-27 | 2025-06-28 |  | 3000000 | 3000000 |  | CGK | CGK
103 | Isinya lexo via mwange road | Murraming, Grading & Culvating | Improve road accesibility and support social & economic activities |  | 4685100300 |  | kajiado East |  | Rongai |  | Roads & transport | Municipality of Kitengela |  | 2025-07-28 | 2025-06-29 |  | 3000000 | 3000000 |  | CGK | CGK
104 | Pipeline via End time Road | Murraming, Grading & Culvating | Improve road accesibility and support social & economic activities |  | 4685100300 |  | kajiado East |  | Rongai |  | Roads & transport | Municipality of Kitengela |  | 2025-07-29 | 2025-06-30 |  | 4000000 | 4000000 |  | CGK | CGK
105 | PCEA road | Murraming, Grading & Culvating | Improve road accesibility and support social & economic activities |  | 4685100300 |  | kajiado East |  | Rongai |  | Roads & transport | Municipality of Kitengela |  | 2025-07-30 | 2025-07-01 |  | 1000000 | 1000000 |  | CGK | CGK
106 | Lucy base via Karoyia Road | Murraming, Grading & Culvating | Improve road accesibility and support social & economic activities |  | 4685100300 |  | kajiado East |  |  |  | Roads & transport | Municipality of Kitengela |  | 2025-07-31 | 2025-07-02 |  | 2000000 | 2000000 |  | CGK | CGK
107 | Acacia Feedr Road | Murraming, Grading & Drainage | Improve road accesibility and support social & economic activities |  | 4685100300 |  | kajiado East |  |  |  | Roads & transport | Municipality of Kitengela |  | 2025-08-01 | 2025-07-03 |  | 4000000 | 4000000 |  | CGK | CGK
108 | Sifa-Farm-Old Namanga-Government Road | Murraming, Grading & Drainage | Improve road accesibility and support social & economic activities |  | 4685100300 |  | kajiado East |  |  |  | Roads & transport | Municipality of Kitengela |  | 2025-08-02 | 2025-07-04 |  | 4000000 | 4000000 |  | CGK | CGK
109 | Twala-Green View Area-Bridge | Murraming, Grading & Drainage-Bridge | Improve road accesibility and support social & economic activities | Twala road View Area-Bridger maintained | 4685100300 |  | kajiado East |  |  |  | Roads & transport | Municipality of Kitengela |  | 2025-08-03 | 2025-07-05 |  | 5000000 | 5000000 |  | CGK | CGK
110 | Happy land-Maji Mazuri Road | Murraming, Grading & Drainage | Improve road accesibility and support social & economic activities |  | 4685100300 |  | kajiado East |  |  |  | Roads & transport | Municipality of Kitengela |  | 2025-08-04 | 2025-07-06 |  | 5000000 | 5000000 |  | CGK | CGK
111 | Sigma - Emakoko Road | Murraming, Grading & Drainage | Improve road accesibility and support social & economic activities |  | 4685100300 |  | kajiado East |  |  |  | Roads & transport | Municipality of Kitengela |  | 2025-08-05 | 2025-07-07 |  | 3000000 | 3000000 |  | CGK | CGK
112 | Mosiro - Metro Road | Murraming, Grading & Drainage | Improve road accesibility and support social & economic activities |  | 4685100300 |  | kajiado East |  |  |  | Roads & transport | Municipality of Kitengela |  | 2025-08-06 | 2025-07-08 |  | 2000000 | 2000000 |  | CGK | CGK | [7 empty] | Not started
113 | Noonkopir - Solar mast Dumpsite | Installation of High Mast | enhance security | securiy enhanced | 4685100300 |  | kajiado East |  |  |  | Public works | Municipality of Kitengela |  | 2025-08-07 | 2025-07-09 |  | 2000000 | 2000000 |  | CGK | CGK | [7 empty] | ongoin
114 | Enkasin ECDE Renovation | Renovation |  | Improved learning environment | 4685100400 |  | kajiado East |  |  |  | Education | Municipality of Kitengela |  | 2025-08-08 | 2025-07-10 |  | 2000000 | 2000000 |  | CGK | CGK | [7 empty] | Not started
115 | Kisaju Dipak Girls Sec | Construction of Girls Dormitory | Increase acomodation and enrollement | Improved learning environment | 4685100400 |  | kajiado East |  |  |  | Education | Municipality of Kitengela |  | 2025-08-09 | 2025-07-11 |  | 5000000 | 5000000 |  | CGK | CGK | [7 empty] | completed
116 | Moi Girls Isinya Sec | Construction of two classrooms | Increase enrollment | Improved learning environment | 4685100400 |  | kajiado East | Kaputiei North | Isinya |  | Education | Municipality of Kitengela |  | 2025-08-10 | 2025-07-12 |  | 4000000 | 4000000 |  | CGK | CGK | [7 empty] | completed
117 | Sautet ECDE | Construction of ECDE Classroom | Increase enrollment | Increased ECDE enrolment | 4685100400 |  | kajiado East |  |  |  | Education | Municipality of Kitengela |  | 2025-08-11 | 2025-07-13 |  | 2000000 | 2000000 |  | CGK | CGK | [7 empty] | completed
118 | Olepolos ECDE | Construction of ECDE Classroom | Increase enrollment | Increased ECDE enrolment | 4685100400 |  | kajiado East |  |  |  | Education | Municipality of Kitengela |  | 2025-08-12 | 2025-07-14 |  | 2000000 | 2000000 |  | CGK | CGK | [7 empty] | Ongoing
119 | Birika Borehole | Solarization | Improve water accesibility | birika borehole solarized | 4685100200 |  | kajiado East | Kitengela | Olooloitikoshi |  | water | Municipality of Kitengela |  | 2025-08-13 | 2025-07-15 |  | 3000000 | 3000000 |  | CGK | CGK | [7 empty] | Ongoing
120 | Noompopong | Solar Installation and Pump and Tank |  | water accesibility improved | 4685100200 |  | kajiado East |  |  |  | water | Municipality of Kitengela |  | 2025-08-14 | 2025-07-16 |  | 5000000 | 5000000 |  | CGK | CGK | [7 empty] | Ongoing
121 | Isinya Health Center | Renovation of the Health Centre |  | Isinya health centre renovated | 4685100100 |  | kajiado East | Kaputiei North | Isinya |  | Health | Municipality of Kitengela |  | 2025-08-15 | 2025-07-17 |  | 4000000 | 4000000 |  | CGK | CGK | [7 empty] | Ongoing
122 | Boda boda Shades | Construction | Improve road accesibility and support social & economic activities | boda boda shades constructed | 4685100300 |  | kajiado East | Oloolua |  |  | Roads & transport | Municipality of Kitengela |  | 2025-08-16 | 2025-07-18 |  | 3000000 | 3000000 |  | CGK | CGK | [7 empty] | Ongoing
123 | 3T St. Elite World Church Road | Grading and Murraming | Improve road accesibility and support social & economic activities | Church road gradded | 4685100300 |  | kajiado East | Oloolua |  |  | Roads & transport | Municipality of Kitengela |  | 2025-08-17 | 2025-07-19 |  | 3000000 | 3000000 |  | CGK | CGK | [7 empty] | Ongoing
124 | Waiguru Nyamu House Road Vision 2030 | Grading and Murraming | Improve road accesibility and support social & economic activities | road gradded and murramed | 4685100300 |  | kajiado East | Oloolua |  |  | Roads & transport | Municipality of Kitengela |  | 2025-08-18 | 2025-07-20 |  | 3000000 | 3000000 |  | CGK | CGK | [7 empty] | Ongoing
125 | Tropicana Road | Grading and Murraming | Improve road accesibility and support social & economic activities | road gradded and murramed | 4685100300 |  | kajiado East |  |  |  | Roads & transport | Municipality of Kitengela |  | 2025-08-19 | 2025-07-21 |  | 2500000 | 2500000 |  | CGK | CGK | [7 empty] | Ongoing
126 | ACK Trinity Road | Grading and Murraming | Improve road accesibility and support social & economic activities | road gradded and murramed | 4685100300 |  | kajiado East |  |  |  | Roads & transport | Municipality of Kitengela |  | 2025-08-20 | 2025-07-22 |  | 2500000 | 2500000 |  | CGK | CGK | [7 empty] | Ongoing
127 | Birika Matali | Grading Murraming and Drainage | Improve road accesibility and support social & economic activities | road gradded and murramed | 4685100300 |  | kajiado East |  |  |  | Roads & transport | Municipality of Kitengela |  | 2025-08-21 | 2025-07-23 |  | 4000000 | 4000000 |  | CGK | CGK | [7 empty] | Ongoing
128 | Enka Siti Social Hall | Construction of Social Hall | Improve road accesibility and support social & economic activities | road gradded and murramed | 4685100700 |  | kajiado East |  |  |  | Roads & transport | Municipality of Kitengela |  | 2025-08-22 | 2025-07-24 |  | 4000000 | 4000000 |  | CGK | CGK | [7 empty] | Ongoing
129 | Mekel Road | Grading and Murraming | Improve road accesibility and support social & economic activities | road gradded and murramed | 4685100300 |  | kajiado East |  |  |  | Roads & transport | Municipality of Kitengela |  | 2025-08-23 | 2025-07-25 |  | 3000000 | 3000000 |  | CGK | CGK | [7 empty] | Ongoing
130 | Kitengela Boarding Uzima Road | Grading and Murraming | Improve road accesibility and support social & economic activities | road gradded and murramed | 4685100300 |  | kajiado East |  |  |  | Roads & transport | Municipality of Kitengela |  | 2025-08-24 | 2025-07-26 |  | 3600000 | 3600000 |  | CGK | CGK | [7 empty] | Ongoing
131 | Vekaria – Airview-Noonkopir | Grading and Murraming | Improve road accesibility and support social & economic activities | road gradded and murramed | 4685100300 |  | kajiado East |  |  |  | Roads & transport | Municipality of Kitengela |  | 2025-08-25 | 2025-07-27 |  | 3600000 | 3600000 |  | CGK | CGK | [7 empty] | Ongoing
132 | Tuala mugetho – Greenview | Grading and Murraming | Improve road accesibility and support social & economic activities | road gradded and murramed | 4685100300 |  | kajiado East |  |  |  | Roads & transport | Municipality of Kitengela |  | 2025-08-26 | 2025-07-28 |  | 3600000 | 3600000 |  | CGK | CGK | [7 empty] | Ongoing
133 | Panai Jua Kali Hospital Road | Grading and Murraming | Improve road accesibility and support social & economic activities | road gradded and murramed | 4685100300 |  | kajiado East |  |  |  | Roads & transport | Municipality of Kitengela |  | 2025-08-27 | 2025-07-29 |  | 3600000 | 3600000 |  | CGK | CGK | [7 empty] | Ongoing
134 | Birika women diary | Construction | Improve road accesibility and support social & economic activities | Birika women dairy constructed | 3110200 |  | kajiado East |  |  |  | Roads & transport | Municipality of Kitengela |  | 2025-08-28 | 2025-07-30 |  | 3000000 | 3000000 |  | CGK | CGK | [7 empty] | Ongoing
135 | Purchase of Land for ECDE Construction | Metro Kirikao Land Acquisition Land Acquisition | construction of ECDE Classrooms | Land purchased and ECDE constructed | 4685100400 |  | kajiado East |  |  |  | Education | Municipality of Kitengela |  | 2025-08-29 | 2025-07-31 |  | 10000000 | 10000000 |  | CGK | CGK | [7 empty] | Ongoing
136 | Equiping Sholinke Dispensary | Equiping | increase access to health services | equiped sholinke dispensary | 4685100100 |  | kajiado East | Olosirkon | sholinke | Kitengela Municipality | Health | Municipality of Kitengela |  | 2025-08-30 | 2025-08-01 |  | 3600000 | 3600000 |  | CGK | CGK | [7 empty] | Ongoing
137 | Noonkopir Dumpsite Improvement | Dumpsite Rehabilitation | waste management | Dumpsite rehabilitated | 4685100200 | [6 empty] | Municipality of Kitengela |  | 2025-08-31 | 2025-08-02 |  | 10000000 | 10000000 |  | CGK | CGK | [7 empty] | Ongoing
138 |  | NGONG MUNICIPALITY
139 | Ole kasasi Stadium | Leveling of the field | promote sports and enhance safety | olekasasi stadium leveled | 4685100400 |  | Kajiado North |  | Ole Kasasi |  | Education Youth and Sports | Ngong Municipality |  | 1st July 20223 | 30th June 20224 |  | 1000000 | 1000000
140 | Ole kasasi Stadium | Renovation of toilets and shawers | iImprove sanitation status | olekasasi stadium toilets renovated | 4685100400 |  | Kajiado North |  | Ole Kasasi |  | Education Youth and Sports | Ngong Municipality |  | 2nd July 20223 | 31st June 20224 |  | 1000000 | 1000000
141 | Olekasasi Multipurpose Hall | Completion of the multipurpose hall and Equipping of the Kitchen ware | improve social status of the community | multipurpose hall costructed & kitechen equiped | 4685100400 |  | Kajiado North |  | Olekasasi |  | Education Youth and Sports | Ngong Municipality |  | 3rd July 20223 | 32nd June 20224 |  | 3000000 | 3000000
142 | Ole Kasasi Primary School | Construction of special classroom for 50 students | increase access to education for special students | olekasasi special classrooms constructed | 4685100400 |  | Kajiado North |  | Olekasasi |  | Education Youth and Sports | Ngong Municipality |  | 4th July 20223 | 33rd June 20224 |  | 2000000 | 2000000 | [10 empty] | ongoing
143 | Fencing of Nkaimurunya ECDE | Fencing of Nkaimurunya ECDE | improve learning environment & security | Nkaimuruna ECDE fenced | 4685100400 |  | Kajiado North |  | Embakasi |  | Education Youth and Sports | Ngong Municipality |  | 5th July 20223 | 34th June 20224 |  | 4500000 | 4500000 | [6 empty] | 80% |  |  |  | stalled |  | Kenya forest stoped the project
144 | Nakeel Stadium | Piping (1km) & Landscaping | improve sanitation & safety | nakeel sanitation pipiki | 4685100400 |  | Kajiado North |  | Kware |  | Education Youth and Sports | Ngong Municipality |  | 6th July 20223 | 35th June 20224 |  | 3000000 | 3000000 | [10 empty] | completed
145 | Ngong Township Primary School | Construction of four special unit toilets | improve learning environment & safty | Primary learning toilets construct | 4685100400 |  | Kajiado North | Ngong | Ngong Township |  | Education Youth and Sports | Ngong Municipality |  | 7th July 20223 | 36th June 20224 |  | 2000000 | 2000000 | [10 empty] | ongoing
146 | Oloolua ECDE | Completion of Kitchen area; Drainage Construction; Class painting & Furnishing | improve learning environment | oloolua learning compop | 4685100400 |  | Kajiado North | Oloolua | Oloolua |  | Education Youth and Sports | Ngong Municipality |  | 8th July 20223 | 37th June 20224 |  | 2500000 | 2500000 | [10 empty] | ongoing
147 | Embul-bul Community Field | Lighting, Drainage and Carpeting; Tree Planting & Rehabilitation of damaged fence | improve social status of the community & safty | Embulbul community field maintained | 4685100400 |  | Kajiado North | Ngong | Embulbul |  | Education Youth and Sports | Ngong Municipality |  | 9th July 20223 | 38th June 20224 |  | 2000000 | 2000000 | [10 empty] | ongoing
148 | Gataka Health Centre | Completion of upper floor | increase access to health services | Gataka access u flt flealth Centrep | 4685100100 |  | Kajiado North |  | Gataka |  | Health Services | Ngong Municipality |  | 10th July 20223 | 39th June 20224 |  | 4000000 | 4000000 | [10 empty] | ongoing
149 | Oloolua Dispensary | construction of a perimeter wall | improve security | oloolua security consos | 4685100100 |  | Kajiado North |  | Oloolua |  | Health Services | Ngong Municipality |  | 11th July 20223 | 40th June 20224 |  | 3000000 | 3000000 | 3000000 | CGK | CGK |  |  |  | 90% |  |  |  | completed
150 | Ongata Rongai Social Hall | Installation of air conditioner & Equipping (PA system, Tables, 800 plastic chairs and the emergency exit) |  |  | 4685100400 |  | Kajiado North |  | Rongai |  | Public Service, Inspectorate and Social Services | Ngong Municipality |  | 12th July 20223 | 41st June 20224 |  | 2000000 | 2000000
151 | Kasisi road | Grading and Murraming; and installation of drainage facilities |  |  | 4685100300 |  | Kajiado North |  | Scheme 6 |  | Road, Public Works, Energy and Transport | Ngong Municipality |  | 13th July 20223 | 42nd June 20224 |  | 1500000 | 1500000
152 | Roysambu road | Grading and Murraming; and installation of drainage facilities |  |  | 4685100300 |  | Kajiado North |  | Scheme 6 |  | Road, Public Works, Energy and Transport | Ngong Municipality |  | 14th July 20223 | 43rd June 20224 |  | 1500000 | 1500000
153 | Endomoto drive 13 | Street lighting ofEndomoto drive 13 |  |  | 4685100300 |  | Kajiado North |  | Masai Lodge |  | Road, Public Works, Energy and Transport | Ngong Municipality |  | 15th July 20223 | 44th June 20224 |  | 1500000 | 1500000
154 | Simba Drive | Street lighting of Simba drive |  |  | 4685100300 |  | Kajiado North |  | Masai Lodge |  | Road, Public Works, Energy and Transport | Ngong Municipality |  | 16th July 20223 | 45th June 20224 |  | 1500000 | 1500000
155 | Sironik road | Grading and Murraming; and installation of drainage facilities |  |  | 4685100300 |  | Kajiado North |  | Ongata Rongai |  | Road, Public Works, Energy and Transport | Ngong Municipality |  | 17th July 20223 | 46th June 20224 |  | 3000000 | 3000000
156 | Umoja Road | Grading and Murraming; and installation of drainage facilities |  |  | 4685100300 |  | Kajiado North |  | Laiser |  | Road, Public Works, Energy and Transport | Ngong Municipality |  | 18th July 20223 | 47th June 20224 |  | 3000000 | 3000000
157 | Mosque road ole kasasi | Grading and Murraming; and installation of drainage facilities |  |  | 4685100300 |  | Kajiado North |  | Ole Kasasi |  | Road, Public Works, Energy and Transport | Ngong Municipality |  | 19th July 20223 | 48th June 20224 |  | 2000000 | 2000000
158 | Somalia estate entarnce - flood light | Installation of flood light |  | somalia estate entarnce flood light instmalia- flood light | 4685100300 |  | Kajiado North |  | Ole Kasasi B |  | Road, Public Works, Energy and Transport | Ngong Municipality |  | 20th July 20223 | 49th June 20224 |  | 2000000 | 2000000
159 | Somalia estate to kisoi road | Grading and Murraming; and installation of drainage facilities |  | somalia estate to kisoi road gradmaliaroad | 4685100300 |  | Kajiado North |  | Ole Kasasi B |  | Road, Public Works, Energy and Transport | Ngong Municipality |  | 21st July 20223 | 50th June 20224 |  | 2000000 | 2000000
160 | Masai road- Bondeni street lighting | Streetlighting of Masai road- Bondeni |  |  | 4685100300 |  | Kajiado North |  | Olkeri |  | Road, Public Works, Energy and Transport | Ngong Municipality |  | 22nd July 20223 | 51st June 20224 |  | 2000000 | 2000000
161 | Kaka Valley Road | Grading & Murraming; Construction of Culvert & streetlight - 1.5km |  |  | 4685100300 |  | Kajiado North |  | Oloika |  | Road, Public Works, Energy and Transport | Ngong Municipality |  | 23rd July 20223 | 52nd June 20224 |  | 3000000 | 3000000
162 | Kiserian Primary Bridge | Opening and grading of a new road |  |  | 4685100300 |  | Kajiado North |  | Kiserian |  | Road, Public Works, Energy and Transport | Ngong Municipality |  | 24th July 20223 | 53rd June 20224 |  | 3000000 | 3000000
163 | Memusi olkeri highmast | Installation of a highmast |  |  | 4685100300 |  | Kajiado North |  | Matasia |  | Road, Public Works, Energy and Transport | Ngong Municipality |  | 25th July 20223 | 54th June 20224 |  | 2000000 | 2000000
164 | airport and Washaiyo road | Grading & Murraming; Culvert construction |  |  | 4685100300 |  | Kajiado North |  | lekuruki |  | Road, Public Works, Energy and Transport | Ngong Municipality |  | 26th July 20223 | 55th June 20224 |  | 3000000 | 3000000
165 | Matasia town roads | Grading, murraming and Culvert |  |  | 4685100300 |  | Kajiado North |  | Olkeri |  | Road, Public Works, Energy and Transport | Ngong Municipality |  | 27th July 20223 | 56th June 20224 |  | 3500000 | 3500000
166 | Neema- tipanko road | Grading, murraming and Culvert |  |  | 4685100300 |  | Kajiado North |  | Lemelepo |  | Road, Public Works, Energy and Transport | Ngong Municipality |  | 28th July 20223 | 57th June 20224 |  | 3000000 | 3000000
167 | Merisho- PEFA road | Grading, murraming and Culvert |  |  | 4685100300 |  | Kajiado North |  | Olkeri |  | Road, Public Works, Energy and Transport | Ngong Municipality |  | 29th July 20223 | 58th June 20224 |  | 1500000 | 1500000
168 | resort u- turn road | Grading & Murraming ,and culvert- |  |  | 4685100300 |  | Kajiado North |  | Lekuruki |  | Road, Public Works, Energy and Transport | Ngong Municipality |  | 30th July 20223 | 59th June 20224 |  | 2000000 | 2000000
169 | kamukunji (4) Roads | Grading & Murraming |  |  | 4685100300 |  | Kajiado North |  | Kamukunji |  | Road, Public Works, Energy and Transport | Ngong Municipality |  | 31st July 20223 | 60th June 20224 |  | 2500000 | 2500000
170 | Gataka Road Network (16 roads) | Grading & Murraming |  |  | 4685100300 |  | Kajiado North |  | Gataka |  | Road, Public Works, Energy and Transport | Ngong Municipality |  | 32nd July 20223 | 61st June 20224 |  | 6000000 | 6000000
171 | Kisumu Ndogo road via boonhouse to Waichanguru’s place | Grading & Murraming |  |  | 4685100300 |  | Kajiado North |  | Kisumu Ndogo |  | Road, Public Works, Energy and Transport | Ngong Municipality |  | 33rd July 20223 | 62nd June 20224 |  | 3000000 | 3000000
172 | Nafrom Road to St. Mary Road | Grading & Murraming |  |  | 4685100300 |  | Kajiado North |  | Nafrom |  | Road, Public Works, Energy and Transport | Ngong Municipality |  | 34th July 20223 | 63rd June 20224 |  | 2000000 | 2000000
173 | PCEA to Gataka road | Grading & Murraming |  |  | 4685100300 |  | Kajiado North |  | PCEA Gataka |  | Road, Public Works, Energy and Transport | Ngong Municipality |  | 35th July 20223 | 64th June 20224 |  | 3000000 | 3000000
174 | Ole Sakuda road solar light | Installation of solar light |  |  | 4685100300 |  | Kajiado North |  | Embakasi |  | Road, Public Works, Energy and Transport | Ngong Municipality |  | 36th July 20223 | 65th June 20224 |  | 1000000 | 1000000
175 | St Marry road solar light | Installation of solar light |  |  | 4685100300 |  | Kajiado North |  | Nkaimurunya |  | Road, Public Works, Energy and Transport | Ngong Municipality |  | 37th July 20223 | 66th June 20224 |  | 1000000 | 1000000
176 | Gichagi - Mumeru Road | Drainage and cabro paving of 1KM road |  |  | 4685100300 |  | Kajiado North |  | Gichagi |  | Road, Public Works, Energy and Transport | Ngong Municipality |  | 38th July 20223 | 67th June 20224 |  | 2000000 | 2000000
177 | Kundos Florida to Catholic Road | Laying of cabro works |  |  | 4685100300 |  | Kajiado North |  | Ngong Township |  | Road, Public Works, Energy and Transport | Ngong Municipality |  | 39th July 20223 | 68th June 20224 |  | 4000000 | 4000000
178 | Equity to Ngong Heights Road | Laying of cabro works |  |  | 4685100300 |  | Kajiado North |  | Ngong town |  | Road, Public Works, Energy and Transport | Ngong Municipality |  | 40th July 20223 | 69th June 20224 |  | 3000000 | 3000000
179 | Salama road | Laying of cabro works |  |  | 4685100300 |  | Kajiado North |  | Scheme 305 |  | Road, Public Works, Energy and Transport | Ngong Municipality |  | 41st July 20223 | 70th June 20224 |  | 3000000 | 3000000
180 | Damaskas- Imani feeder roads | Grading, murraming and drainage |  |  | 4685100300 |  | Kajiado North |  | Oloolua |  | Road, Public Works, Energy and Transport | Ngong Municipality |  | 42nd July 20223 | 71st June 20224 |  | 4000000 | 4000000
181 | Jerusalem - Chonjo feeder road | Grading, murraming and drainage |  |  | 4685100300 |  | Kajiado North |  | Kirarapon |  | Road, Public Works, Energy and Transport | Ngong Municipality |  | 43rd July 20223 | 72nd June 20224 |  | 3000000 | 3000000
182 | Kariobangi- Forest view feeder road | Grading, murraming and drainage |  |  | 4685100300 |  | Kajiado North |  | Bulbul |  | Road, Public Works, Energy and Transport | Ngong Municipality |  | 44th July 20223 | 73rd June 20224 |  | 3000000 | 3000000
183 | Bulbul highmast | Installation of a high mast |  |  | 4685100300 |  | Kajiado North |  | Bulbul |  | Road, Public Works, Energy and Transport | Ngong Municipality |  | 45th July 20223 | 74th June 20224 |  | 2000000 | 2000000
184 | Jerusalem - Kirarapon highmast | Installation of a high mast |  |  | 4685100300 |  | Kajiado North |  | Kirarapon |  | Road, Public Works, Energy and Transport | Ngong Municipality |  | 46th July 20223 | 75th June 20224 |  | 2000000 | 2000000
185 | Rongai | Solar Lighting, Construction of drainage and water collection facilities (Gutters & Tanks) |  | rongai solangaii | 4685100300 |  | Kajiado North |  | Ongata Rongai Market |  | Trade, Investment and Enterprise Devt | Ngong Municipality |  | 47th July 20223 | 76th June 20224 |  | 3000000 | 3000000
186 | Matasia Centre | Lighting; Completion of Stalls; Toilet Construction; Cabro works and Road network around market | improve security,road access and good business environment | Matasia security market lighting;i | 4685100300 |  | Kajiado North |  | Matasia Market |  | Trade, Investment and Enterprise Devt | Ngong Municipality |  | 48th July 20223 | 77th June 20224 |  | 4000000 | 4000000
187 | Ngong Market | Construction of Ngong market stare case | goood business environment | ngong business consos | 4685100300 |  | Kajiado North |  | Ngong Township |  | Trade, Investment and Enterprise Devt | Ngong Municipality |  | 49th July 20223 | 78th June 20224 |  | 1000000 | 1000000 | 1000000
188 | Construction of five shades | Construction of 5 Bodaboda shades with stalls | provide shades for boda boda riders | construction of five shades consnstructiondes | 4685100300 |  | Kajiado North |  | Across Ngong ward |  | Trade, Investment and Enterprise Devt | Ngong Municipality |  | 50th July 20223 | 79th June 20224 |  | 1000000 | 1000000 | 1000000 | [9 empty] | Stalled | insuficient funds
189 | Upgrading of Juakali Shades | Landscaping of the 2 acres; Cabro Paving & Construction of shades | provide shades for boda boda riders | jua kali shades upgraded | 4685100300 |  | Kajiado North |  | Ngong township |  | Trade, Investment and Enterprise Devt | Ngong Municipality |  | 51st July 20223 | 80th June 20224 |  | 3000000 | 3000000 | 3000000
190 | Repair of Water Tanks at Gishagi | Repairs for 4 water tanks (concrete), elaveted steel tank , soloraization and battery | improve sanitation &water access | Gishagi water tanks repaired | 4685100300 |  | Kajiado North |  | Gichagi |  | Water, Enviroment and Natural Resouces | Ngong Municipality |  | 52nd July 20223 | 81st June 20224 |  | 5000000 | 5000000 | 5000000 | [5 empty] | 100% |  |  |  | completed
191 | Florida borehole at Mathare | Erection of elevated steel tank , intallation of water pump , piping to nearest water kiosk | increase water access | florida borehole maintained | 4685100200 |  | Kajiado North |  | Umoja |  | Water, Enviroment and Natural Resouces | Ngong Municipality |  | 53rd July 20223 | 82nd June 20224 |  | 4000000 | 4000000 | 4000000 | [5 empty] | 0% |  |  |  | ongoing | [15 empty] | recommended for tarmination
192 | Ngong holding Market next to stadium | Drilling of berehole | increased access to water | to access berehole drilling arket ne | 4685100200 |  | Kajiado North |  | Kisii ndogo |  | Water, Enviroment and Natural Resouces | Ngong Municipality |  | 54th July 20223 | 83rd June 20224 |  | 2000000 | 2000000 | 2000000 | [5 empty] | 0% |  |  |  | ongoing
193 | Mutungu Borehole | Borehole solarization | instalation of solar | Mutungu of solarization borehole utungu Boreholg | 4685100200 |  | Kajiado North |  | Olepolos SGR |  | Water, Enviroment and Natural Resouces | Ngong Municipality |  | 55th July 20223 | 84th June 20224 |  | 4500000 | 4500000 | 4500000 | CGK | 4500000 | 4500000 |  |  | 100% |  |  |  | completed
194 | Embul-bul Borehole | Borehole solarization | instalation of solar | embul of borebe | 4685100200 |  | Kajiado North |  | Embulbul |  | Water, Enviroment and Natural Resouces | Ngong Municipality |  | 56th July 20223 | 85th June 20224 |  | 4000000 | 4000000 | 4000000 | CGK | 4000000 |  |  |  | 100% |  |  |  | completed
195 | Matasia Oloika Water Project | 2km pipeline and watering facilities | Increase access to water | Matasia access nng rng Oloika Water Project | 4685100200 |  | Kajiado North |  | Merisho |  | Water, Enviroment and Natural Resouces | Ngong Municipality |  | 57th July 20223 | 86th June 20224 |  | 3000000 | 3000000 | 3000000 | CGK | 3000000 |  |  |  | 0% |  |  |  | ongoing
196 | Ngong Sub-County Hospital OPD expansion | Expansion of OPD to create Accident and Emmergency Casualty; Increase the OPD pay points, Wash rooms for OPD | Increase access to health services | Ngong sub county hospital expanded | 4685100100 |  | Kajiado North
Report prepared by:
Designation:
Signature:
Report Submited by:
Designation:
Signature:

## Formula Sheet
GOK
Development Partner
GOK & Development Partner
Yes
No
Compete
Cancel
Defer
Completed
Ongoing
Stalled