## instructions1
INSTRUCTIONS ON COMPLETION OF PROJECT STOCK TAKE TEMPLATE
1. All fields are mandatory and should be populated.
2. DO NOT EDIT the CONFIGURATION worksheet.
3. ONLY populate rows applicable in your respective Counties &Ward Location(s) and Hide the rest of the rows (DO NOT DELETE the Rows).
4. The scope of this exercise is projects started between the year 2013 and 30th June, 2024
5.Remember to SAVE the document after populating the required details in the worksheet.

## Project Stocktaking Template
PROJECT DETAILS | [6 empty] | PROJECT LOCATION |  |  | IMPLEMENTATION DETAILS | [6 empty] | FINANCIAL INFORMATION |  |  |  |  | DISBURSMENT |  |  |  | EXPENDITURE |  |  | PROJECT STATUS |  |  | ACTIONS FOR STALLED |  |  |  | RISKS AND RECOMMENDATIONS |  |  | CLIMATE & DISASTER RISK SCREENING |  | ENVIRONMENTAL , SOCIAL AND OCCUPATIONAL HEALTH, SAFETY AND GENDER SCREENING |  | TECHNICAL, FINANCIAL, AND ECONOMIC VIABILITY SCREENING |  | ADDITIONAL REMARKS
S/No. | Project Name/Title | Project Description | Project Goal/Objective | Project Output | Project Code (Budget line) | Budget Item Name | Sub-County | Ward | Geographic Location (Latitude & Longitude) | Sector/ Vote Name | Department, Directorate, Units, Agencies | Implementing Department/Agency / Muncipalities | Date of Approval/Financial Approval | Project Start Date | Expected Project Completion Date | Actual Project Completion Date | Estimated Project Cost (Kshs.) | Approved Project Cost | Funds available in the specific year | Project Funding Source | If Development Partners, Please specify . | County Government component in the Project Cost (Kshs.) | Development Partner component in the Project Cost (Kshs.) | Total Disbursed Funds as at 30th June 2024 (Kshs.) | Percentage (%) Disbursed Amount = (Disbursed/ Approved) | Expenditure to date | Pending Bill/Outstanding commitment not paid but work done | Project Balance (Kshs.) i.e (Approved Project Cost - Disbursed Amount) | Project Status at the time of the Exercise (i.e Completed, Ongoing, Stalled) | % completion for ongoing/stalled projects | If Stalled, what is the percentage (%) completion at the time of stalling (Physical completion status) | If stalled give reasons; | Year the project stalled | Time required to complete the stalled project (in months) | Estimated cost required to complete the stalled project (in Kshs.) | Is the project still appering in the budget or is it still receiving funds in the annual budgets? (Yes/No) | Recommendation for the Stalled Project (Complete/ Cancel/ Defer) | Identify the Risks associated with the stalled/completed/ongoing project ie. (Contractual/legal/Financial/Environmental etc.) | Has this project been screened for Climate & Disaster Risks? Yes/No | If yes, what action has been taken to mitigate? IF Not, give reasons and the immediate plans for conducting the screening. | Has the project been screened for Environmental, Social, Occupational Health, Safety and gender risks | If yes, what action has been taken to mitigate? IF Not, give reasons and the immediate plans for conducting the screening. | Has the project been screened for Technical, Financial, and Economic Viability and a fesibility report been prepared? (yes/No) | If yes, what action has been taken to mitigate? IF Not, what is being used to measure viability of the project? Additionally, indicate immediate plans on when the screening and feasibility study will be undertaken | REMARKS
[11 empty] | education | education | 2013-07-01 | 1st aug 2013 | 30th june 2014 | 30th june 2014 | 1051076 | 1051076 | 1051076 | CGK |  |  | 0 | [5 empty] | complete | [6 empty] | No
| Column10 | Column9 | Column8 | Column7 | Column6 | Column5 | Column4 | Column3 | Column2 | education | education | education | 2013-07-01 | 1st aug 2013 | 30th june 2014 | 30th june 2014 | 2613294.4 | 2613294.4 | 2613294.4 | CGK |  | 2613294.4 | 0 |  | 100% | 2613294.4 |  |  | complete | [6 empty] | No
| Enchoro eseneteu primary | Renovation of classrooms | to increase enrolment | Renovation of classrooms | 3110200 | construction of buildings | kajiado west | iloodokilani |  | education | education | education | 1st july 2013 | 1st aug 2013 | 30th june 2014 | 30th june 2014 | 1265541 | 1265541 | 1265541 | CGK |  | 1265541 | 0 |  | 100% | 1265541 |  |  | complete | [6 empty] | No
| Oltotoi primary school | construction of 2 classrooms | to increase enrolment | construction of 2 classrooms | 3110200 | construction of buildings | kajiado west | iloodokilani |  | education | education | education | 1st july 2013 | 1st aug 2013 | 30th june 2014 | 30th june 2014 | 3586515.84 | 3586515.84 | 3586515.84 | CGK |  | 3586515.84 | 0 |  | 100% | 3586515.84 |  |  | complete | [6 empty] | No
| Embulbul primary school | construction of 1 classroom | to increase enrolment | construction of 1 classroom | 3110200 | construction of buildings | kajiado north | oloolua |  | education | education | education | 1st july 2013 | 1st aug 2013 | 30th june 2014 | 30th june 2014 | 744060 | 744060 | 744060 | CGK |  | 744060 | 0 |  | 100% | 744060 |  |  | complete | [6 empty] | No
| Enkisajani primary school | construction of 3 classroom | to increase enrolment | construction of 3 classroom | 3110200 | construction of buildings | kajiado south | kuku |  | education | education | education | 1st july 2013 | 1st aug 2013 | 30th june 2014 | 30th june 2014 | 2526596 | 2526596 | 2526596 | CGK |  | 2526596 | 0 |  | 100% | 2526596 |  |  | complete | [6 empty] | No
| Saina primary | construction of 1 classroom | to increase enrolment | construction of 1 classroom | 3110200 | construction of buildings | kajiado central | dalalekutuk |  | education | education | education | 1st july 2013 | 1st aug 2013 | 30th june 2014 | 30th june 2014 | 1251593 | 1251593 | 1251593 | CGK |  | 1251593 | 0 |  | 100% | 1251593 |  |  | complete | [6 empty] | No
| Enkasurai primary school | construction of admn block | to increase enrolment | construction of admn block | 3110200 | construction of buildings | kajiado central | dalalekutuk |  | education | education | education | 1st july 2013 | 1st aug 2013 | 30th june 2014 | 30th june 2014 | 8998587 | 8998587 | 8998587 | CGK |  | 8998587 | 0 |  | 100% | 8998587 |  |  | complete | [6 empty] | No
| Endonyo Enkampi pri.sch | construction of ECDE classroom | to increase enrolment | construction of ECDE classroom | 3110200 | construction of buildings | kajiado central | purko |  | education | education | education | 1st july 2013 | 1st aug 2013 | 30th june 2014 | 30th june 2014 | 1236813.49 | 1236813.49 | 1236813.49 | CGK |  | 1236813.49 | 0 |  | 100% | 1236813.49 |  |  | complete | [6 empty] | No
| Ole kasasi youth polytechnique computer lab | construction of a computer lab | to increase enrolment | construction of a computer lab | 3110200 | construction of buildings | kajiado north | ongata rongai |  | education | education | education | 1st july 2013 | 1st aug 2013 | 30th june 2014 | 30th june 2014 | 1263884.67 | 1263884.67 | 1263884.67 | CGK |  | 1263884.67 | 0 |  | 100% | 1263884.67 |  |  | complete | [6 empty] | No
| Enkongu primary school | construction of 1 classroom | to increase enrolment | construction of 1 classroom | 3110200 | construction of buildings | kajiado south | imbirikani |  | education | education | education | 1st july 2013 | 1st aug 2013 | 30th june 2014 | 30th june 2014 | 3972141.6 | 3972141.6 | 3972141.6 | CGK |  | 3972141.6 | 0 |  | 100% | 3972141.6 |  |  | complete | [6 empty] | No
| Oloomeuti pri.sch | construction of 1 classroom | to increase enrolment | construction of 1 classroom | 3110200 | construction of buildings | kajiado south | kimana |  | education | education | education | 1st july 2013 | 1st aug 2013 | 30th june 2014 | 30th june 2014 | 2572000 | 2572000 | 2572000 | CGK |  | 2572000 | 0 |  | 100% | 2572000 |  |  | complete | [6 empty] | No
| Oldorko primary school | construction of 3 classrooms | to increase enrolment | construction of 3 classrooms | 3110200 | construction of buildings | kajiado west | mosiro |  | education | education | education | 1st july 2013 | 1st aug 2013 | 30th june 2014 | 30th june 2014 | 1324047.2 | 1324047.2 | 1324047.2 | CGK |  | 1324047.2 | 0 |  | 100% | 1324047.2 |  |  | complete | [6 empty] | No
| Isinya boys sec.school | construction of 2 classrooms | to increase enrolment | construction of 2 classrooms | 3110200 | construction of buildings | kajiado east | kaputiei north |  | education | education | education | 1st july 2013 | 1st aug 2013 | 30th june 2014 | 30th june 2014 | 1206829.2 | 1206829.2 | 1206829.2 | CGK |  | 1206829.2 | 0 |  | 100% | 1206829.2 |  |  | complete | [6 empty] | No
| Oloile primary school | construction of 1 classroom | to increase enrolment | construction of 1 classroom | 3110200 | construction of buildings | kajiado south | kimana |  | education | education | education | 1st july 2013 | 1st aug 2013 | 30th june 2014 | 30th june 2014 | 6893021.6 | 6893021.6 | 6893021.6 | CGK |  | 6893021.6 | 0 |  | 100% | 6893021.6 |  |  | complete | [6 empty] | No
| Matali primary school | construction of 1 classroom | to increase enrolment | construction of 1 classroom | 3110200 | construction of buildings | kajiado east | sholinke |  | education | education | education | 1st july 2013 | 1st aug 2013 | 30th june 2014 | 30th june 2014 | 2171918 | 2171918 | 2171918 | CGK |  | 2171918 | 0 |  | 100% | 2171918 |  |  | complete | [6 empty] | No
| Oldonyo onyokie sec | construction of 3 classrooms and 5no tailet blocks | to increase enrolment | construction of 3 classrooms and 5no tailet blocks | 3110200 | construction of buildings | kajiado west | magadi |  | education | education | education | 1st july 2013 | 1st aug 2013 | 30th june 2014 | 30th june 2014 | 2506823.8 | 2506823.8 | 2506823.8 | CGK |  | 2506823.8 | 0 |  | 100% | 2506823.8 |  |  | complete | [6 empty] | No
| Ole polos primary school | construction of 2 ECDE classrooms | to increase enrolment | construction of 2 ECDE classrooms | 3110200 | construction of buildings | kajiado central | matapato north |  | education | education | education | 1st july 2013 | 1st aug 2013 | 30th june 2014 | 30th june 2014 | 2648094 | 2648094 | 2648094 | CGK |  | 2648094 | 0 |  | 100% | 2648094 |  |  | complete | [6 empty] | No
| Oloika primary school | construction of an Admn block | to increase enrolment | construction of an Admn block | 3110200 | construction of buildings | kajiado west | magadi |  | education | education | education | 1st july 2013 | 1st aug 2013 | 30th june 2014 | 30th june 2014 | 1301057.6 | 1301057.6 | 1301057.6 | CGK |  | 1301057.6 | 0 |  | 100% | 1301057.6 |  |  | complete | [6 empty] | No
| Enkijape pri.school | construction of 2 classrooms | to increase enrolment | construction of 2 classrooms | 3110200 | construction of buildings | kajiado south | kuku |  | education | education | education | 1st july 2013 | 1st aug 2013 | 30th june 2014 | 30th june 2014 | 1205541.6 | 1205541.6 | 1205541.6 | CGK |  | 1205541.6 | 0 |  | 100% | 1205541.6 |  |  | complete | [6 empty] | No
| Embulbul oloolua | construction of 1 classroom | to increase enrolment | construction of 1 classroom | 3110200 | construction of buildings | kajiado north | oloolua |  | education | education | education | 1st july 2013 | 1st aug 2013 | 30th june 2014 | 30th june 2014 | 2454699.2 | 2454699.2 | 2454699.2 | CGK |  | 2454699.2 | 0 |  | 100% | 2454699.2 |  |  | complete | [6 empty] | No
| Oloile primary school | construction of 1 classroom | to increase enrolment | construction of 1 classroom | 3110200 | construction of buildings | kajiado south | kimana |  | education | education | education | 1st july 2013 | 1st aug 2013 | 30th june 2014 | 30th june 2014 | 7088516 | 7088516 | 7088516 | CGK |  | 7088516 | 0 |  | 100% | 7088516 |  |  | complete | [6 empty] | No
| Enyuata primary school | construction of 2 classrooms | to increase enrolment | construction of 2 classrooms | 3110200 | construction of buildings | kajiado west | magadi |  | education | education | education | 1st july 2013 | 1st aug 2013 | 30th june 2014 | 30th june 2014 | 2409923 | 2409923 | 2409923 | CGK |  | 2409923 | 0 |  | 100% | 2409923 |  |  | complete | [6 empty] | No
| Isinya Polytechnique | construction of a polytecnique | to increase enrolment | construction of a polytecnique | 3110200 | construction of buildings | kajiado east | kaputiei north |  | education | education | education | 1st july 2013 | 1st aug 2013 | 30th june 2014 | 30th june 2014 | 1366944 | 1366944 | 1366944 | CGK |  | 1366944 | 0 |  | 100% | 1366944 |  |  | complete | [6 empty] | No
| Kimana mixed | construction of 2 classrooms | to increase enrolment | construction of 2 classrooms | 3110200 | construction of buildings | kajiado south | kimana |  | education | education | education | 1st july 2013 | 1st aug 2013 | 30th june 2014 | 30th june 2014 | 1182243 | 1182243 | 1182243 | CGK |  | 1182243 | 0 |  | 100% | 1182243 |  |  | complete | [6 empty] | No
| Musenke pri.school | construction of 1no classroom | to increase enrolment | construction of 1no classroom | 3110200 | construction of buildings | kajiado west | magadi |  | education | education | education | 1st july 2013 | 1st aug 2013 | 30th june 2014 | 30th june 2014 | 1250642.4 | 1250642.4 | 1250642.4 | CGK |  | 1250642.4 | 0 |  | 100% | 1250642.4 |  |  | complete | [6 empty] | No
| Enkutoto primary school | construction of 1no ECDE classroom | to increase enrolment | construction of 1no ECDE classroom | 3110200 | construction of buildings | kajiado east | sholinke |  | education | education | education | 1st july 2013 | 1st aug 2013 | 30th june 2014 | 30th june 2014 | 1030033.6 | 1030033.6 | 1030033.6 | CGK |  | 1030033.6 | 0 |  | 100% | 1030033.6 |  |  | complete | [6 empty] | No
| Noompopong primary school | construction of 1no classroom | to increase enrolment | construction of 1no classroom | 3110200 | construction of buildings | kajiado east | sholinke |  | education | education | education | 1st july 2013 | 1st aug 2013 | 30th june 2014 | 30th june 2014 | 1231780.8 | 1231780.8 | 1231780.8 | CGK |  | 1231780.8 | 0 |  | 100% | 1231780.8 |  |  | complete | [6 empty] | No
| Oldonyo Onyokie primary sch. | Fancing | to increase enrolment | Fancing | 3110200 | construction of buildings | kajiado west | magadi |  | education | education | education | 1st july 2013 | 1st aug 2013 | 30th june 2014 | 30th june 2014 | 1389756.8 | 1389756.8 | 1389756.8 | CGK |  | 1389756.8 | 0 |  | 100% | 1389756.8 |  |  | complete | [6 empty] | No
| Imbuko primary school | construction of 1classroom | to increase enrolment | construction of 1classroom | 3110200 | construction of buildings | kajiado east | kenyawa/poka |  | education | education | education | 1st july 2013 | 1st aug 2013 | 30th june 2014 | 30th june 2014 | 1306647.2 | 1306647.2 | 1306647.2 | CGK |  | 1306647.2 | 0 |  | 100% | 1306647.2 |  |  | complete | [6 empty] | No
| Oloilalei primary school | construction of 1no classroom | to increase enrolment | construction of 1no classroom | 3110200 | construction of buildings | kajiado central | matapato south |  | education | education | education | 1st july 2013 | 1st aug 2013 | 30th june 2014 | 30th june 2014 | 9801478 | 9801478 | 9801478 | CGK |  | 9801478 | 0 |  | 100% | 9801478 |  |  | complete | [6 empty] | No
| Olmoti ECDE | construction of 1 ECDE classroom | to increase enrolment | construction of 1 ECDE classroom | 3110200 | construction of buildings | kajiado central | matapato south |  | education | education | education | 1st july 2013 | 1st aug 2013 | 30th june 2014 | 30th june 2014 | 1201267 | 1201267 | 1201267 | CGK |  | 1201267 | 0 |  | 100% | 1201267 |  |  | complete | [6 empty] | No
| Entasopia youth polytechnique | construction of polytechnique classroom | to increase enrolment | construction of polytechnique classroom | 3110200 | construction of buildings | kajiado west | magadi |  | education | education | education | 1st july 2013 | 1st aug 2013 | 30th june 2014 | 30th june 2014 | 2499962.4 | 2499962.4 | 2499962.4 | CGK |  | 2499962.4 | 0 |  | 100% | 2499962.4 |  |  | complete | [6 empty] | No
| olmoti primary | construction of 1 classroom | to increase enrolment | construction of 1 classroom | 3110200 | construction of buildings | kajiado south | entonet/lenkisem |  | education | education | education | 1st july 2013 | 1st aug 2013 | 30th june 2014 | 30th june 2014 | 3569529.9 | 3569529.9 | 3569529.9 | CGK |  | 3569529.9 | 0 |  | 100% | 3569529.9 |  |  | complete | [6 empty] | No
| saina primary | construction of an Admn block | to increase enrolment | construction of an Admn block | 3110200 | construction of buildings | kajiado central | dalalekutuk |  | education | education | education | 1st july 2013 | 1st aug 2013 | 30th june 2014 | 30th june 2014 | 2171918 | 2171918 | 2171918 | CGK |  | 2171918 | 0 |  | 100% | 2171918 |  |  | complete | [6 empty] | No
| Pilewa primary school | construction of 3 classrooms | to increase enrolment | construction of 3 classrooms | 3110200 | construction of buildings | kajiado central | dalalekutuk |  | education | education | education | 1st july 2013 | 1st aug 2013 | 30th june 2014 | 30th june 2014 | 4994728 | 4994728 | 4994728 | CGK |  | 4994728 | 0 |  | 100% | 4994728 |  |  | complete | [6 empty] | No
| Ilparua primary sch. | construction of 2 classrooms | to increase enrolment | construction of 2 classrooms | 3110200 | construction of buildings | kajiado central | purko |  | education | education | education | 1st july 2013 | 1st aug 2013 | 30th june 2014 | 30th june 2014 | 2393196 | 2393196 | 2393196 | CGK |  | 2393196 | 0 |  | 100% | 2393196 |  |  | complete | [6 empty] | No
| namelok sec. | construction of a dormitory | to increase enrolment | construction of a dormitory | 3110200 | construction of buildings | kajiado south | entonet/lenkisem |  | education | education | education | 1st july 2013 | 1st aug 2013 | 30th june 2014 | 30th june 2014 | 1200000 | 1200000 | 1200000 | CGK |  | 1200000 | 0 |  | 100% | 1200000 |  |  | complete | [6 empty] | No
| Mailwa secondary | construction of 2 classrooms | to increase enrolment | construction of 2 classrooms | 3110200 | construction of buildings | kajiado central | matapato south |  | education | education | education | 1st july 2013 | 1st aug 2013 | 30th june 2014 | 30th june 2014 | 3701589 | 3701589 | 3701589 | CGK |  | 3701589 | 0 |  | 100% | 3701589 |  |  | complete | [6 empty] | No
| Entaamo | construction of 1 classroom | to increase enrolment | construction of 1 classroom | 3110200 | construction of buildings | kajiado west | magadi |  | education
| enkutoto primary | construction of 3 classrooms | to increase enrolment | construction of 3 classrooms | 3110200 | construction of buildings | kajiado central | dalalekutuk |  | education | education | education | 1st july2014 | 1st aug 2014 | 30th june 2015 | 30th june 2015 | 3007091.2 | 3007091.2 | 3007091.2 | CGK |  | 3007091.2 | 0 |  | 100% | 3007091.2 |  |  | complete
[11 empty] | education | education | 1st july2014 | 1st aug 2014 | 30th june 2015 | 30th june 2015 | 2998927.6 | 2998927.6 | 2998927.6 | CGK |  | 2998927.6 | 0 |  | 100% | 2998927.6 |  |  | complete
| Engumi ECDE primary | construction of 2no classrooms | to increase enrolment | construction of 2no classrooms | 3110200 | construction of buildings | kajiado south | kimana |  | education | education | education | 1st july2014 | 1st aug 2014 | 30th june 2015 | 30th june 2015 | 2999690 | 2999690 | 2999690 | CGK |  | 2999690 | 0 |  | 100% | 2999690 |  |  | complete
| Impiron primary | construction of 2no classrooms | to increase enrolment | construction of 2no classrooms | 3110200 | construction of buildings | kajiado south | kimana |  | education | education | education | 1st july2014 | 1st aug 2014 | 30th june 2015 | 30th june 2015 | 1998000 | 1998000 | 1998000 | CGK |  | 1998000 | 0 |  | 100% | 1998000 |  |  | complete
| Lenkobei primary | construction of 2no classrooms | to increase enrolment | construction of 2no classrooms | 3110200 | construction of buildings | kajiado west | Magadi |  | education | education | education | 1st july2014 | 1st aug 2014 | 30th june 2015 | 30th june 2015 | 2972975.6 | 2972975.6 | 2972975.6 | CGK |  | 2972975.6 | 0 |  | 100% | 2972975.6 |  |  | complete
| Olobelibel mixed sec school | construction of Chainlink fence | to increase enrolment | construction of Chainlink fence | 3110200 | construction of buildings | kajiado central | Dalalekutuk |  | education | education | education | 1st july2014 | 1st aug 2014 | 30th june 2015 | 30th june 2015 | 1492473 | 1492473 | 1492473 | CGK |  | 1492473 | 0 |  | 100% | 1492473 |  |  | complete
| Maral primary school | construction of 2no classrooms | to increase enrolment | construction of 2no classrooms | 3110200 | construction of buildings | kajiado south | kimana |  | education | education | education | 1st july2014 | 1st aug 2014 | 30th june 2015 | 30th june 2015 | 9995882.4 | 9995882.4 | 9995882.4 | CGK |  | 9995882.4 | 0 |  | 100% | 9995882.4 |  |  | complete
| Kikeleya primary school | construction of 1no classroom | to increase enrolment | construction of 1no classroom | 3110200 | construction of buildings | kajaido central | Matapato North |  | education | education | education | 1st july2014 | 1st aug 2014 | 30th june 2015 | 30th june 2015 | 3001510 | 3001510 | 3001510 | CGK |  | 3001510 | 0 |  | 100% | 3001510 |  |  | complete
| Isinet sec. | construction of an Adm block and 4 classrooms | to increase enrolment | construction of an Adm block and 4 classrooms | 3110200 | construction of buildings | kajiado south | Imbirikani |  | education | education | education | 1st july2014 | 1st aug 2014 | 30th june 2015 | 30th june 2015 | 2999368.8 | 2999368.8 | 2999368.8 | CGK |  | 2999368.8 | 0 |  | 100% | 2999368.8 |  |  | complete
| Oldoinyo Oibor primary | construction of 2no classrooms | to increase enrolment | construction of 2no classrooms | 3110200 | construction of buildings | kajiado south | Kuku |  | education | education | education | 1st july2014 | 1st aug 2014 | 30th june 2015 | 30th june 2015 | 1499530 | 1499530 | 1499530 | CGK |  | 1499530 | 0 |  | 100% | 1499530 |  |  | complete
| Koromboi pri. | construction of 2no classroom | to increase enrolment | construction of 2no classroom | 3110200 | construction of buildings | kajiado east | Kaputiei north |  | education | education | education | 1st july2014 | 1st aug 2014 | 30th june 2015 | 30th june 2015 | 2990960 | 2990960 | 2990960 | CGK |  | 2990960 | 0 |  | 100% | 2990960 |  |  | complete
| Inkiito primary school | construction of 1no classroom | to increase enrolment | construction of 1no classroom | 3110200 | construction of buildings | kajiado west | Keekonyokie |  | education | education | education | 1st july2014 | 1st aug 2014 | 30th june 2015 | 30th june 2015 | 1498940 | 1498940 | 1498940 | CGK |  | 1498940 | 0 |  | 100% | 1498940 |  |  | complete
| Isinya boys sec.school | construction of 2no classrooms | to increase enrolment | construction of 2no classrooms | 3110200 | construction of buildings | kajiado east | Kaputiei north |  | education | education | education | 1st july2014 | 1st aug 2014 | 30th june 2015 | 30th june 2015 | 2996442.4 | 2996442.4 | 2996442.4 | CGK |  | 2996442.4 | 0 |  | 100% | 2996442.4 |  |  | complete
| Endoinyo Sumeiria pri. | construction of 1no classrooms | to increase enrolment | construction of 1no classrooms | 3110200 | construction of buildings | kajiado south | Kimana |  | education | education | education | 1st july2014 | 1st aug 2014 | 30th june 2015 | 30th june 2015 | 3017517.6 | 3017517.6 | 3017517.6 | CGK |  | 3017517.6 | 0 |  | 100% | 3017517.6 |  |  | complete
| Olodungoro primary school | construction of 2no classrooms | to increase enrolment | construction of 2no classrooms | 3110200 | construction of buildings | kajiado west | Ewuaso oo Nkidongi |  | education | education | education | 1st july2014 | 1st aug 2014 | 30th june 2015 | 30th june 2015 | 3010942 | 3010942 | 3010942 | CGK |  | 3010942 | 0 |  | 100% | 3010942 |  |  | complete
| Noolasit primary school | construction of 2no classrooms | to increase enrolment | construction of 2no classrooms | 3110200 | construction of buildings | kajiado south | Rombo |  | education | education | education | 1st july2014 | 1st aug 2014 | 30th june 2015 | 30th june 2015 | 2998616.24 | 2998616.24 | 2998616.24 | CGK |  | 2998616.24 | 0 |  | 100% | 2998616.24 |  |  | complete
| Kiserian primary school | construction of 2no classrooms | to increase enrolment | construction of 2no classrooms | 3110200 | construction of buildings | kajiado west | Keekonyokie |  | education | education | education | 1st july2014 | 1st aug 2014 | 30th june 2015 | 30th june 2015 | 3968368 | 3968368 | 3968368 | CGK |  | 3968368 | 0 |  | 100% | 3968368 |  |  | complete
| Murantawua primary school | construction of 2no classrooms | to increase enrolment | construction of 2no classrooms | 3110200 | construction of buildings | kajiado central | ildamat |  | education | education | education | 1st july2014 | 1st aug 2014 | 30th june 2015 | 30th june 2015 | 4999350.6 | 4999350.6 | 4999350.6 | CGK |  | 4999350.6 | 0 |  | 100% | 4999350.6 |  |  | complete
| Utumishi sacco primary sch. | Construction of office block | to increase enrolment | Construction of office block | 3110200 | construction of buildings | kajiado east | Kitengela |  | education | education | education | 1st july2014 | 1st aug 2014 | 30th june 2015 | 30th june 2015 | 3005962 | 3005962 | 3005962 | CGK |  | 3005962 | 0 |  | 100% | 3005962 |  |  | complete
| Elerai primary sch. | construction of ECDE centre | to increase enrolment | construction of ECDE centre | 3110200 | construction of buildings | kajiado south | Kuku ward |  | education | education | education | 1st july2014 | 1st aug 2014 | 30th june 2015 | 30th june 2015 | 30055962 | 30055962 | 30055962 | CGK |  | 30055962 | 0 |  | 100% | 30055962 |  |  | complete
| Oloibor Toto primary sch. | construction of 2no classrooms | to increase enrolment | construction of 2no classrooms | 3110200 | construction of buildings | kajiado west | Magadi |  | education | education | education | 1st july2014 | 1st aug 2014 | 30th june 2015 | 30th june 2015 | 4963860 | 4963860 | 4963860 | CGK |  | 4963860 | 0 |  | 100% | 4963860 |  |  | complete
| Lorngosua Musenke | construction of 2No classrooms | to increase enrolment | construction of 2No classrooms | 3110200 | construction of buildings | kajiado west | Magadi |  | education | education | education | 1st july2014 | 1st aug 2014 | 30th june 2015 | 30th june 2015 | 2999945.6 | 2999945.6 | 2999945.6 | CGK |  | 2999945.6 | 0 |  | 100% | 2999945.6 |  |  | complete
| Entaretoi sec. school | construction of 64 bed dormitory | to increase enrolment | construction of 64 bed dormitory | 3110200 | construction of buildings | kajiado east | Kenyawa poka |  | education | education | education | 1st july2014 | 1st aug 2014 | 30th june 2015 | 30th june 2015 | 2999249.6 | 2999249.6 | 2999249.6 | CGK |  | 2999249.6 | 0 |  | 100% | 2999249.6 |  |  | complete
| Olmapinu primary school | construction of 2no classrooms | to increase enrolment | construction of 2no classrooms | 3110200 | construction of buildings | kajiado south | Rombo |  | education | education | education | 1st july2014 | 1st aug 2014 | 30th june 2015 | 30th june 2015 | 4942342.4 | 4942342.4 | 4942342.4 | CGK |  | 4942342.4 | 0 |  | 100% | 4942342.4 |  |  | complete
| Oloibor soit sec.school | construction of Adm block | to increase enrolment | construction of Adm block | 3110200 | construction of buildings | kajiado west | Iloodokilani |  | education | education | education | 1st july2014 | 1st aug 2014 | 30th june 2015 | 30th june 2015 | 12814628.85 | 12814628.85 | 12814628.85 | CGK |  | 12814628.85 | 0 |  | 100% | 12814628.85 |  |  | complete
| Kimana mixed sec.school | construction of Science laboratory | to increase enrolment | construction of Science laboratory | 3110200 | construction of buildings | kajiado south | Kimana |  | education | education | education | 1st july2014 | 1st aug 2014 | 30th june 2015 | 30th june 2015 | 2497364 | 2497364 | 2497364 | CGK |  | 2497364 | 0 |  | 100% | 2497364 |  |  | complete
| Oloolua Polytechnique | construction of Oloolua Polytechnique | to increase enrolment | construction of Oloolua Polytechnique | 3110200 | construction of buildings | kajiado north | Oloolua |  | education | education | education | 1st july2014 | 1st aug 2014 | 30th june 2015 | 30th june 2015 | 2960548 | 2960548 | 2960548 | CGK |  | 2960548 | 0 |  | 100% | 2960548 |  |  | complete
| Ketura ECDE | construction of 2no ECDE classroom | to increase enrolment | construction of 2no ECDE classroom | 3110200 | construction of buildings | kajiado west | Keekonyokie |  | education | education | education | 1st july2014 | 1st aug 2014 | 30th june 2015 | 30th june 2015 | 2991360 | 2991360 | 2991360 | CGK |  | 2991360 | 0 |  | 100% | 2991360 |  |  | complete
| Komia primary school | construction of 2no classrooms | to increase enrolment | construction of 2no classrooms | 3110200 | construction of buildings | kajiado west | Magadi |  | education | education | education | 1st july2014 | 1st aug 2014 | 30th june 2015 | 30th june 2015 | 3006031 | 3006031 | 3006031 | CGK |  | 3006031 | 0 |  | 100% | 3006031 |  |  | complete
| Oltepesi primary school | construction of 2no classrooms | to increase enrolment | construction of 2no classrooms | 3110200 | construction of buildings | kajiado west | Iloodokilani |  | education | education | education | 1st july2014 | 1st aug 2014 | 30th june 2015 | 30th june 2015 | 2973000 | 2973000 | 2973000 | CGK |  | 2973000 | 0 |  | 100% | 2973000 |  |  | complete
| Eiti primary school | construction of 2no classrooms | to increase enrolment | construction of 2no classrooms | 3110200 | construction of buildings | kajiado west | Keekonyokie |  | education | education | education | 1st july2014 | 1st aug 2014 | 30th june 2015 | 30th june 2015 | 2999491 | 2999491 | 2999491 | CGK |  | 2999491 | 0 |  | 100% | 2999491 |  |  | complete
| Eseki primary school | construction of 2no classrooms | to increase enrolment | construction of 2no classrooms | 3110200 | construction of buildings | kajiado central | Matapato North |  | education | education | education | 1st july2014 | 1st aug 2014 | 30th june 2015 | 30th june 2015 | 1906982 | 1906982 | 1906982 | CGK |  | 1906982 | 0 |  | 100% | 1906982 |  |  | complete
| Olkina primary school | construction of 2no classrooms | to increase enrolment | construction of 2no classrooms | 3110200 | construction of buildings | kajiado south | Imbirikani |  | education | education | education | 1st july2014 | 1st aug 2014 | 30th june 2015 | 30th june 2015 | 5056804.2 | 5056804.2 | 5056804.2 | CGK |  | 5056804.2 | 0 |  | 100% | 5056804.2 |  |  | complete
| Ilparakuo pri.sch | construction of 2no clasrroms | to increase enrolment | construction of 2no clasrroms | 3110200 | construction of buildings | kajiado west | Magadi |  | education | education | education | 1st july2014 | 1st aug 2014 | 30th june 2015 | 30th june 2015 | 2999164.2 | 2999164.2 | 2999164.2 | CGK |  | 2999164.2 | 0 |  | 100% | 2999164.2 |  |  | complete
| Olentoko pri.sch. | construction of 2no classroom,2no,staffhouse,pit latrine | to increase enrolment | construction of 2no classroom,2no,staffhouse,pit latrine | 3110200 | construction of buildings | kajiado west | Ewuaso oo Nkidongi |  | education | education | education | 1st july2014 | 1st aug 2014 | 30th june 2015 | 30th june 2015 | 4996603 | 4996603 | 4996603 | CGK |  | 4996603 | 0 |  | 100% | 4996603 |  |  | complete
| Enkusero primary school | construction of 2no classrooms | to increase enrolment | construction of 2no classrooms | 3110200 | construction of buildings | kajiado south | KUKU |  | education | education | education | 1st july2014 | 1st aug 2014 | 30th june 2015 | 30th june 2015 | 2164870.8 | 2164870.8 | 2164870.8 | CGK |  | 2164870.8 | 0 |  | 100% | 2164870.8 |  |  | complete
| Ilpolosat sec.school | construction of 64 bed dormitory | to increase enrolment | construction of 64 bed dormitory | 3110200 | construction of buildings | kajiado east | Kaputiei north |  | education | education | education | 1st july2014 | 1st aug 2014 | 30th june 2015 | 30th june 2015 | 2999900 | 2999900 | 2999900 | CGK |  | 2999900 | 0 |  | 100% | 2999900 |  |  | complete
| Singiraine pri.sch. | construction of Adm block | to increase enrolment | construction of Adm block | 3110200 | construction of buildings | kajiado west | Iloodokilani |  | education | education | education | 1st july2014 | 1st aug 2014 | 30th june 2015 | 30th june 2015 | 2999156.8 | 2999156.8 | 2999156.8 | CGK |  | 2999156.8 | 0 |  | 100% | 2999156.8 |  |  | complete
| Ereteti sec.school | construction 2no classrooms | to increase enrolment | construction 2no classrooms | 3110200 | construction of buildings | kajiodo west | Keekonyokie |  | education | education | education | 1st july2014 | 1st aug 2014 | 30th june 2015 | 30th june 2015 | 7999680.16 | 7999680.16 | 7999680.16 | CGK |  | 7999680.16 | 0 |  | 100% | 7999680.16 |  |  | complete
| Olgirra primary school | construction of 2no classroooms | to increase enrolment | construction of 2no classroooms | 3110200 | construction of buildings | kajio south | Rombo |  | education | education | education | 1st july2014 | 1st aug 2014 | 30th june 2015 | 30th june 2015 | 2975069.4 | 2975069.4 | 2975069.4 | CGK |  | 2975069.4 | 0 |  | 100% | 2975069.4 |  |  | complete
| kibiko secondary | construction of 1no 64 bed dormitory | to increase enrolment | construction of 1no 64 bed dormitory | 3110200 | construction of buildings | kajiodo west | Ewuaso oo Nkidongi |  | education | education | education | 1st july2014 | 1st aug 2014 | 30th june 2015 | 30th june 2015 | 1570442.8 | 1570442.8 | 1570442.8 | CGK |  | 1570442.8 | 0 |  | 100% | 1570442.8 |  |  | complete
| sompet primary | construction of 2no classroom | to increase enrolment | construction of 2no classroom | 3110200 | construction of buildings | kajiado south | Kimana |  | education | education | education | 1st july2014 | 1st aug 2014 | 30th june 2015 | 30th june 2015 | 3011751.2 | 3011751.2 | 3011751.2 | CGK |  | 3011751.2 | 0 |  | 100% | 3011751.2 |  |  | complete
| isinya township primary | construction of 1no classroom | to increase enrolment | construction of 1no classroom | 3110200 | construction of buildings | kajiado east | Kaputiei north |  | education | education | education | 1st july2014 | 1st aug 2014 | 30th june 2015 | 30th june 2015 | 3005932 | 3005932 | 3005932 | CGK |  | 3005932 | 0 |  | 100% | 3005932 |  |  | complete
| enkariak rongena primary | construction of 2no classrooms | to increase enrolment | construction of 2no classrooms | 3110200 | construction of buildings | kajiado south | KUKU |  | education | education | education | 1st july2014 | 1st aug 2014 | 30th june 2015 | 30th june 2015 | 3996026 | 3996026 | 3996026 | CGK |  | 3996026 | 0 |  | 100% | 3996026 |  |  | complete
| erankau primary | construction of 2no classrooms | to increase enrolment | construction of 2no classrooms | 3110200 | construction of buildings | kajiado east | Imaroro |  | education | education | education | 1st july2014 | 1st aug 2014 | 30th june 2015 | 30th june 2015 | 5194385 | 5194385 | 5194385 | CGK |  | 5194385 | 0 |  | 100% | 5194385 |  |  | complete
| thomasfish secondary | construction of 40 beddormitory | to increase enrolment | construction of 40 beddormitory | 3110200 | construction of buildings | kajiado east | Kenyawa poka |  | education | education | education | 1st july2014 | 1st aug 2014 | 30th june 2015 | 30th june 2015 | 2943616 | 2943616 | 2943616 | CGK |  | 2943616 | 0 |  | 100% | 2943616 |  |  | complete
| gichagi-ngong | construction of ecde block | to increase enrolment | construction of ecde block | 3110200 | construction of buildings | kajiado north | Ngong |  | education | education | education | 1st july2014 | 1st aug 2014 | 30th june 2015 | 30th june 2015 | 3008947.2 | 3008947.2 | 3008947.2 | CGK |  | 3008947.2 | 0 |  | 100% | 3008947.2 |  |  | complete
| oltiyani primary | construction of 2no classrooms | to increase enrolment | construction of 2no classrooms | 3110200 | construction of buildings | kajiado north | Olkeri |  | education | education | education | 1st july2014 | 1st aug 2014 | 30th june 2015 | 30th june 2015 | 4497717.9 | 4497717.9 | 4497717.9 | CGK |  | 4497717.9 | 0 |  | 100% | 4497717.9 |  |  | complete
| matepesi primary | construction of 2no classroom | to increase enrolment | construction of 2no classroom | 3110200 | construction of buildings | kajiado south | Rombo |  | education | education | education | 1st july2014 | 1st aug 2014 | 30th june 2015 | 30th june 2015 | 4999669.6 | 4999669.6 | 4999669.6 | CGK |  | 4999669.6 | 0 |  | 100% | 4999669.6 |  |  | complete
| oldarpoi ECDE | construction of 2no classroom,sleeping area,staffroom lib | to increase enrolment | construction of 2no classroom,sleeping area,staffroom lib | 3110200 | construction of buildings | kajiado west | Mosiro |  | education | education | education | 1st july2014 | 1st aug 2014 | 30th june 2015 | 30th june 2015 | 1498940 | 1498940 | 1498940 | CGK |  | 1498940 | 0 |  | 100% | 1498940 |  |  | complete
| Emurkeya pri. | Construction of 64 bed dormitory | to increase enrolment | Construction of 64 bed dormitory | 3110200 | construction of buildings | kajiado west | Iloodokilani |  | education | education | education | 1st july2014 | 1st aug 2014 | 30th june 2015 | 30th june 2015 | 3126840 | 3126840 | 3126840 | CGK |  | 3126840 | 0 |  | 100% | 3126840 |  |  | complete
| Emurtot pri. | Construction of 1no classroom | to increase enrolment | Construction of 1no classroom | 3110200 | construction of buildings | kajiado south | Kuku |  | education | education | education | 1st july2014 | 1st aug 2014 | 30th june 2015 | 30th june 2015 | 5016823 | 5016823 | 5016823 | CGK |  | 5016823 | 0 |  | 100% | 5016823 |  |  | complete
| Emporr nalepo | construction of 2no classrooms | to increase enrolment | construction of 2no classrooms | 3110200 | construction of buildings | kajiado central | Ildamat |  | education | education | education | 1st july2014 | 1st aug 2014 | 30th june 2015 | 30th june 2015 | 3271148.4 | 3271148.4 | 3271148.4 | CGK |  | 3271148.4 | 0 |  | 100% | 3271148.4 |  |  | complete
| Kitengela stadium | construction of Kitengela stadium | to increase enrolment | construction of Kitengela stadium | 3110200 | construction of buildings | kajiado east | Sholinke oloosirkon |  | education | education | education | 1st july2014 | 1st aug 2014 | 30th june 2015 | 30th june 2015 | 2995000 | 2995000 | 2995000 | CGK |  | 2995000 | 0 |  | 100% | 2995000 |  |  | complete
| noonkoben primary | construction of 3no classroom | to increase enrolment | construction of 3no classroom | 3110200 | construction of buildings | kajiado east | Poka kenyawa |  | education | education | education | 1st july2014 | 1st aug 2014 | 30th june 2015 | 30th june 2015 | 2501888 | 2501888 | 2501888 | CGK |  | 2501888 | 0 |  | 100% | 2501888 |  |  | complete
| Namanga mixed sec.school | construction of Labaratory | to increase enrolment | construction of Labaratory | 3110200 | construction of buildings | kajiado central | matapato south |  | education | education | education | 1st july2014 | 1st aug 2014 | 30th june 2015 | 30th june 2015 | 4961522 | 4961522 | 4961522 | CGK |  | 4961522 | 0 |  | 100% | 4961522 |  |  | complete
| oldorko pri.sch. | construction of Adm block | to increase enrolment | construction of Adm block | 3110200 | construction of buildings | kajiado west | Mosiro |  | education | education | education | 1st july2014 | 1st aug 2014 | 30th june 2015 | 30th june 2015 | 1493906 | 1493906 | 1493906 | CGK |  | 1493906 | 0 |  | 100% | 1493906 |  |  | complete
| enkeju oolokuarak | construction of ECDE and staff house | to increase enrolment | construction of ECDE and staff house | 3110200 | construction of buildings | kajiado east | Sholinke oloosirkon |  | education | education | education | 1st july2014 | 1st aug 2014 | 30th june 2015 | 30th june 2015 | 4966627 | 4966627 | 4966627 | CGK |  | 4966627 | 0 |  | 100% | 4966627 |  |  | complete
| Moipei primary | construction of 2no 3 door pitlatrine | to increase enrolment | construction of 2no 3 door pitlatrine | 3110200 | construction of buildings | kajiado central | Ildamat |  | education | education | education | 1st july2014 | 1st aug 2014 | 30th june 2015 | 30th june 2015 | 1499856 | 1499856 | 1499856 | CGK |  | 1499856 | 0 |  | 100% | 1499856 |  |  | complete
| Lorngosua ECDE centre | construction of ECDE centre | to increase enrolment | construction of ECDE centre | 3110200 | construction of buildings | kajiado central | Matapato north |  | education | education | education | 1st july2014 | 1st aug 2014 | 30th june 2015 | 30th june 2015 | 3044582 | 3044582 | 3044582 | CGK |  | 3044582 | 0 |  | 100% | 3044582 |  |  | complete
| Oldulei pri.sch | construction of 1no classroom | to increase enrolment | construction of 1no classroom | 3110200 | construction of buildings | kajiado south | Entonet lenkisim |  | education | education | education | 1st july2014 | 1st aug 2014 | 30th june 2015 | 30th june 2015 | 5992670 | 5992670 | 5992670 | CGK |  | 5992670 | 0 |  | 100% | 5992670 |  |  | complete
| Emparinkoi primary | construction of 2no classrooms | to increase enrolment | construction of 2no classrooms | 3110200 | construction of buildings | kajiado south | Entonet lenkisim |  | education | education | education | 1st july2014 | 1st aug 2014 | 30th june 2015 | 30th june 2015 | 19846494 | 19846494 | 19846494 | CGK |  | 19846494 | 0 |  | 100% | 19846494 |  |  | complete
| Irmaba secondary | construction of 4no classrooms | to increase enrolment | construction of 4no classrooms | 3110200 | construction of buildings | kajiado central | Matapato north |  | education | education | education | 1st july2014 | 1st aug 2014 | 30th june 2015 | 30th june 2015 | 3007491.2 | 3007491.2 | 3007491.2 | CGK |  | 3007491.2 | 0 |  | 100% | 3007491.2 |  |  | complete
| Desighn for Ngong stadium | construction of Desighn for Ngong stadium | to increase enrolment | construction of Desighn for Ngong stadium | 3110200 | construction of buildings | kajiado north | Ngong |  | education | education | education | 1st july2014 | 1st aug 2014 | 30th june 2015 | 30th june 2015 | 4997240.3 | 4997240.3 | 4997240.3 | CGK |  | 4997240.3 | 0 |  | 100% | 4997240.3 |  |  | complete
| Aic Loitoktok sec | construction of 2no classrooms | to increase enrolment | construction of 2no classrooms | 3110200 | construction of buildings | kajiado south | Kuku |  | education | education | education | 1st july2014 | 1st aug 2014 | 30th june 2015 | 30th june 2015 | 1499020 | 1499020 | 1499020 | CGK |  | 1499020 | 0 |  | 100% | 1499020 |  |  | complete
| Paranae ECDE | Construction of ECDE classroom | to increase enrolment | Construction of ECDE classroom | 3110200 | construction of buildings | kajiado central | Ildamat |  | education | education | education | 1st july2014 | 1st aug 2014 | 30th june 2015 | 30th june 2015 | 1507710 | 1507710 | 1507710 | CGK |  | 1507710 | 0 |  | 100% | 1507710 |  |  | complete
| oloserian Orkiu | construction of 1No classroom | to increase enrolment | construction of 1No classroom | 3110200 | construction of buildings | kajaido central | Matapato south |  | education | education | education | 1st july2014 | 1st aug 2014 | 30th june 2015 | 30th june 2015 | 1498360 | 1498360 | 1498360 | CGK |  | 1498360 | 0 |  | 100% | 1498360 |  |  | complete
| torosei ecde | construction of 1no classroom | to increase enrolment | construction of 1no classroom | 3110200 | construction of buildings | kajiado west | Iloodokilani |  | education | education | education | 1st july2014 | 1st aug 2014 | 30th june 2015 | 30th june 2015 | 2998112.8 | 2998112.8 | 2998112.8 | CGK |  | 2998112.8 | 0 |  | 100% | 2998112.8 |  |  | complete
| Oldonyo lormoti primary school | construction of 1no classroom | to increase enrolment | construction of 1no classroom | 3110200 | construction of buildings | kajiado central | matapato north |  | education | education | education | 1st july2014 | 1st aug 2014 | 30th june 2015 | 30th june 2015 | 1499325 | 1499325 | 1499325 | CGK |  | 1499325 | 0 |  | 100% | 1499325 |  |  | complete
| Loosoito primary school | construction of 2no classrooms | to increase enrolment | construction of 2no classrooms | 3110200 | construction of buildings | kajiado south | kuku |  | education | education | education | 1st july2014 | 1st aug 2014 | 30th june 2015 | 30th june 2015 | 4998820 | 4998820 | 4998820 | CGK |  | 4998820 | 0 |  | 100% | 4998820 |  |  | complete
| Elerai primary | construction of 1no classroom | to increase enrolment | construction of 1no classroom | 3110200 | construction of buildings | kajiado south | entonet |  | education | education | education | 1st july2014 | 1st aug 2014 | 30th june 2015 | 30th june 2015 | 5050100 | 5050100 | 5050100 | CGK |  | 5050100 | 0 |  | 100% | 5050100 |  |  | complete
| Oloirien secondary | construction of 64 bed dormitory | to increase enrolment | construction of 64 bed dormitory | 3110200 | construction of buildings | kajiado south | Rombo |  | education | education | education | 1st july2014 | 1st aug 2014 | 30th june 2015 | 30th june 2015 | 2499520 | 2499520 | 2499520 | CGK |  | 2499520 | 0 |  | 100% | 2499520 |  |  | complete
| Enkongu Narok Primary | construction of 64bed dormotory | to increase enrolment | construction of 64bed dormotory | 3110200 | construction of buildings | kajiado south | entonet |  | education | education | education | 1st july2014 | 1st aug 2014 | 30th june 2015 | 30th june 2015 | 3020060 | 3020060 | 3020060 | CGK |  | 3020060 | 0 |  | 100% | 3020060 |  |  | complete
| isinya boys sec.school | construction of Admn block at isinya boys | to increase enrolment | construction of Admn block at isinya boys | 3110200 | construction of buildings | kajiado east | Kaputiei north |  | education | education | education | 1st july2014 | 1st aug 2014 | 30th june 2015 | 30th june 2015 | 1,6395,86.7 | 1,6395,86.7 | 1,6395,86.7 | CGK |  | 1,6395,86.7 | 0 |  | 100% | 1,6395,86.7 |  |  | complete
| shurie pri. | construction of 2no classrooms | to increase enrolment | construction of 2no classrooms | 3110200 | construction of buildings | kajiado south | kuku |  | education | education | education | 1st july2014 | 1st aug 2014 | 30th june 2015 | 30th june 2015 | 4961552 | 4961552 | 4961552 | CGK |  | 4961552 | 0 |  | 100% | 4961552 |  |  | complete
| eluai primary | construction of 2no classrooms | to increase enrolment | construction of 2no classrooms | 3110200 | construction of buildings | kajiado south | entonet lenkisem |  | education | education | education | 1st july2014 | 1st aug 2014 | 30th june 2015 | 30th june 2015 | 4998820 | 4998820 | 4998820 | CGK |  | 4998820 | 0 |  | 100% | 4998820 |  |  | complete
| Leboo primary sch. | construction of ECDE block and staff house | to increase enrolment | construction of ECDE block and staff house | 3110200 | construction of buildings | kajiado central | matapato north |  | education | education | education | 1st july2014 | 1st aug 2014 | 30th june 2015 | 30th june 2015 | 3003500 | 3003500 | 3003500 | CGK |  | 3003500 | 0 |  | 100% | 3003500 |  |  | complete
| naningoi boarding school | construction of 64 bed dormitory | to increase enrolment | construction of 64 bed dormitory | 3110200 | construction of buildings | kajiado west | Mosiro |  | education | education | education | 1st july2014 | 1st aug 2014 | 30th june 2015 | 30th june 2015 | 1500000 | 1500000 | 1500000 | CGK |  | 1500000 | 0 |  | 100% | 1500000 |  |  | complete
| Ndarkalali pri.sch | construction of 2no staffhouse | to increase enrolment | construction of 2no staffhouse | 3110200 | construction of buildings | kajiado west | Magadi |  | education | education | education | 1st july2014 | 1st aug 2014 | 30th june 2015 | 30th june 2015 | 10252823 | 10252823 | 10252823 | CGK |  | 10252823 | 0 |  | 100% | 10252823 |  |  | complete
| olepolos primary | construction 1no classroom | to increase enrolment | construction 1no classroom | 3110200 | construction of buildings | kajiado south | entonet |  | education | education | education | 1st july2014 | 1st aug 2014 | 30th june 2015 | 30th june 2015 | 4995105 | 4995105 | 4995105 | CGK |  | 4995105 | 0 |  | 100% | 4995105 |  |  | complete
| Ewuaso pri. | construction of 2no classroom,40 bed dormitory and kitchen | to increase enrolment | construction of 2no classroom,40 bed dormitory and kitchen | 3110200 | construction of buildings | kajiado west | Ewuaso oo Nkidongi |  | education
| oloontulugum | construction of 64 bed dormitory | to increase enrolment | construction of 64 bed dormitory | 3110200 | construction of buildings | kajiado central | Dalalekutuk |  | education | education | education | 2015-07-01 | 2015-08-01 | 2016-06-01 | 2016-06-01 | 6959127.9 | 6959127.9 | 6959127.9 | CGK |  | 6959127.9 | 0 |  | 100% | 6959127.9 |  |  | complete
[11 empty] | education | education | 2015-07-01 | 2015-08-01 | 2016-06-01 | 2016-06-01 | 1484834 | 1484834 | 1484834 | CGK |  | 1484834 | 0 |  | 100% | 1484834 |  |  | complete
| Matasia social hall | construction of matasia hall | to increase enrolment | construction of matasia hall | 3110200 | construction of buildings | kajiado north | Olkeri |  | education | education | education | 2015-07-01 | 2015-08-01 | 2016-06-01 | 2016-06-01 | 3028423 | 3028423 | 3028423 | CGK |  | 3028423 | 0 |  | 100% | 3028423 |  |  | complete
| Olosurutia | construction of olosurutia ECDE centre | to increase enrolment | construction of olosurutia ECDE centre | 3110200 | construction of buildings | kajaido north | Olkeri |  | education | education | education | 2015-07-01 | 2015-08-01 | 2016-06-01 | 2016-06-01 | 1500000 | 1500000 | 1500000 | CGK |  | 1500000 | 0 |  | 100% | 1500000 |  |  | complete
| Kandisi ECDE | construction of kandisi ECDE | to increase enrolment | construction of kandisi ECDE | 3110200 | construction of buildings | kajiado north | Olkeri |  | education | education | education | 2015-07-01 | 2015-08-01 | 2016-06-01 | 2016-06-01 | 4497581 | 4497581 | 4497581 | CGK |  | 4497581 | 0 |  | 100% | 4497581 |  |  | complete
| Upper matasia ECDE | construction of upper matasia ECDE | to increase enrolment | construction of upper matasia ECDE | 3110200 | construction of buildings | kajiado north | Olkeri |  | education | education | education | 2015-07-01 | 2015-08-01 | 2016-06-01 | 2016-06-01 | 6002000 | 6002000 | 6002000 | CGK |  | 6002000 | 0 |  | 100% | 6002000 |  |  | complete
| Ilmerijo ECDE | construction of Ilmerijo ECDE | to increase enrolment | construction of Ilmerijo ECDE | 3110200 | construction of buildings | kajiado north | Olkeri |  | education | education | education | 2015-07-01 | 2015-08-01 | 2016-06-01 | 2016-06-01 | 6151027 | 6151027 | 6151027 | CGK |  | 6151027 | 0 |  | 100% | 6151027 |  |  | complete
| ECDE centre at Kerarapon | construction of ECDE centre at Kerarapon | to increase enrolment | construction of ECDE centre at Kerarapon | 3110200 | construction of buildings | kajiado north | Oloolua |  | education | education | education | 2015-07-01 | 2015-08-01 | 2016-06-01 | 2016-06-01 | 7000000 | 7000000 | 7000000 | CGK |  | 7000000 | 0 |  | 100% | 7000000 |  |  | complete
| Nakeel stadium enhancement | construction of nakeel stadium | to increase enrolment | construction of nakeel stadium | 3110200 | construction of buildings | kajiado north | Nkaimurunya |  | education | education | education | 2015-07-01 | 2015-08-01 | 2016-06-01 | 2016-06-01 | 38208204 | 38208204 | 38208204 | CGK |  | 38208204 | 0 |  | 100% | 38208204 |  |  | complete
| Youth plytechnic at Kware | construction of kware polytechnique | to increase enrolment | construction of kware polytechnique | 3110200 | construction of buildings | kajiado north | Nkaimurunya |  | education | education | education | 2015-07-01 | 2015-08-01 | 2016-06-01 | 2016-06-01 | 8000000 | 8000000 | 8000000 | CGK |  | 8000000 | 0 |  | 100% | 8000000 |  |  | complete
| Ngong stadium 1 block | construction of ngong stadium block | to increase enrolment | construction of ngong stadium block | 3110200 | construction of buildings | kajiado north | Ngong |  | education | education | education | 2015-07-01 | 2015-08-01 | 2016-06-01 | 2016-06-01 | 4000000 | 4000000 | 4000000 | CGK |  | 4000000 | 0 |  | 100% | 4000000 |  |  | complete
| bondeni ecde | construction of bondeni ecde | to increase enrolment | construction of bondeni ecde | 3110200 | construction of buildings | kajiado north | Ngong |  | education | education | education | 2015-07-01 | 2015-08-01 | 2016-06-01 | 2016-06-01 | 4000000 | 4000000 | 4000000 | CGK |  | 4000000 | 0 |  | 100% | 4000000 |  |  | complete
| ole kasasi ecde centre | construction of ole kasasi ecde centre | to increase enrolment | construction of ole kasasi ecde centre | 3110200 | construction of buildings | kajiado north | Ongata Rongai |  | education | education | education | 2015-07-01 | 2015-08-01 | 2016-06-01 | 2016-06-01 | 12000000 | 12000000 | 12000000 | CGK |  | 12000000 | 0 |  | 100% | 12000000 |  |  | complete
| ole kasasi youth polytechinc | construction of ole kasasi youth polytechnique | to increase enrolment | construction of ole kasasi youth polytechnique | 3110200 | construction of buildings | kajiado north | Ongata Rongai |  | education | education | education | 2015-07-01 | 2015-08-01 | 2016-06-01 | 2016-06-01 | 3000000 | 3000000 | 3000000 | CGK |  | 3000000 | 0 |  | 100% | 3000000 |  |  | complete
| ongata rongai social hall | construction of ongata rongai social hall | to increase enrolment | construction of ongata rongai social hall | 3110200 | construction of buildings | kajiado north | Ongata Rongai |  | education | education | education | 2015-07-01 | 2015-08-01 | 2016-06-01 | 2016-06-01 | 2999910 | 2999910 | 2999910 | CGK |  | 2999910 | 0 |  | 100% | 2999910 |  |  | complete
| Olepolos ECDE centre | construction of Olepolos ECDE centre | to increase enrolment | construction of Olepolos ECDE centre | 3110200 | construction of buildings | kajiado south | Entonet Lenkism |  | education | education | education | 2015-07-01 | 2015-08-01 | 2016-06-01 | 2016-06-01 | 3000000 | 3000000 | 3000000 | CGK |  | 3000000 | 0 |  | 100% | 3000000 |  |  | complete
| risa ecde centre | construction of risa ecde centre | to increase enrolment | construction of risa ecde centre | 3110200 | construction of buildings | kajiado south | Entonet Lenkism |  | education | education | education | 2015-07-01 | 2015-08-01 | 2016-06-01 | 2016-06-01 | 2000000 | 2000000 | 2000000 | CGK |  | 2000000 | 0 |  | 100% | 2000000 |  |  | complete
| olgulului pri | construction of admn. Block | to increase enrolment | construction of admn. Block | 3110200 | construction of buildings | kajiado south | Entonet Lenkism |  | education | education | education | 2015-07-01 | 2015-08-01 | 2016-06-01 | 2016-06-01 | 4985900 | 4985900 | 4985900 | CGK |  | 4985900 | 0 |  | 100% | 4985900 |  |  | complete
| esoit pri. | construction of pitlatrine | to increase enrolment | construction of pitlatrine | 3110200 | construction of buildings | kajiado south | Entonet Lenkism |  | education | education | education | 2015-07-01 | 2015-08-01 | 2016-06-01 | 2016-06-01 | 2986880 | 2986880 | 2986880 | CGK |  | 2986880 | 0 |  | 100% | 2986880 |  |  | complete
| amboseli pri. | construction of a dormitory | to increase enrolment | construction of a dormitory | 3110200 | construction of buildings | kajiado south | Entonet Lenkism |  | education | education | education | 2015-07-01 | 2015-08-01 | 2016-06-01 | 2016-06-01 | 1000000 | 1000000 | 1000000 | CGK |  | 1000000 | 0 |  | 100% | 1000000 |  |  | complete
| parane primary | construction of an ecde centre | to increase enrolment | construction of an ecde centre | 3110200 | construction of buildings | kajiado south | Entonet Lenkism |  | education | education | education | 2015-07-01 | 2015-08-01 | 2016-06-01 | 2016-06-01 | 2988757.4 | 2988757.4 | 2988757.4 | CGK |  | 2988757.4 | 0 |  | 100% | 2988757.4 |  |  | complete
| olchorro pri. | equiping of ecde descks | to increase enrolment | equiping of ecde descks | 3110200 | construction of buildings | kajiado south | Entonet Lenkism |  | education | education | education | 2015-07-01 | 2015-08-01 | 2016-06-01 | 2016-06-01 | 4999223 | 4999223 | 4999223 | CGK |  | 4999223 | 0 |  | 100% | 4999223 |  |  | complete
| enkirgirri pri | construction of ecde centre | to increase enrolment | construction of ecde centre | 3110200 | construction of buildings | kajiado south | Imbirikani |  | education | education | education | 2015-07-01 | 2015-08-01 | 2016-06-01 | 2016-06-01 | 2000000 | 2000000 | 2000000 | CGK |  | 2000000 | 0 |  | 100% | 2000000 |  |  | complete
| lenkisem sec . | construction of a lab | to increase enrolment | construction of a lab | 3110200 | construction of buildings | kajiado south | Imbirikani |  | education | education | education | 2015-07-01 | 2015-08-01 | 2016-06-01 | 2016-06-01 | 2997221.92 | 2997221.92 | 2997221.92 | CGK |  | 2997221.92 | 0 |  | 100% | 2997221.92 |  |  | complete
| imbirikani ECDE | equiping of ecde | to increase enrolment | equiping of ecde | 3110200 | construction of buildings | kajiado south | Imbirikani |  | education | education | education | 2015-07-01 | 2015-08-01 | 2016-06-01 | 2016-06-01 | 2973474 | 2973474 | 2973474 | CGK |  | 2973474 | 0 |  | 100% | 2973474 |  |  | complete
| shilishili pri. | construction of an ecde centre | to increase enrolment | construction of an ecde centre | 3110200 | construction of buildings | kajiado south | Imbirikani |  | education | education | education | 2015-07-01 | 2015-08-01 | 2016-06-01 | 2016-06-01 | 7999081.8 | 7999081.8 | 7999081.8 | CGK |  | 7999081.8 | 0 |  | 100% | 7999081.8 |  |  | complete
| olkiloriti pri. | construction of an ecde centre | to increase enrolment | construction of an ecde centre | 3110200 | construction of buildings | kajiado south | Rombo |  | education | education | education | 2015-07-01 | 2015-08-01 | 2016-06-01 | 2016-06-01 | 2999934 | 2999934 | 2999934 | CGK |  | 2999934 | 0 |  | 100% | 2999934 |  |  | complete
| rombo girls sec. | construction of a dormitory | to increase enrolment | construction of a dormitory | 3110200 | construction of buildings | kajiado south | Rombo |  | education | education | education | 2015-07-01 | 2015-08-01 | 2016-06-01 | 2016-06-01 | 3000000 | 3000000 | 3000000 | CGK |  | 3000000 | 0 |  | 100% | 3000000 |  |  | complete
| ilasit pri. | construction of admn. Block | to increase enrolment | construction of admn. Block | 3110200 | construction of buildings | kajiado south | Rombo |  | education | education | education | 2015-07-01 | 2015-08-01 | 2016-06-01 | 2016-06-01 | 2939829 | 2939829 | 2939829 | CGK |  | 2939829 | 0 |  | 100% | 2939829 |  |  | complete
| kikelelwa sec. | construction of 2no.classroom | to increase enrolment | construction of 2no.classroom | 3110200 | construction of buildings | kajiado south | Rombo |  | education | education | education | 2015-07-01 | 2015-08-01 | 2016-06-01 | 2016-06-01 | 2996303.2 | 2996303.2 | 2996303.2 | CGK |  | 2996303.2 | 0 |  | 100% | 2996303.2 |  |  | complete
| enchurrai pri. | construction of an ecde centre | to increase enrolment | construction of an ecde centre | 3110200 | construction of buildings | kajiado south | Rombo |  | education | education | education | 2015-07-01 | 2015-08-01 | 2016-06-01 | 2016-06-01 | 3000000 | 3000000 | 3000000 | CGK |  | 3000000 | 0 |  | 100% | 3000000 |  |  | complete
| esosian pri. | construction of an ecde centre | to increase enrolment | construction of an ecde centre | 3110200 | construction of buildings | kajiado south | Rombo |  | education | education | education | 2015-07-01 | 2015-08-01 | 2016-06-01 | 2016-06-01 | 2973544 | 2973544 | 2973544 | CGK |  | 2973544 | 0 |  | 100% | 2973544 |  |  | complete
| rombo pri. | construction of an ecde centre | to increase enrolment | construction of an ecde centre | 3110200 | construction of buildings | kajiado south | Rombo |  | education | education | education | 2015-07-01 | 2015-08-01 | 2016-06-01 | 2016-06-01 | 2400000 | 2400000 | 2400000 | CGK |  | 2400000 | 0 |  | 100% | 2400000 |  |  | complete
| maisuyati pri. | construction of an ecde centre | to increase enrolment | construction of an ecde centre | 3110200 | construction of buildings | kajiado south | Kimana |  | education | education | education | 2015-07-01 | 2015-08-01 | 2016-06-01 | 2016-06-01 | 3000000 | 3000000 | 3000000 | CGK |  | 3000000 | 0 |  | 100% | 3000000 |  |  | complete
| namelok pri. | renovation | to increase enrolment | renovation | 3110200 | construction of buildings | kajiado south | Kimana |  | education | education | education | 2015-07-01 | 2015-08-01 | 2016-06-01 | 2016-06-01 | 1980700 | 1980700 | 1980700 | CGK |  | 1980700 | 0 |  | 100% | 1980700 |  |  | complete
| oltiasika pri. | construction of 2no. Ecde classes | to increase enrolment | construction of 2no. Ecde classes | 3110200 | construction of buildings | kajiado south | Kuku |  | education | education | education | 2015-07-01 | 2015-08-01 | 2016-06-01 | 2016-06-01 | 2987649 | 2987649 | 2987649 | CGK |  | 2987649 | 0 |  | 100% | 2987649 |  |  | complete
| Oltiasika primary school | fencing | to increase enrolment | fencing | 3110200 | construction of buildings | kajiado south | kuku |  | education | education | education | 2015-07-01 | 2015-08-01 | 2016-06-01 | 2016-06-01 | 3000000 | 3000000 | 3000000 | CGK |  | 3000000 | 0 |  | 100% | 3000000 |  |  | complete
| enkii pri. | construction of an admn block | to increase enrolment | construction of an admn block | 3110200 | construction of buildings | kajiado south | Kuku |  | education | education | education | 2015-07-01 | 2015-08-01 | 2016-06-01 | 2016-06-01 | 2999957 | 2999957 | 2999957 | CGK |  | 2999957 | 0 |  | 100% | 2999957 |  |  | complete
| samai pri. | construction of 2no. ecde classes | to increase enrolment | construction of 2no. ecde classes | 3110200 | construction of buildings | kajiado south | Kuku |  | education | education | education | 2015-07-01 | 2015-08-01 | 2016-06-01 | 2016-06-01 | 1500000 | 1500000 | 1500000 | CGK |  | 1500000 | 0 |  | 100% | 1500000 |  |  | complete
| iltilal pri. | construction of 2no ecde classes | to increase enrolment | construction of 2no ecde classes | 3110200 | construction of buildings | kajiado south | Kuku |  | education | education | education | 2015-07-01 | 2015-08-01 | 2016-06-01 | 2016-06-01 | 1500000 | 1500000 | 1500000 | CGK |  | 1500000 | 0 |  | 100% | 1500000 |  |  | complete
| kuku pri. | equiping and purchase of ecde descks | to increase enrolment | equiping and purchase of ecde descks | 3110200 | construction of buildings | kajiado south | Kuku |  | education | education | education | 2015-07-01 | 2015-08-01 | 2016-06-01 | 2016-06-01 | 2000000 | 2000000 | 2000000 | CGK |  | 2000000 | 0 |  | 100% | 2000000 |  |  | complete
| narok enterit pri. | construction of 1no. Ecde class | to increase enrolment | construction of 1no. Ecde class | 3110200 | construction of buildings | kajiado south | Kuku |  | education | education | education | 2015-07-01 | 2015-08-01 | 2016-06-01 | 2016-06-01 | 2798596 | 2798596 | 2798596 | CGK |  | 2798596 | 0 |  | 100% | 2798596 |  |  | complete
| enkilele pri. | construction of an ecde | to increase enrolment | construction of an ecde | 3110200 | construction of buildings | kajiado east | Kaputiei north |  | education | education | education | 2015-07-01 | 2015-08-01 | 2016-06-01 | 2016-06-01 | 1000000 | 1000000 | 1000000 | CGK |  | 1000000 | 0 |  | 100% | 1000000 |  |  | complete
| enkeju oo lowuarak | equiping of ecde centre | to increase enrolment | equiping of ecde centre | 3110200 | construction of buildings | kajiado east | Kitengela |  | education | education | education | 2015-07-01 | 2015-08-01 | 2016-06-01 | 2016-06-01 | 5000000 | 5000000 | 5000000 | CGK |  | 5000000 | 0 |  | 100% | 5000000 |  |  | complete
| enkeju oo lowuarak pri. | fencing | to increase enrolment | fencing | 3110200 | construction of buildings | kajiado east | Kitengela |  | education | education | education | 2015-07-01 | 2015-08-01 | 2016-06-01 | 2016-06-01 | 1499931.04 | 1499931.04 | 1499931.04 | CGK |  | 1499931.04 | 0 |  | 100% | 1499931.04 |  |  | complete
| kitengela ecde | construction and equiping | to increase enrolment | construction and equiping | 3110200 | construction of buildings | kajiado east | Kitengela |  | education | education | education | 2015-07-01 | 2015-08-01 | 2016-06-01 | 2016-06-01 | 1496980 | 1496980 | 1496980 | CGK |  | 1496980 | 0 |  | 100% | 1496980 |  |  | complete
| ewangan oo nkama pri. | fencing | to increase enrolment | fencing | 3110200 | construction of buildings | kajiado east | Kenyawa poka |  | education | education | education | 2015-07-01 | 2015-08-01 | 2016-06-01 | 2016-06-01 | 6000000 | 6000000 | 6000000 | CGK |  | 6000000 | 0 |  | 100% | 6000000 |  |  | complete
| kunchu pri. | fencing | to increase enrolment | fencing | 3110200 | construction of buildings | kajiado east | Kenyawa poka |  | education | education | education | 2015-07-01 | 2015-08-01 | 2016-06-01 | 2016-06-01 | 4999814.6 | 4999814.6 | 4999814.6 | CGK |  | 4999814.6 | 0 |  | 100% | 4999814.6 |  |  | complete
| olkoilanga ecde | construction and equiping | to increase enrolment | construction and equiping | 3110200 | construction of buildings | kajiado east | Kenyawa poka |  | education | education | education | 2015-07-01 | 2015-08-01 | 2016-06-01 | 2016-06-01 | 6002627.55 | 6002627.55 | 6002627.55 | CGK |  | 6002627.55 | 0 |  | 100% | 6002627.55 |  |  | complete
| merrueshi pri. | fencing and construction of a dormintory | to increase enrolment | fencing and construction of a dormintory | 3110200 | construction of buildings | kajiado east | Kenyawa poka |  | education | education | education | 2015-07-01 | 2015-08-01 | 2016-06-01 | 2016-06-01 | 5052496 | 5052496 | 5052496 | CGK |  | 5052496 | 0 |  | 100% | 5052496 |  |  | complete
| enaika ecde | construction and equiping | to increase enrolment | construction and equiping | 3110200 | construction of buildings | kajiado east | Kenyawa poka |  | education | education | education | 2015-07-01 | 2015-08-01 | 2016-06-01 | 2016-06-01 | 4997240.3 | 4997240.3 | 4997240.3 | CGK |  | 4997240.3 | 0 |  | 100% | 4997240.3 |  |  | complete
| oloonkai ecde | construction and equiping | to increase enrolment | construction and equiping | 3110200 | construction of buildings | kajiado east | Kenyawa poka |  | education | education | education | 2015-07-01 | 2015-08-01 | 2016-06-01 | 2016-06-01 | 6000000 | 6000000 | 6000000 | CGK |  | 6000000 | 0 |  | 100% | 6000000 |  |  | complete
| paranae ecde | construction and equiping | to increase enrolment | construction and equiping | 3110200 | construction of buildings | kajiado east | Sholinke oloosirkon |  | education | education | education | 2015-07-01 | 2015-08-01 | 2016-06-01 | 2016-06-01 | 5998583 | 5998583 | 5998583 | CGK |  | 5998583 | 0 |  | 100% | 5998583 |  |  | complete
| kitengela pri. | construction of ecde | to increase enrolment | construction of ecde | 3110200 | construction of buildings | kajiado east | Sholinke oloosirkon |  | education | education | education | 2015-07-01 | 2015-08-01 | 2016-06-01 | 2016-06-01 | 2995490 | 2995490 | 2995490 | CGK |  | 2995490 | 0 |  | 100% | 2995490 |  |  | complete
| emakoko ecde | construction and equiping | to increase enrolment | construction and equiping | 3110200 | construction of buildings | kajiado east | Sholinke oloosirkon |  | education | education | education | 2015-07-01 | 2015-08-01 | 2016-06-01 | 2016-06-01 | 5933593.15 | 5933593.15 | 5933593.15 | CGK |  | 5933593.15 | 0 |  | 100% | 5933593.15 |  |  | complete
| olmeleleki pri. | construction and equiping of ecde | to increase enrolment | construction and equiping of ecde | 3110200 | construction of buildings | kajiado east | Imaroro |  | education | education | education | 2015-07-01 | 2015-08-01 | 2016-06-01 | 2016-06-01 | 3001016 | 3001016 | 3001016 | CGK |  | 3001016 | 0 |  | 100% | 3001016 |  |  | complete
| lesoit pri. | construction of a modern ecde centre | to increase enrolment | construction of a modern ecde centre | 3110200 | construction of buildings | kajiado east | Imaroro |  | education | education | education | 2015-07-01 | 2015-08-01 | 2016-06-01 | 2016-06-01 | 2991720 | 2991720 | 2991720 | CGK |  | 2991720 | 0 |  | 100% | 2991720 |  |  | complete
| enkiushin pri. | construction of an ecde | to increase enrolment | construction of an ecde | 3110200 | construction of buildings | kajiado east | Imaroro |  | education | education | education | 2015-07-01 | 2015-08-01 | 2016-06-01 | 2016-06-01 | 2995000 | 2995000 | 2995000 | CGK |  | 2995000 | 0 |  | 100% | 2995000 |  |  | complete
| parsinti pri. | construction of an ecde centre | to increase enrolment | construction of an ecde centre | 3110200 | construction of buildings | kajiado east | Imaroro |  | education | education | education | 2015-07-01 | 2015-08-01 | 2016-06-01 | 2016-06-01 | 2995375.2 | 2995375.2 | 2995375.2 | CGK |  | 2995375.2 | 0 |  | 100% | 2995375.2 |  |  | complete
| ilmunkush pri. | construction of ecde | to increase enrolment | construction of ecde | 3110200 | construction of buildings | kajiado east | Imaroro |  | education | education | education | 2015-07-01 | 2015-08-01 | 2016-06-01 | 2016-06-01 | 2997498 | 2997498 | 2997498 | CGK |  | 2997498 | 0 |  | 100% | 2997498 |  |  | complete
| oldupai pri. | construction of an ecde | to increase enrolment | construction of an ecde | 3110200 | construction of buildings | kajiado east | Imaroro |  | education | education | education | 2015-07-01 | 2015-08-01 | 2016-06-01 | 2016-06-01 | 4200000 | 4200000 | 4200000 | CGK |  | 4200000 | 0 |  | 100% | 4200000 |  |  | complete
| nkumama memorial pri. | construction construction of an ecde | to increase enrolment | construction construction of an ecde | 3110200 | construction of buildings | kajiado east | Imaroro |  | education | education | education | 2015-07-01 | 2015-08-01 | 2016-06-01 | 2016-06-01 | 3028423 | 3028423 | 3028423 | CGK |  | 3028423 | 0 |  | 100% | 3028423 |  |  | complete
| inkorienito | construction of ecde classes | to increase enrolment | construction of ecde classes | 3110200 | construction of buildings | kajiado west | Ewuaso oonkidongi |  | education | education | education | 2015-07-01 | 2015-08-01 | 2016-06-01 | 2016-06-01 | 4193561 | 4193561 | 4193561 | CGK |  | 4193561 | 0 |  | 100% | 4193561 |  |  | complete
| kandirisi | construction of ecde classes | to increase enrolment | construction of ecde classes | 3110200 | construction of buildings | kajiado west | Ewuaso oonkidongi |  | education | education | education | 2015-07-01 | 2015-08-01 | 2016-06-01 | 2016-06-01 | 1298419 | 1298419 | 1298419 | CGK |  | 1298419 | 0 |  | 100% | 1298419 |  |  | complete
| olngarua pri. | construction of ecde classes | to increase enrolment | construction of ecde classes | 3110200 | construction of buildings | kajiado west | Ewuaso oonkidongi |  | education | education | education | 2015-07-01 | 2015-08-01 | 2016-06-01 | 2016-06-01 | 2494428 | 2494428 | 2494428 | CGK |  | 2494428 | 0 |  | 100% | 2494428 |  |  | complete
| olkirdingai | construction of an ecde | to increase enrolment | construction of an ecde | 3110200 | construction of buildings | kajiado west | Ewuaso oonkidongi |  | education | education | education | 2015-07-01 | 2015-08-01 | 2016-06-01 | 2016-06-01 | 2999180 | 2999180 | 2999180 | CGK |  | 2999180 | 0 |  | 100% | 2999180 |  |  | complete
| namunyak pri. | construction of an ecde | to increase enrolment | construction of an ecde | 3110200 | construction of buildings | kajiado west | Ewuaso oonkidongi |  | education | education | education | 2015-07-01 | 2015-08-01 | 2016-06-01 | 2016-06-01 | 3000000 | 3000000 | 3000000 | CGK |  | 3000000 | 0 |  | 100% | 3000000 |  |  | complete
| kisaju pri. | construction of 2no.ecde classes | to increase enrolment | construction of 2no.ecde classes | 3110200 | construction of buildings | kajiado west | Keekonyokie |  | education | education | education | 2015-07-01 | 2015-08-01 | 2016-06-01 | 2016-06-01 | 4997512 | 4997512 | 4997512 | CGK |  | 4997512 | 0 |  | 100% | 4997512 |  |  | complete
| naromoru pri | construction of 2 no. ecde classes | to increase enrolment | construction of 2 no. ecde classes | 3110200 | construction of buildings | kajiado west | Keekonyokie |  | education | education | education | 2015-07-01 | 2015-08-01 | 2016-06-01 | 2016-06-01 | 3000000 | 3000000 | 3000000 | CGK |  | 3000000 | 0 |  | 100% | 3000000 |  |  | complete
| namelok girls sec. | connstruction of dormitory | to increase enrolment | connstruction of dormitory | 3110200 | construction of buildings | kajiado west | Keekonyokie |  | education | education | education | 2015-07-01 | 2015-08-01 | 2016-06-01 | 2016-06-01 | 2996200 | 2996200 | 2996200 | CGK |  | 2996200 | 0 |  | 100% | 2996200 |  |  | complete
| endoinyo enkoito pri | construction of an ecde | to increase enrolment | construction of an ecde | 3110200 | construction of buildings | kajiado west | Mosiro |  | education | education | education | 2015-07-01 | 2015-08-01 | 2016-06-01 | 2016-06-01 | 1700000 | 1700000 | 1700000 | CGK |  | 1700000 | 0 |  | 100% | 1700000 |  |  | complete
| lempitira pri | construction of ecde classes | to increase enrolment | construction of ecde classes | 3110200 | construction of buildings | kajiado west | Mosiro |  | education | education | education | 2015-07-01 | 2015-08-01 | 2016-06-01 | 2016-06-01 | 2990004 | 2990004 | 2990004 | CGK |  | 2990004 | 0 |  | 100% | 2990004 |  |  | complete
| kayior pri | construction of ecde classes | to increase enrolment | construction of ecde classes | 3110200 | construction of buildings | kajiado west | Magadi |  | education | education | education | 2015-07-01 | 2015-08-01 | 2016-06-01 | 2016-06-01 | 2000000 | 2000000 | 2000000 | CGK |  | 2000000 | 0 |  | 100% | 2000000 |  |  | complete
| shompole pri. | fencing | to increase enrolment | fencing | 3110200 | construction of buildings | kajiado west | Magadi |  | education | education | education | 2015-07-01 | 2015-08-01 | 2016-06-01 | 2016-06-01 | 2569980 | 2569980 | 2569980 | CGK |  | 2569980 | 0 |  | 100% | 2569980 |  |  | complete
| magadi sec. | equiping of a dormitory | to increase enrolment | equiping of a dormitory | 3110200 | construction of buildings | kajiado west | Magadi |  | education | education | education | 2015-07-01 | 2015-08-01 | 2016-06-01 | 2016-06-01 | 2000000 | 2000000 | 2000000 | CGK |  | 2000000 | 0 |  | 100% | 2000000 |  |  | complete
| ilparakuo pri. | rehabilitation and fencing | to increase enrolment | rehabilitation and fencing | 3110200 | construction of buildings | kajiado west | Magadi |  | education | education | education | 2015-07-01 | 2015-08-01 | 2016-06-01 | 2016-06-01 | 1469281.6 | 1469281.6 | 1469281.6 | CGK |  | 1469281.6 | 0 |  | 100% | 1469281.6 |  |  | complete
| ilparakuo pri. | fencing | to increase enrolment | fencing | 3110200 | construction of buildings | kajiado west | Magadi |  | education | education | education | 2015-07-01 | 2015-08-01 | 2016-06-01 | 2016-06-01 | 2499985.6 | 2499985.6 | 2499985.6 | CGK |  | 2499985.6 | 0 |  | 100% | 2499985.6 |  |  | complete
| magadi primary | construction of ECDE classroom | to increase enrolment | construction of ECDE classroom | 3110200 | construction of buildings | kajiado west | Magadi |  | education | education | education | 2015-07-01 | 2015-08-01 | 2016-06-01 | 2016-06-01 | 1000000 | 1000000 | 1000000 | CGK |  | 1000000 | 0 |  | 100% | 1000000 |  |  | complete
| Oldonyo onyokie primary sch. | construction of an abolition block and fencing | to increase enrolment | construction of an abolition block and fencing | 3110200 | construction of buildings | kajiado west | Magadi |  | education | education | education | 2015-07-01 | 2015-08-01 | 2016-06-01 | 2016-06-01 | 997600 | 997600 | 997600 | CGK |  | 997600 | 0 |  | 100% | 997600 |  |  | complete
| oldorko primary | fencing | to increase enrolment | fencing | 3110200 | construction of buildings | kajiado west | Magadi |  | education | education | education | 2015-07-01 | 2015-08-01 | 2016-06-01 | 2016-06-01 | 2999990 | 2999990 | 2999990 | CGK |  | 2999990 | 0 |  | 100% | 2999990 |  |  | complete
| lenkobei primary | fencing | to increase enrolment | fencing | 3110200 | construction of buildings | kajiado west | Magadi |  | education | education | education | 2015-07-01 | 2015-08-01 | 2016-06-01 | 2016-06-01 | 2999910 | 2999910 | 2999910 | CGK |  | 2999910 | 0 |  | 100% | 2999910 |  |  | complete
| Kilonito pri. | Construction of ECDE classes | to increase enrolment | Construction of ECDE classes | 3110200 | construction of buildings | kajiado west | Iloodokilani |  | education | education | education | 2015-07-01 | 2015-08-01 | 2016-06-01 | 2016-06-01 | 2988600 | 2988600 | 2988600 | CGK |  | 2988600 | 0 |  | 100% | 2988600 |  |  | complete
| paranae pri. | Construction of ECDE classes | to increase enrolment | Construction of ECDE classes | 3110200 | construction of buildings | kajiado west | Iloodokilani |  | education | education | education | 2015-07-01 | 2015-08-01 | 2016-06-01 | 2016-06-01 | 3000000 | 3000000 | 3000000 | CGK |  | 3000000 | 0 |  | 100% | 3000000 |  |  | complete
| Intepen primary | Construction of ECDE | to increase enrolment | Construction of ECDE | 3110200 | construction of buildings | kajiado west | Iloodokilani |  | education | education | education | 2015-07-01 | 2015-08-01 | 2016-06-01 | 2016-06-01 | 4920511.2 | 4920511.2 | 4920511.2 | CGK |  | 4920511.2 | 0 |  | 100% | 4920511.2 |  |  | complete
| Oltotoi primary school | Construction of ECDE classes | to increase enrolment | Construction of ECDE classes | 3110200 | construction of buildings | kajiado west | Iloodokilani |  | education | education | education | 2015-07-01 | 2015-08-01 | 2016-06-01 | 2016-06-01 | 2997377.2 | 2997377.2 | 2997377.2 | CGK |  | 2997377.2 | 0 |  | 100% | 2997377.2 |  |  | complete
| Elangata Uas primary | Construction of ECDE | to increase enrolment | Construction of ECDE | 3110200 | construction of buildings | kajiado west | Iloodokilani |  | education | education | education | 2015-07-01 | 2015-08-01 | 2016-06-01 | 2016-06-01 | 1995176.8 | 1995176.8 | 1995176.8 | CGK |  | 1995176.8 | 0 |  | 100% | 1995176.8 |  |  | complete
| Iyarat primary | Construction of ECDE | to increase enrolment | Construction of ECDE | 3110200 | construction of buildings | kajiado west | Iloodokilani |  | education | education | education | 2015-07-01 | 2015-08-01 | 2016-06-01 | 2016-06-01 | 4919931 | 4919931 | 4919931 | CGK |  | 4919931 | 0 |  | 100% | 4919931 |  |  | complete
| Nengosua primary | Construction of ECDE | to increase enrolment | Construction of ECDE | 3110200 | construction of buildings | kajiado west | Iloodokilani |  | education | education | education | 2015-07-01 | 2015-08-01 | 2016-06-01 | 2016-06-01 | 5854841.4 | 5854841.4 | 5854841.4 | CGK |  | 5854841.4 | 0 |  | 100% | 5854841.4 |  |  | complete
| Maparasha sec. | fencing | to increase enrolment | fencing | 3110200 | construction of buildings | kajiado central | Matapato north |  | education | education | education | 2015-07-01 | 2015-08-01 | 2016-06-01 | 2016-06-01 | 5998970.45 | 5998970.45 | 5998970.45 | CGK |  | 5998970.45 | 0 |  | 100% | 5998970.45 |  |  | complete
| olmotiany | Construction and equiping of mdern ECDE | to increase enrolment | Construction and equiping of mdern ECDE | 3110200 | construction of buildings | kajiado central | Matapato north |  | education | education | education | 2015-07-01 | 2015-08-01 | 2016-06-01 | 2016-06-01 | 2982394.8 | 2982394.8 | 2982394.8 | CGK |  | 2982394.8 | 0 |  | 100% | 2982394.8 |  |  | complete
| Mopia pri | Construction of modern ECDE | to increase enrolment | Construction of modern ECDE | 3110200 | construction of buildings | kajiado central | Matapato north |  | education | education | education | 2015-07-01 | 2015-08-01 | 2016-06-01 | 2016-06-01 | 2969832 | 2969832 | 2969832 | CGK |  | 2969832 | 0 |  | 100% | 2969832 |  |  | complete
| Moipei pri. | Consruction of an admin block | to increase enrolment | Consruction of an admin block | 3110200 | construction of buildings | kajiado central | Ildamat |  | education | education | education | 2015-07-01 | 2015-08-01 | 2016-06-01 | 2016-06-01 | 2916240 | 2916240 | 2916240 | CGK |  | 2916240 | 0 |  | 100% | 2916240 |  |  | complete
| Elerai pri. | Consruction of an modern ECDE centre | to increase enrolment | Consruction of an modern ECDE centre | 3110200 | construction of buildings | kajiado central | Ildamat |  | education | education | education | 2015-07-01 | 2015-08-01 | 2016-06-01 | 2016-06-01 | 1998680 | 1998680 | 1998680 | CGK |  | 1998680 | 0 |  | 100% | 1998680 |  |  | complete
| Moipei primary | fencing | to increase enrolment | fencing | 3110200 | construction of buildings | kajiado central | Ildamat |  | education | education | education | 2015-07-01 | 2015-08-01 | 2016-06-01 | 2016-06-01 | 2999876 | 2999876 | 2999876 | CGK |  | 2999876 | 0 |  | 100% | 2999876 |  |  | complete
| Iseuri primary school | fencing | to increase enrolment | fencing | 3110200 | construction of buildings | kajiado central | Dalalekutuk |  | education | education | education | 2015-07-01 | 2015-08-01 | 2016-06-01 | 2016-06-01 | 2997370 | 2997370 | 2997370 | CGK |  | 2997370 | 0 |  | 100% | 2997370 |  |  | complete
| Meguarra | Construction of ECDE | to increase enrolment | Construction of ECDE | 3110200 | construction of buildings | kajiado central | Dalalekutuk |  | education | education | education | 2015-07-01 | 2015-08-01 | 2016-06-01 | 2016-06-01 | 3900000 | 3900000 | 3900000 | CGK |  | 3900000 | 0 |  | 100% | 3900000 |  |  | complete
| Imanyat | Constructinon Equiping of ECDE | to increase enrolment | Constructinon Equiping of ECDE | 3110200 | construction of buildings | kajiado central | Dalalekutuk |  | education | education | education | 2015-07-01 | 2015-08-01 | 2016-06-01 | 2016-06-01 | 5970764.8 | 5970764.8 | 5970764.8 | CGK |  | 5970764.8 | 0 |  | 100% | 5970764.8 |  |  | complete
| purko ECDE centres | equiping | to increase enrolment | equiping | 3110200 | construction of buildings | kajiado central | purko |  | education | education | education | 2015-07-01 | 2015-08-01 | 2016-06-01 | 2016-06-01 | 1488836.8 | 1488836.8 | 1488836.8 | CGK |  | 1488836.8 | 0 |  | 100% | 1488836.8 |  |  | complete
| Empukani ECDE | Construction and equping | to increase enrolment | Construction and equping | 3110200 | construction of buildings | kajiado central | Matapato south |  | education | education | education | 2015-07-01 | 2015-08-01 | 2016-06-01 | 2016-06-01 | 1488836.8 | 1488836.8 | 1488836.8 | CGK |  | 1488836.8 | 0 |  | 100% | 1488836.8 |  |  | complete
| iltripen primary | construction of 1no classrooom | to increase enrolment | construction of 1no classrooom | 3110200 | construction of buildings | kajiado central | Matapato south |  | education | education | education | 2015-07-01 | 2015-08-01 | 2016-06-01 | 2016-06-01 | 1493152 | 1493152 | 1493152 | CGK |  | 1493152 | 0 |  | 100% | 1493152 |  |  | complete
| Iltripen ECDE | equiping | to increase enrolment | equiping | 3110200 | construction of buildings | kajiado central | Matapato south |  | education | education | education | 2015-07-01 | 2015-08-01 | 2016-06-01 | 2016-06-01 | 3000000 | 3000000 | 3000000 | CGK |  | 3000000 | 0 |  | 100% | 3000000 |  |  | complete
| Olekimaki ECDE | Construction and equiping | to increase enrolment | Construction and equiping | 3110200 | construction of buildings | kajiado central | Matapato south |  | education | education | education | 2015-07-01 | 2015-08-01 | 2016-06-01 | 2016-06-01 | 2000000 | 2000000 | 2000000 | CGK |  | 2000000 | 0 |  | 100% | 2000000 |  |  | complete
| rongai pri. | construction of an ecde centre | to increase enrolment | construction of an ecde centre | 3110200 | construction of buildings | kajiado south | Kimana |  | education | education | education | 2015-07-01 | 2015-08-01 | 2016-06-01 | 2016-06-01 | 1000000 | 1000000 | 1000000 | CGK |  | 1000000 | 0 |  | 100% | 1000000 |  |  | complete
| Dam area ECDE centre | construction | to increase enrolment | construction | 3110200 | construction of buildings | kajiado north | Olkeri |  | education | education | education | 2015-07-01 | 2015-08-01 | 2016-06-01 | 2016-06-01 | 3000000 | 3000000 | 3000000 | CGK |  | 3000000 | 0 |  | 100% | 3000000 |  |  | complete
| Oloolua Polytechnic | construction | to increase enrolment | construction | 3110200 | construction of buildings | kajiado north | Oloolua |  | education | education | education | 2015-07-01 | 2015-08-01 | 2016-06-01 | 2016-06-01 | 1000000 | 1000000 | 1000000 | CGK |  | 1000000 | 0 |  | 100% | 1000000 |  |  | complete
| Sinkiraine | Constraction of ECDE classes | to increase enrolment | Constraction of ECDE classes | 3110200 | construction of buildings | kajiado west | Iloodokilani |  | education | education | education | 2015-07-01 | 2015-08-01 | 2016-06-01 | 2016-06-01 | 2000000 | 2000000 | 2000000 | CGK |  | 2000000 | 0 |  | 100% | 2000000 |  |  | complete
| indarkalali ecde | construction of toilets | to increase enrolment | construction of toilets | 3110200 | construction of buildings | kajiado west | Magadi |  | education | education | education | 2015-07-01 | 2015-08-01 | 2016-06-01 | 2016-06-01 | 750000 | 750000 | 750000 | CGK |  | 750000 | 0 |  | 100% | 750000 |  |  | complete
| endoinyo oo lasho pri. | construction of 1no ecde and toilet | to increase enrolment | construction of 1no ecde and toilet | 3110200 | construction of buildings | kajiado west | Magadi |  | education | education | education | 2015-07-01 | 2015-08-01 | 2016-06-01 | 2016-06-01 | 2000000 | 2000000 | 2000000 | CGK |  | 2000000 | 0 |  | 100% | 2000000 |  |  | complete
| Embulbul ECDE centre | equiping | to increase enrolment | equiping | 3110200 | construction of buildings | kajiado north | Oloolua |  | education | education | education | 2015-07-01 | 2015-08-01 | 2016-06-01 | 2016-06-01 | 1500000 | 1500000 | 1500000 | CGK |  | 1500000 | 0 |  | 100% | 1500000 |  |  | complete
| emamparisuai | construction of a modern ecde centre at | to increase enrolment | construction of a modern ecde centre at | 3110200 | construction of buildings | kajiado east | Kaputiei north |  | education
| Inkinye ECDE | Construction and equping | to increase enrolment | Construction and equping | 3110200 | construction of buildings | kajiado central | Matapato south |  | education | education | education | 2016-07-01 | 2016-08-01 | 2017-06-01 | 2017-06-01 | 2992800 | 2992800 | 2992800 | CGK |  | 2992800 | 0 |  |  | 2992800 |  |  | complete
[11 empty] | education | education | 2016-07-01 | 2016-08-01 | 2017-06-01 | 2017-06-01 | 999398 | 999398 | 999398 | CGK |  | 999398 | 0 |  |  | 999398 |  |  | complete
| MAGADI PRIMARY | Construction of 2 NO. CLASSROOM | to increase enrolment | Construction of 2 NO. CLASSROOM | 3110200 | construction of buildings | kajiado west | magadi |  | education | education | education | 2016-07-01 | 2016-08-01 | 2017-06-01 | 2017-06-01 | 2988841 | 2988841 | 2988841 | CGK |  | 2988841 | 0 |  |  | 2988841 |  |  | complete
| RENOVATION OF ISEURI PRIMARY SCHOOL | Renovation | to increase enrolment | Renovation | 3110200 | construction of buildings | kajiado central | dalalekutuk |  | education | education | education | 2016-07-01 | 2016-08-01 | 2017-06-01 | 2017-06-01 | 13958825 | 13958825 | 13958825 | CGK |  | 13958825 | 0 |  |  | 13958825 |  |  | complete
| 2 NO. CLASSROOM AT OLOOLARROI PRIMARY SCHOOL | Construction | to increase enrolment | Construction | 3110200 | construction of buildings | kajiado central | matapato south |  | education | education | education | 2016-07-01 | 2016-08-01 | 2017-06-01 | 2017-06-01 | 999920 | 999920 | 999920 | CGK |  | 999920 | 0 |  |  | 999920 |  |  | complete
| SAIKERI YOUTH POLYTECHNIC | Construction | to increase enrolment | Construction | 3110200 | construction of buildings | kajiado west | ewuaso cc nkidongi |  | education | education | education | 2016-07-01 | 2016-08-01 | 2017-06-01 | 2017-06-01 | 2980900 | 2980900 | 2980900 | CGK |  | 2980900 | 0 |  |  | 2980900 |  |  | complete
| 2.NO 2 DOOR PIT LATRINE WITH URINAL AT ELUNAT PRIMARY SCHOOL | Construction | to increase enrolment | Construction | 3110200 | construction of buildings | kajiado west | magadi |  | education | education | education | 2016-07-01 | 2016-08-01 | 2017-06-01 | 2017-06-01 | 1495810 | 1495810 | 1495810 | CGK |  | 1495810 | 0 |  |  | 1495810 |  |  | complete
| 2.NO CLASSROOM AT OLMANIE PRIMARY SCHOOL | Construction | to increase enrolment | Construction | 3110200 | construction of buildings | kajiado east | I maroro |  | education | education | education | 2016-07-01 | 2016-08-01 | 2017-06-01 | 2017-06-01 | 1487420.64 | 1487420.64 | 1487420.64 | CGK |  | 1487420.64 | 0 |  |  | 1487420.64 |  |  | complete
| 1. NO CLASSROOM AT ILLAIMIRO PRIMARY SCHOOL | Construction | to increase enrolment | Construction | 3110200 | construction of buildings | kajiado east | kenyawa poka |  | education | education | education | 2016-07-01 | 2016-08-01 | 2017-06-01 | 2017-06-01 | 4980720 | 4980720 | 4980720 | CGK |  | 4980720 | 0 |  |  | 4980720 |  |  | complete
| 1 NO. ECDE CLASSROOM AT ENTOMONO PRIMARY SCHOOL | Construction | to increase enrolment | Construction | 3110200 | construction of buildings | kajiado west | magadi |  | education | education | education | 2016-07-01 | 2016-08-01 | 2017-06-01 | 2017-06-01 | 1490195 | 1490195 | 1490195 | CGK |  | 1490195 | 0 |  |  | 1490195 |  |  | complete
| ECDE AT ENKUTOTO PRIMARY SCHOOL | Construction | to increase enrolment | Construction | 3110200 | construction of buildings | kajiado central | matapato north |  | education | education | education | 2016-07-01 | 2016-08-01 | 2017-06-01 | 2017-06-01 | 2980900 | 2980900 | 2980900 | CGK |  | 2980900 | 0 |  |  | 2980900 |  |  | complete
| 1.NO CLASSROOM NALEPO PRIMARY SCHOOL | Construction | to increase enrolment | Construction | 3110200 | construction of buildings | kajiado north | olkeri |  | education | education | education | 2016-07-01 | 2016-08-01 | 2017-06-01 | 2017-06-01 | 2994440 | 2994440 | 2994440 | CGK |  | 2994440 | 0 |  |  | 2994440 |  |  | complete
| 2.NO ECDE CLASSROOM AT OLMANIE PRIMARY SCHOOL | Construction | to increase enrolment | Construction | 3110200 | construction of buildings | kajiado central | matapato south |  | education | education | education | 2016-07-01 | 2016-08-01 | 2017-06-01 | 2017-06-01 | 4980850 | 4980850 | 4980850 | CGK |  | 4980850 | 0 |  |  | 4980850 |  |  | complete
| 2 NO. CLASSROOM AT ILPARAKUO PRIMARY SCHOOL | Construction | to increase enrolment | Construction | 3110200 | construction of buildings | kajiado west | magadi |  | education | education | education | 2016-07-01 | 2016-08-01 | 2017-06-01 | 2017-06-01 | 989941 | 989941 | 989941 | CGK |  | 989941 | 0 |  |  | 989941 |  |  | complete
| E CDE CENTRE AT ERANKAU PRIMARY SCHOOL | Construction | to increase enrolment | Construction | 3110200 | construction of buildings | kajiado east | imaroro |  | education | education | education | 2016-07-01 | 2016-08-01 | 2017-06-01 | 2017-06-01 | 3195953 | 3195953 | 3195953 | CGK |  | 3195953 | 0 |  |  | 3195953 |  |  | complete
| TOILET AT MATALI PRIMARY SCHOOL | Construction | to increase enrolment | Construction | 3110200 | construction of buildings | kajiado east | sholinke |  | education | education | education | 2016-07-01 | 2016-08-01 | 2017-06-01 | 2017-06-01 | 1413019 | 1413019 | 1413019 | CGK |  | 1413019 | 0 |  |  | 1413019 |  |  | complete
| PERIMETRE WALL AT KIRARAPON | fencing | to increase enrolment | fencing | 3110200 | construction of buildings | kajiado north | olkeri |  | education | education | education | 2016-07-01 | 2016-08-01 | 2017-06-01 | 2017-06-01 | 2981920 | 2981920 | 2981920 | CGK |  | 2981920 | 0 |  |  | 2981920 |  |  | complete
| 1 NO. CLASSROOM AT NKUYAN PRIMARY SCHOOL | Construction | to increase enrolment | Construction | 3110200 | construction of buildings | kajiado central | matapato south |  | education | education | education | 2016-07-01 | 2016-08-01 | 2017-06-01 | 2017-06-01 | 2326496 | 2326496 | 2326496 | CGK |  | 2326496 | 0 |  |  | 2326496 |  |  | complete
| 2 NO. CLASSROOM AT SOMPET PRIMARY SCHOOL | Construction | to increase enrolment | Construction | 3110200 | construction of buildings | kajiado south | kuku |  | education | education | education | 2016-07-01 | 2016-08-01 | 2017-06-01 | 2017-06-01 | 2288600 | 2288600 | 2288600 | CGK |  | 2288600 | 0 |  |  | 2288600 |  |  | complete
| GATE HOUSE AND CHAINLINK FENCE AT OLNGUSUA PRIMARY SCHOOL | Construction | to increase enrolment | Construction | 3110200 | construction of buildings | kajiado central | matapato north |  | education | education | education | 2016-07-01 | 2016-08-01 | 2017-06-01 | 2017-06-01 | 1499990 | 1499990 | 1499990 | CGK |  | 1499990 | 0 |  |  | 1499990 |  |  | complete
| 2.NO CLASSROMS AT ORMANKEKI PRIMARY SCHOOL | Construction | to increase enrolment | Construction | 3110200 | construction of buildings | kajiado central | matapato north |  | education | education | education | 2016-07-01 | 2016-08-01 | 2017-06-01 | 2017-06-01 | 995106 | 995106 | 995106 | CGK |  | 995106 | 0 |  |  | 995106 |  |  | complete
| CHAINLINK FENCE NAIRRATAAT PRIMARY SCHOOL | fencing | to increase enrolment | fencing | 3110200 | construction of buildings | kajiado east | kenyawa poka |  | education | education | education | 2016-07-01 | 2016-08-01 | 2017-06-01 | 2017-06-01 | 2988020 | 2988020 | 2988020 | CGK |  | 2988020 | 0 |  |  | 2988020 |  |  | complete
| CHAINLINK FENCE AT OLENTOKO | fencing | to increase enrolment | fencing | 3110200 | construction of buildings | kajiado west | ewuaso cc nkidongi |  | education | education | education | 2016-07-01 | 2016-08-01 | 2017-06-01 | 2017-06-01 | 1497966 | 1497966 | 1497966 | CGK |  | 1497966 | 0 |  |  | 1497966 |  |  | complete
| 2.NO CLAASSRROM AT ENTASHATA | Construction | to increase enrolment | Construction | 3110200 | construction of buildings | kajiado west | iloodokilani |  | education | education | education | 2016-07-01 | 2016-08-01 | 2017-06-01 | 2017-06-01 | 2988290 | 2988290 | 2988290 | CGK |  | 2988290 | 0 |  |  | 2988290 |  |  | complete
| 1 NO ECDE CLASSROOM AT NASERIAN PRIMARY SCHOOL | Construction | to increase enrolment | Construction | 3110200 | construction of buildings | kajiado east | kenyawa poka |  | education | education | education | 2016-07-01 | 2016-08-01 | 2017-06-01 | 2017-06-01 | 2987584 | 2987584 | 2987584 | CGK |  | 2987584 | 0 |  |  | 2987584 |  |  | complete
| 2.NO CLAASSROOM AT EMBUYA PRIMARY SCHOOL | Construction | to increase enrolment | Construction | 3110200 | construction of buildings | kajiado east | kenyawa poka |  | education | education | education | 2016-07-01 | 2016-08-01 | 2017-06-01 | 2017-06-01 | 2995328.8 | 2995328.8 | 2995328.8 | CGK |  | 2995328.8 | 0 |  |  | 2995328.8 |  |  | complete
| OLEPOLOS PRIMARY SCHOOL 2 NO.CLASSROOMS | Construction | to increase enrolment | Construction | 3110200 | construction of buildings | kajiado south | kuku |  | education | education | education | 2016-07-01 | 2016-08-01 | 2017-06-01 | 2017-06-01 | 1499240 | 1499240 | 1499240 | CGK |  | 1499240 | 0 |  |  | 1499240 |  |  | complete
| 2.NO CLASSROOM AT ELERAI PRIMARY SCHOOL | Construction | to increase enrolment | Construction | 3110200 | construction of buildings | kajiado east | kenyawa poka |  | education | education | education | 2016-07-01 | 2016-08-01 | 2017-06-01 | 2017-06-01 | 1486662 | 1486662 | 1486662 | CGK |  | 1486662 | 0 |  |  | 1486662 |  |  | complete
| FENCE AT ENOORETETI PRIMARY SCHOOL | fencing | to increase enrolment | fencing | 3110200 | construction of buildings | kajiado east | kenyawa poka |  | education | education | education | 2016-07-01 | 2016-08-01 | 2017-06-01 | 2017-06-01 | 1495650 | 1495650 | 1495650 | CGK |  | 1495650 | 0 |  |  | 1495650 |  |  | complete
| 1 NO. CLASSROOM AT LESINKO PRIMARY SCHOOL | Construction | to increase enrolment | Construction | 3110200 | construction of buildings | kajiado central | dalalekutuk |  | education | education | education | 2016-07-01 | 2016-08-01 | 2017-06-01 | 2017-06-01 | 2989528 | 2989528 | 2989528 | CGK |  | 2989528 | 0 |  |  | 2989528 |  |  | complete
| 1 NO. CLASSROOM AT KURKET MAILUA PRIMARY SCHOOL | Construction | to increase enrolment | Construction | 3110200 | construction of buildings | kajiado central | matapato south |  | education | education | education | 2016-07-01 | 2016-08-01 | 2017-06-01 | 2017-06-01 | 2998356.4 | 2998356.4 | 2998356.4 | CGK |  | 2998356.4 | 0 |  |  | 2998356.4 |  |  | complete
| 2.NO CLASSROM AT EMUKUTAN PRIMARY SCHOOL | Construction | to increase enrolment | Construction | 3110200 | construction of buildings | kajiado west | loodokilani |  | education | education | education | 2016-07-01 | 2016-08-01 | 2017-06-01 | 2017-06-01 | 2929139 | 2929139 | 2929139 | CGK |  | 2929139 | 0 |  |  | 2929139 |  |  | complete
| 2.NO CLASSROOM ELAGATA OOMAYIANAT PRIMARY SCHOOL | Construction | to increase enrolment | Construction | 3110200 | construction of buildings | kajiado east | imaroro |  | education | education | education | 2016-07-01 | 2016-08-01 | 2017-06-01 | 2017-06-01 | 1490000 | 1490000 | 1490000 | CGK |  | 1490000 | 0 |  |  | 1490000 |  |  | complete
| 2.NO CLASSROOM AT NAILUMPE PRIMARY SCHOOL | Construction | to increase enrolment | Construction | 3110200 | construction of buildings | kajiado central | dalalekutuk |  | education | education | education | 2016-07-01 | 2016-08-01 | 2017-06-01 | 2017-06-01 | 2995154.8 | 2995154.8 | 2995154.8 | CGK |  | 2995154.8 | 0 |  |  | 2995154.8 |  |  | complete
| FENCE AT MATOI PRIMARY SCHOOL | fencing | to increase enrolment | fencing | 3110200 | construction of buildings | kajiado east | kenyawa poka |  | education | education | education | 2016-07-01 | 2016-08-01 | 2017-06-01 | 2017-06-01 | 1495068 | 1495068 | 1495068 | CGK |  | 1495068 | 0 |  |  | 1495068 |  |  | complete
| 2 NO CLASSROOM AT LENKISIM PRIMARY SCHOOL | Construction | to increase enrolment | Construction | 3110200 | construction of buildings | kajiado south | lenkisim |  | education | education | education | 2016-07-01 | 2016-08-01 | 2017-06-01 | 2017-06-01 | 1486590 | 1486590 | 1486590 | CGK |  | 1486590 | 0 |  |  | 1486590 |  |  | complete
| 1.NO CLASSROOM AT MATASIA PRIMARY SCHOOL | Construction | to increase enrolment | Construction | 3110200 | construction of buildings | kajiado north | olkeri |  | education | education | education | 2016-07-01 | 2016-08-01 | 2017-06-01 | 2017-06-01 | 2497322.24 | 2497322.24 | 2497322.24 | CGK |  | 2497322.24 | 0 |  |  | 2497322.24 |  |  | complete
| 1 NO. CLASSROOM AT OLDONYO PRIMARY SCHOOL | Construction | to increase enrolment | Construction | 3110200 | construction of buildings | kajiado central | dalalekutuk |  | education | education | education | 2016-07-01 | 2016-08-01 | 2017-06-01 | 2017-06-01 | 2385603.8 | 2385603.8 | 2385603.8 | CGK |  | 2385603.8 | 0 |  |  | 2385603.8 |  |  | complete
| 2.NO CLASSROOM AT OLTINKA PRIMARY SCHOOL | Construction | to increase enrolment | Construction | 3110200 | construction of buildings | kajiado east | kenyawa poka |  | education | education | education | 2016-07-01 | 2016-08-01 | 2017-06-01 | 2017-06-01 | 4975405 | 4975405 | 4975405 | CGK |  | 4975405 | 0 |  |  | 4975405 |  |  | complete
| KITCHEN AND STORES AT NGONG TOWNSHIP | Construction | to increase enrolment | Construction | 3110200 | construction of buildings | kajiado north | ngong |  | education | education | education | 2016-07-01 | 2016-08-01 | 2017-06-01 | 2017-06-01 | 2977569.2 | 2977569.2 | 2977569.2 | CGK |  | 2977569.2 | 0 |  |  | 2977569.2 |  |  | complete
| OLOIBOR AJIJIK PRIMARY SCHOOL ECDE CENTRE | Construction | to increase enrolment | Construction | 3110200 | construction of buildings | kajiado east | imaroro |  | education | education | education | 2016-07-01 | 2016-08-01 | 2017-06-01 | 2017-06-01 | 2995570.4 | 2995570.4 | 2995570.4 | CGK |  | 2995570.4 | 0 |  |  | 2995570.4 |  |  | complete
| ADMIN BLOCK AT ILOOSHON PRIMARY SCHOOL | Construction | to increase enrolment | Construction | 3110200 | construction of buildings | kajiado east | imaroro |  | education | education | education | 2016-07-01 | 2016-08-01 | 2017-06-01 | 2017-06-01 | 2989520 | 2989520 | 2989520 | CGK |  | 2989520 | 0 |  |  | 2989520 |  |  | complete
| 2.NO CLASSROOM AT OITI PRIMARY SCHOOL | Construction | to increase enrolment | Construction | 3110200 | construction of buildings | kajiado west | ewuaso cc nkidongi |  | education | education | education | 2016-07-01 | 2016-08-01 | 2017-06-01 | 2017-06-01 | 1496226 | 1496226 | 1496226 | CGK |  | 1496226 | 0 |  |  | 1496226 |  |  | complete
| 2.NO CLASSROOM AT ENARAU PRIMARY SCHOOL | Construction | to increase enrolment | Construction | 3110200 | construction of buildings | kajiado central | dalalekutuk |  | education | education | education | 2016-07-01 | 2016-08-01 | 2017-06-01 | 2017-06-01 | 1490613 | 1490613 | 1490613 | CGK |  | 1490613 | 0 |  |  | 1490613 |  |  | complete
| 1 NO. ECDE CLASSRROM AT KIBINI PRIMARY SCHOOL | Construction | to increase enrolment | Construction | 3110200 | construction of buildings | kajiado east | kenyawa poka |  | education | education | education | 2016-07-01 | 2016-08-01 | 2017-06-01 | 2017-06-01 | 2979215 | 2979215 | 2979215 | CGK |  | 2979215 | 0 |  |  | 2979215 |  |  | complete
| 1.NO. CLASSROOM AT ILOOORMARORO PRIMARY SCHOOL | Construction | to increase enrolment | Construction | 3110200 | construction of buildings | kajiado south | rombo |  | education | education | education | 2016-07-01 | 2016-08-01 | 2017-06-01 | 2017-06-01 | 1493546.6 | 1493546.6 | 1493546.6 | CGK |  | 1493546.6 | 0 |  |  | 1493546.6 |  |  | complete
| 2 NO. CLASSROOM AT ENCHORRO PRIMARY SCHOOL | Construction | to increase enrolment | Construction | 3110200 | construction of buildings | kajiado south | rombo |  | education | education | education | 2016-07-01 | 2016-08-01 | 2017-06-01 | 2017-06-01 | 1486438.28 | 1486438.28 | 1486438.28 | CGK |  | 1486438.28 | 0 |  |  | 1486438.28 |  |  | complete
| 1 NO. CLASSROOM AT EMBOLIEN PRIMARY SCHOOL | Construction | to increase enrolment | Construction | 3110200 | construction of buildings | kajiado south | kuku |  | education | education | education | 2016-07-01 | 2016-08-01 | 2017-06-01 | 2017-06-01 | 2988600 | 2988600 | 2988600 | CGK |  | 2988600 | 0 |  |  | 2988600 |  |  | complete
| 1.NO CLASSRROM AT OLOSHAIKI ECDE | Construction | to increase enrolment | Construction | 3110200 | construction of buildings | kajiado east | imaroro |  | education | education | education | 2016-07-01 | 2016-08-01 | 2017-06-01 | 2017-06-01 | 2981370.4 | 2981370.4 | 2981370.4 | CGK |  | 2981370.4 | 0 |  |  | 2981370.4 |  |  | complete
| 2.NO CLASSROOM AT MERISHO PRIMARY SCHOOOL | Construction | to increase enrolment | Construction | 3110200 | construction of buildings | kajiado north | olkeri |  | education | education | education | 2016-07-01 | 2016-08-01 | 2017-06-01 | 2017-06-01 | 2985950 | 2985950 | 2985950 | CGK |  | 2985950 | 0 |  |  | 2985950 |  |  | complete
| ADMIN BLOCK AT OLOKERI PRIMARY SCHOOL | Construction | to increase enrolment | Construction | 3110200 | construction of buildings | kajiado west | mosiro |  | education | education | education | 2016-07-01 | 2016-08-01 | 2017-06-01 | 2017-06-01 | 2902417.44 | 2902417.44 | 2902417.44 | CGK |  | 2902417.44 | 0 |  |  | 2902417.44 |  |  | complete
| 2 NO. CLASSROOM AT OLTEPESI PRIMARY SCHOOL | Construction | to increase enrolment | Construction | 3110200 | construction of buildings | kajiado west | iloodokilani |  | education | education | education | 2016-07-01 | 2016-08-01 | 2017-06-01 | 2017-06-01 | 2965841 | 2965841 | 2965841 | CGK |  | 2965841 | 0 |  |  | 2965841 |  |  | complete
| 2.NO CLASSROM AT LINTI PRIMARY SCHOOL | Construction | to increase enrolment | Construction | 3110200 | construction of buildings | kajiado central | matapato south |  | education | education | education | 2016-07-01 | 2016-08-01 | 2017-06-01 | 2017-06-01 | 1498686.36 | 1498686.36 | 1498686.36 | CGK |  | 1498686.36 | 0 |  |  | 1498686.36 |  |  | complete
| 2.NO CLASSROOM AT OLENARAU PRIMARY SCHOOL | Construction | to increase enrolment | Construction | 3110200 | construction of buildings | kajiado central | dalalekutuk |  | education | education | education | 2016-07-01 | 2016-08-01 | 2017-06-01 | 2017-06-01 | 2989111.2 | 2989111.2 | 2989111.2 | CGK |  | 2989111.2 | 0 |  |  | 2989111.2 |  |  | complete
| 1 NO CLASSROOM AT OLOMAYIANA PRIMARY SCHOOL | Construction | to increase enrolment | Construction | 3110200 | construction of buildings | kajiado east | imaroro |  | education | education | education | 2016-07-01 | 2016-08-01 | 2017-06-01 | 2017-06-01 | 4990842 | 4990842 | 4990842 | CGK |  | 4990842 | 0 |  |  | 4990842 |  |  | complete
| OLE NKATI PRIMARY SCHOOL | Construction | to increase enrolment | Construction | 3110200 | construction of buildings | kajiado south | imbrikani eselenkei |  | education | education | education | 2016-07-01 | 2016-08-01 | 2017-06-01 | 2017-06-01 | 4995671 | 4995671 | 4995671 | CGK |  | 4995671 | 0 |  |  | 4995671 |  |  | complete
| ENKONEREI ECDE CENTRE | Construction | to increase enrolment | Construction | 3110200 | construction of buildings | kajiado east | kenyawa poka |  | education | education | education | 2016-07-01 | 2016-08-01 | 2017-06-01 | 2017-06-01 | 999976 | 999976 | 999976 | CGK |  | 999976 | 0 |  |  | 999976 |  |  | complete
| NAKEEL STADIUM IN NKAIMURUNYA WARD | Construction | to increase enrolment | Construction | 3110200 | construction of buildings | kajiado north | nkaimurunya |  | education | education | education | 2016-07-01 | 2016-08-01 | 2017-06-01 | 2017-06-01 | 1497966 | 1497966 | 1497966 | CGK |  | 1497966 | 0 |  |  | 1497966 |  |  | complete
| ORKINA ECDE | Construction | to increase enrolment | Construction | 3110200 | construction of buildings | kajiado south | kimana |  | education | education | education | 2016-07-01 | 2016-08-01 | 2017-06-01 | 2017-06-01 | 1487966 | 1487966 | 1487966 | CGK |  | 1487966 | 0 |  |  | 1487966 |  |  | complete
| KISHARU PRIMARY SCHOOL | Construction | to increase enrolment | Construction | 3110200 | construction of buildings | kajiado west | ewuaso cc nkidongi |  | education | education | education | 2016-07-01 | 2016-08-01 | 2017-06-01 | 2017-06-01 | 2997860 | 2997860 | 2997860 | CGK |  | 2997860 | 0 |  |  | 2997860 |  |  | complete
| ILKILORITI PRIMARY SCHOOL | Construction | to increase enrolment | Construction | 3110200 | construction of buildings | kajiado west | ewuaso cc nkidongi |  | education | education | education | 2016-07-01 | 2016-08-01 | 2017-06-01 | 2017-06-01 | 2998040 | 2998040 | 2998040 | CGK |  | 2998040 | 0 |  |  | 2998040 |  |  | complete
| ESELENKEI PRIMARY SCHOOL | Construction | to increase enrolment | Construction | 3110200 | construction of buildings | kajiado east | kenyawa poka |  | education | education | education | 2016-07-01 | 2016-08-01 | 2017-06-01 | 2017-06-01 | 2987928 | 2987928 | 2987928 | CGK |  | 2987928 | 0 |  |  | 2987928 |  |  | complete
| ELANGATA PRIMARY SCHOOL | Construction | to increase enrolment | Construction | 3110200 | construction of buildings | kajiado east | imaroro |  | education | education | education | 2016-07-01 | 2016-08-01 | 2017-06-01 | 2017-06-01 | 1489097 | 1489097 | 1489097 | CGK |  | 1489097 | 0 |  |  | 1489097 |  |  | complete
| NOORETETI PRIMARY SCHOOL | Construction | to increase enrolment | Construction | 3110200 | construction of buildings | kajiado east | kenyawa poka |  | education | education | education | 2016-07-01 | 2016-08-01 | 2017-06-01 | 2017-06-01 | 2484570 | 2484570 | 2484570 | CGK |  | 2484570 | 0 |  |  | 2484570 |  |  | complete
| OLETUMUKE PRIMARY SCHOOL | Construction | to increase enrolment | Construction | 3110200 | construction of buildings | kajiado central | matapato south |  | education | education | education | 2016-07-01 | 2016-08-01 | 2017-06-01 | 2017-06-01 | 2989528 | 2989528 | 2989528 | CGK |  | 2989528 | 0 |  |  | 2989528 |  |  | complete
| OLGUMI SDA PRIMARY SCHOOL | Construction | to increase enrolment | Construction | 3110200 | construction of buildings | kajiado west | ewuaso cc nkidongi |  | education | education | education | 2016-07-01 | 2016-08-01 | 2017-06-01 | 2017-06-01 | 1493198 | 1493198 | 1493198 | CGK |  | 1493198 | 0 |  |  | 1493198 |  |  | complete
| KEPIRO PRIMARY SCHOOL | Construction | to increase enrolment | Construction | 3110200 | construction of buildings | kajiado east | kaputiei north |  | education | education | education | 2016-07-01 | 2016-08-01 | 2017-06-01 | 2017-06-01 | 2988600 | 2988600 | 2988600 | CGK |  | 2988600 | 0 |  |  | 2988600 |  |  | complete
| ILKIREMISHO PRIMARY SCHOOL | Construction | to increase enrolment | Construction | 3110200 | construction of buildings | kajiado central | dalalekutuk |  | education | education | education | 2016-07-01 | 2016-08-01 | 2017-06-01 | 2017-06-01 | 2985980 | 2985980 | 2985980 | CGK |  | 2985980 | 0 |  |  | 2985980 |  |  | complete
| NCHORROI PRIMARY SCHOOL | Construction | to increase enrolment | Construction | 3110200 | construction of buildings | kajiado east | imaroro |  | education | education | education | 2016-07-01 | 2016-08-01 | 2017-06-01 | 2017-06-01 | 1482966 | 1482966 | 1482966 | CGK |  | 1482966 | 0 |  |  | 1482966 |  |  | complete
| SAIRASHIE PRIMARY SCHOOL | Construction | to increase enrolment | Construction | 3110200 | construction of buildings | kajiado west | ewuaso cc nkidongi |  | education | education | education | 2016-07-01 | 2016-08-01 | 2017-06-01 | 2017-06-01 | 1490000 | 1490000 | 1490000 | CGK |  | 1490000 | 0 |  |  | 1490000 |  |  | complete
| NASARU PRIMARY SCHOOL | Construction | to increase enrolment | Construction | 3110200 | construction of buildings | kajiado west | ewuaso cc nkidongi |  | education | [18 empty] | complete
| OLDUNGORO PRIMARY SCHOOL | Construction | to increase enrolment | Construction | 3110200 | construction of buildings | kajiado west | ewuaso cc nkidongi |  | education | education | education | 2017-07-01 | 2017-08-01 | 2018-06-01 | 2018-06-01 | 4992135 | 4992135 | 4992135 | CGK |  | 4992135 | 0 |  |  | 4992135 |  |  | complete
[11 empty] | education | education | 2017-07-01 | 2017-08-01 | 2018-06-01 | 2018-06-01 | 2988290 | 2988290 | 2988290 | CGK |  | 2988290 | 0 |  |  | 2988290 |  |  | complete
| construction of ecde centre at iloshon/ ilkidemi primary | Construction | to increase enrolment | Construction | 3110200 | construction of buildings | kajiado east | imaroro |  | education | education | education | 2017-07-01 | 2017-08-01 | 2018-06-01 | 2018-06-01 | 2999818 | 2999818 | 2999818 | CGK |  | 2999818 | 0 |  |  | 2999818 |  |  | complete
| 2 no classroom at empuya primary | Construction | to increase enrolment | Construction | 3110200 | construction of buildings | kajiado east | imaroro |  | education | education | education | 2017-07-01 | 2017-08-01 | 2018-06-01 | 2018-06-01 | 2993438 | 2993438 | 2993438 | CGK |  | 2993438 | 0 |  |  | 2993438 |  |  | complete
| construction of 2 no classroom at imaroro primary | Construction | to increase enrolment | Construction | 3110200 | construction of buildings | kajiado east | imaroro |  | education | education | education | 2017-07-01 | 2017-08-01 | 2018-06-01 | 2018-06-01 | 8992285 | 8992285 | 8992285 | CGK |  | 8992285 | 0 |  |  | 8992285 |  |  | complete
| construction of 2 no classroom at oloongosuani primary | Construction | to increase enrolment | Construction | 3110200 | construction of buildings | kajiado east | imaroro |  | education | education | education | 2017-07-01 | 2017-08-01 | 2018-06-01 | 2018-06-01 | 2992711 | 2992711 | 2992711 | CGK |  | 2992711 | 0 |  |  | 2992711 |  |  | complete
| ecde centre at lenchani primary | Construction | to increase enrolment | Construction | 3110200 | construction of buildings | kajiado east | kaputiei north |  | education | education | education | 2017-07-01 | 2017-08-01 | 2018-06-01 | 2018-06-01 | 4990141 | 4990141 | 4990141 | CGK |  | 4990141 | 0 |  |  | 4990141 |  |  | complete
| 2 no classroom at ewangan e maa primary school | Construction | to increase enrolment | Construction | 3110200 | construction of buildings | kajiado east | kenyawa poka |  | education | education | education | 2017-07-01 | 2017-08-01 | 2018-06-01 | 2018-06-01 | 8487360 | 8487360 | 8487360 | CGK |  | 8487360 | 0 |  |  | 8487360 |  |  | complete
| construction of a science labaratory at masimba secondary | Construction | to increase enrolment | Construction | 3110200 | construction of buildings | kajiado east | kenyawa poka |  | education | education | education | 2017-07-01 | 2017-08-01 | 2018-06-01 | 2018-06-01 | 1499780 | 1499780 | 1499780 | CGK |  | 1499780 | 0 |  |  | 1499780 |  |  | complete
| construction of 7 no classroom and toilet block at ilkelunyeti primary | Construction | to increase enrolment | Construction | 3110200 | construction of buildings | kajiado east | kenyawa poka |  | education | education | education | 2017-07-01 | 2017-08-01 | 2018-06-01 | 2018-06-01 | 4999829 | 4999829 | 4999829 | CGK |  | 4999829 | 0 |  |  | 4999829 |  |  | complete
| 1 no classroom at illaimerror primary | Construction | to increase enrolment | Construction | 3110200 | construction of buildings | kajiado east | kenyawa poka |  | education | education | education | 2017-07-01 | 2017-08-01 | 2018-06-01 | 2018-06-01 | 1498511 | 1498511 | 1498511 | CGK |  | 1498511 | 0 |  |  | 1498511 |  |  | complete
| Ecde centre at sultan hamud township | Construction | to increase enrolment | Construction | 3110200 | construction of buildings | kajiado east | kenyawa poka |  | education | education | education | 2017-07-01 | 2017-08-01 | 2018-06-01 | 2018-06-01 | 2987422 | 2987422 | 2987422 | CGK |  | 2987422 | 0 |  |  | 2987422 |  |  | complete
| Construction of Fence at Noompala Pry School | construction | to increase enrolment | construction | 3110200 | construction of buildings | kajiado east | kenyawa poka |  | education | education | education | 2017-07-01 | 2017-08-01 | 2018-06-01 | 2018-06-01 | 1990571 | 1990571 | 1990571 | CGK |  | 1990571 | 0 |  |  | 1990571 |  |  | complete
| Construction of 2no.classrooms at Ereteti pri.sch | Construction | to increase enrolment | Construction | 3110200 | construction of buildings | kajiado east | Kitengela |  | education | education | education | 2017-07-01 | 2017-08-01 | 2018-06-01 | 2018-06-01 | 1999993 | 1999993 | 1999993 | CGK |  | 1999993 | 0 |  |  | 1999993 |  |  | complete
| Completion of Enkasiti ECDE centre | Construction | to increase enrolment | Construction | 3110200 | construction of buildings | kajiado east | Kitengela |  | education | education | education | 2017-07-01 | 2017-08-01 | 2018-06-01 | 2018-06-01 | 20000000 | 20000000 | 20000000 | CGK |  | 20000000 | 0 |  |  | 20000000 |  |  | complete
| chainlink fence at utumishi primary | fencing | to increase enrolment | fencing | 3110200 | construction of buildings | kajiado east | Kitengela |  | education | education | education | 2017-07-01 | 2017-08-01 | 2018-06-01 | 2018-06-01 | 9495644 | 9495644 | 9495644 | CGK |  | 9495644 | 0 |  |  | 9495644 |  |  | complete
| Construction of Kitengela/kyamgombe ecde | Construction | to increase enrolment | Construction | 3110200 | construction of buildings | kajiado east | Kitengela |  | education | education | education | 2017-07-01 | 2017-08-01 | 2018-06-01 | 2018-06-01 | 2963127 | 2963127 | 2963127 | CGK |  | 2963127 | 0 |  |  | 2963127 |  |  | complete
| Construction of an ECDE centre at Enkutoto pri.school | fencing | to increase enrolment | fencing | 3110200 | construction of buildings | kajiado east | sholinke |  | education | education | education | 2017-07-01 | 2017-08-01 | 2018-06-01 | 2018-06-01 | 2997904 | 2997904 | 2997904 | CGK |  | 2997904 | 0 |  |  | 2997904 |  |  | complete
| Construction of 2no.classroom at Nalepo Pri.school | fencing | to increase enrolment | fencing | 3110200 | construction of buildings | kajiado central | dalalekutuk |  | education | education | education | 2017-07-01 | 2017-08-01 | 2018-06-01 | 2018-06-01 | 2997324 | 2997324 | 2997324 | CGK |  | 2997324 | 0 |  |  | 2997324 |  |  | complete
| Construction of 2no.classroom at Indonyo Pri.school | Construction | to increase enrolment | Construction | 3110200 | construction of buildings | kajiado central | dalalekutuk |  | education | education | education | 2017-07-01 | 2017-08-01 | 2018-06-01 | 2018-06-01 | 996150 | 996150 | 996150 | CGK |  | 996150 | 0 |  |  | 996150 |  |  | complete
| Construction of 2no.classroom at Sajiloni Pri.school | Construction | to increase enrolment | Construction | 3110200 | construction of buildings | kajiado central | dalalekutuk |  | education | education | education | 2017-07-01 | 2017-08-01 | 2018-06-01 | 2018-06-01 | 998319 | 998319 | 998319 | CGK |  | 998319 | 0 |  |  | 998319 |  |  | complete
| CONSTRUCTION OF CHAINLINK FENCE AT IMANYAT PRIMARY SCHOOL | fencing | to increase enrolment | fencing | 3110200 | construction of buildings | kajiado central | dalalekutuk |  | education | education | education | 2017-07-01 | 2017-08-01 | 2018-06-01 | 2018-06-01 | 998150 | 998150 | 998150 | CGK |  | 998150 | 0 |  |  | 998150 |  |  | complete
| Construction of chainlink fence at Malilima Pri.school | fencing | to increase enrolment | fencing | 3110200 | construction of buildings | kajiado central | dalalekutuk |  | education | education | education | 2017-07-01 | 2017-08-01 | 2018-06-01 | 2018-06-01 | 36980846 | 36980846 | 36980846 | CGK |  | 36980846 | 0 |  |  | 36980846 |  |  | complete
| Renovation of Eseuri primary | renovation | to increase enrolment | renovation | 3110200 | construction of buildings | kajiado central | dalalekutuk |  | education | education | education | 2017-07-01 | 2017-08-01 | 2018-06-01 | 2018-06-01 | 1483141.2 | 1483141.2 | 1483141.2 | CGK |  | 1483141.2 | 0 |  |  | 1483141.2 |  |  | complete
| Construction of Dining hall at olkejuado high school | fencing | to increase enrolment | fencing | 3110200 | construction of buildings | kajiado central | dalalekutuk |  | education | education | education | 2017-07-01 | 2017-08-01 | 2018-06-01 | 2018-06-01 | 50000000 | 50000000 | 50000000 | CGK |  | 50000000 | 0 |  |  | 50000000 |  |  | complete
| 1 NO CLASSROOM AT OLEMURKAT ECDE | Construction | to increase enrolment | Construction | 3110200 | construction of buildings | kajiado central | dalalekutuk |  | education | education | education | 2017-07-01 | 2017-08-01 | 2018-06-01 | 2018-06-01 | 8997192 | 8997192 | 8997192 | CGK |  | 8997192 | 0 |  |  | 8997192 |  |  | complete
| Technical University of Kajiado | Construction | to increase enrolment | Construction | 3110200 | construction of buildings | kajiado central | dalalekutuk |  | education | education | education | 2017-07-01 | 2017-08-01 | 2018-06-01 | 2018-06-01 | 4478690 | 4478690 | 4478690 | CGK |  | 4478690 | 0 |  |  | 4478690 |  |  | complete
| Construction of 4no classroom and staffhouse at oloilalei Primary | Construction | to increase enrolment | Construction | 3110200 | construction of buildings | kajiado central | Ildamat |  | education | education | education | 2017-07-01 | 2017-08-01 | 2018-06-01 | 2018-06-01 | 990985 | 990985 | 990985 | CGK |  | 990985 | 0 |  |  | 990985 |  |  | complete
| Construction of a dining hall at Kajiado township sec. | Construction | to increase enrolment | Construction | 3110200 | construction of buildings | kajiado central | Ildamat |  | education | education | education | 2017-07-01 | 2017-08-01 | 2018-06-01 | 2018-06-01 | 1991720 | 1991720 | 1991720 | CGK |  | 1991720 | 0 |  |  | 1991720 |  |  | complete
| Supply of Office furniture to Moipei Primary school | supply | to increase enrolment | supply | 3110200 | construction of buildings | kajiado central | Ildamat |  | education | education | education | 2017-07-01 | 2017-08-01 | 2018-06-01 | 2018-06-01 | 1990438.2 | 1990438.2 | 1990438.2 | CGK |  | 1990438.2 | 0 |  |  | 1990438.2 |  |  | complete
| Construction of chainlink fence at Murantawua Pri.school | fencing | to increase enrolment | fencing | 3110200 | construction of buildings | kajiado central | ildamat |  | education | education | education | 2017-07-01 | 2017-08-01 | 2018-06-01 | 2018-06-01 | 4492065 | 4492065 | 4492065 | CGK |  | 4492065 | 0 |  |  | 4492065 |  |  | complete
| construction of 2 no 2 door pit latrines at empor nalepo primary school | Construction | to increase enrolment | Construction | 3110200 | construction of buildings | kajiado central | purko |  | education | education | education | 2017-07-01 | 2017-08-01 | 2018-06-01 | 2018-06-01 | 8998038 | 8998038 | 8998038 | CGK |  | 8998038 | 0 |  |  | 8998038 |  |  | complete
| proposed construction of administraion block at esukuta primary school | Construction | to increase enrolment | Construction | 3110200 | construction of buildings | kajiado central | purko |  | education | education | education | 2017-07-01 | 2017-08-01 | 2018-06-01 | 2018-06-01 | 7999261 | 7999261 | 7999261 | CGK |  | 7999261 | 0 |  |  | 7999261 |  |  | complete
| Construction of an ECDE Centre at Kumpa Pri. | Construction | to increase enrolment | Construction | 3110200 | construction of buildings | kajiado central | purko |  | education | education | education | 2017-07-01 | 2017-08-01 | 2018-06-01 | 2018-06-01 | 7985000 | 7985000 | 7985000 | CGK |  | 7985000 | 0 |  |  | 7985000 |  |  | complete
| Construction of an ECDE Centre at Enkaroni Pri. | Construction | to increase enrolment | Construction | 3110200 | construction of buildings | kajiado central | matapato north |  | education | education | education | 2017-07-01 | 2017-08-01 | 2018-06-01 | 2018-06-01 | 2999584 | 2999584 | 2999584 | CGK |  | 2999584 | 0 |  |  | 2999584 |  |  | complete
| Costruction of ecde centre and staff house at entukai | Construction | to increase enrolment | Construction | 3110200 | construction of buildings | kajiado central | matapato north |  | education | education | education | 2017-07-01 | 2017-08-01 | 2018-06-01 | 2018-06-01 | 2994438 | 2994438 | 2994438 | CGK |  | 2994438 | 0 |  |  | 2994438 |  |  | complete
| Construction of 2no.classroom at Nemayai Pri.school | Construction | to increase enrolment | Construction | 3110200 | construction of buildings | kajiado central | matapato north |  | education | education | education | 2017-07-01 | 2017-08-01 | 2018-06-01 | 2018-06-01 | 2997156 | 2997156 | 2997156 | CGK |  | 2997156 | 0 |  |  | 2997156 |  |  | complete
| Construction of 2no.classroom at Kalia Pri.school | Construction | to increase enrolment | Construction | 3110200 | construction of buildings | kajiado central | matapato north |  | education | education | education | 2017-07-01 | 2017-08-01 | 2018-06-01 | 2018-06-01 | 2991910 | 2991910 | 2991910 | CGK |  | 2991910 | 0 |  |  | 2991910 |  |  | complete
| Construction of 2no.classroom at Ngatataek Pri.school | Construction | to increase enrolment | Construction | 3110200 | construction of buildings | kajiado central | matapato south |  | education | education | education | 2017-07-01 | 2017-08-01 | 2018-06-01 | 2018-06-01 | 1499786 | 1499786 | 1499786 | CGK |  | 1499786 | 0 |  |  | 1499786 |  |  | complete
| Construction of Admistration block at Imarba sec.school | Construction | to increase enrolment | Construction | 3110200 | construction of buildings | kajiado central | matapato south |  | education | education | education | 2017-07-01 | 2017-08-01 | 2018-06-01 | 2018-06-01 | 1497641.2 | 1497641.2 | 1497641.2 | CGK |  | 1497641.2 | 0 |  |  | 1497641.2 |  |  | complete
| Construction of 1no.classroom at Namanga township Pri.school | Construction | to increase enrolment | Construction | 3110200 | construction of buildings | kajiado central | matapato south |  | education | education | education | 2017-07-01 | 2017-08-01 | 2018-06-01 | 2018-06-01 | 1488989.6 | 1488989.6 | 1488989.6 | CGK |  | 1488989.6 | 0 |  |  | 1488989.6 |  |  | complete
| 1 NO CLASSROOM AT LAMPALAKAE PRIMARY SCHOOL | Construction | to increase enrolment | Construction | 3110200 | construction of buildings | kajiado central | matapato south |  | education | education | education | 2017-07-01 | 2017-08-01 | 2018-06-01 | 2018-06-01 | 2487300 | 2487300 | 2487300 | CGK |  | 2487300 | 0 |  |  | 2487300 |  |  | complete
| 1 NO CLASSROOM AT MITON PRIMARY SCHOOL | Construction | to increase enrolment | Construction | 3110200 | construction of buildings | kajiado central | matapato south |  | education | education | education | 2017-07-01 | 2017-08-01 | 2018-06-01 | 2018-06-01 | 1499433 | 1499433 | 1499433 | CGK |  | 1499433 | 0 |  |  | 1499433 |  |  | complete
| ADMINISTRATION BLOCK AT NOOSIKITOK PRIMARY SCHOOL | Construction | to increase enrolment | Construction | 3110200 | construction of buildings | kajiado central | matapato south |  | education | education | education | 2017-07-01 | 2017-08-01 | 2018-06-01 | 2018-06-01 | 1498158 | 1498158 | 1498158 | CGK |  | 1498158 | 0 |  |  | 1498158 |  |  | complete
| construction of 1 no classroom at nairrabala prmary school | Construction | to increase enrolment | Construction | 3110200 | construction of buildings | kajiado central | matapato south |  | education | education | education | 2017-07-01 | 2017-08-01 | 2018-06-01 | 2018-06-01 | 1497734 | 1497734 | 1497734 | CGK |  | 1497734 | 0 |  |  | 1497734 |  |  | complete
| 1 NO CLASSROOM AT kisapuk PRIMARY SCHOOL | Construction | to increase enrolment | Construction | 3110200 | construction of buildings | kajiado central | matapato south |  | education | education | education | 2017-07-01 | 2017-08-01 | 2018-06-01 | 2018-06-01 | 1497641.2 | 1497641.2 | 1497641.2 | CGK |  | 1497641.2 | 0 |  |  | 1497641.2 |  |  | complete
| construction of 1 no ECDE classroom at enderkesi prmary school | Construction | to increase enrolment | Construction | 3110200 | construction of buildings | kajiado west | mosiro |  | education | education | education | 2017-07-01 | 2017-08-01 | 2018-06-01 | 2018-06-01 | 1472408 | 1472408 | 1472408 | CGK |  | 1472408 | 0 |  |  | 1472408 |  |  | complete
| construction of 1 no classroom at namelok primary school | Construction | to increase enrolment | Construction | 3110200 | construction of buildings | kajiado west | mosiro |  | education | education | education | 2017-07-01 | 2017-08-01 | 2018-06-01 | 2018-06-01 | 1497548 | 1497548 | 1497548 | CGK |  | 1497548 | 0 |  |  | 1497548 |  |  | complete
| 1no.Classroom at Eiti Primary school | Construction | to increase enrolment | Construction | 3110200 | construction of buildings | kajiado west | mosiro |  | education | education | education | 2017-07-01 | 2017-08-01 | 2018-06-01 | 2018-06-01 | 1999422 | 1999422 | 1999422 | CGK |  | 1999422 | 0 |  |  | 1999422 |  |  | complete
| 1no.Classroom at Enaikishomi Primary school | Construction | to increase enrolment | Construction | 3110200 | construction of buildings | kajiado west | mosiro |  | education | education | education | 2017-07-01 | 2017-08-01 | 2018-06-01 | 2018-06-01 | 4940382 | 4940382 | 4940382 | CGK |  | 4940382 | 0 |  |  | 4940382 |  |  | complete
| Completion of a Dormitory at Oldorko Primary school | Construction | to increase enrolment | Construction | 3110200 | construction of buildings | kajiado west | mosiro |  | education | education | education | 2017-07-01 | 2017-08-01 | 2018-06-01 | 2018-06-01 | 1059080 | 1059080 | 1059080 | CGK |  | 1059080 | 0 |  |  | 1059080 |  |  | complete
| COMPLETION AND EQUIPING OF DORMITORY AT NANINGOI GIRLS | Construction | to increase enrolment | Construction | 3110200 | construction of buildings | kajiado west | magadi |  | education | education | education | 2017-07-01 | 2017-08-01 | 2018-06-01 | 2018-06-01 | 2995256 | 2995256 | 2995256 | CGK |  | 2995256 | 0 |  |  | 2995256 |  |  | complete
| CHAINLINK FENCE AT NANINGOI GIRLS SECONDARY SCHOOL | fencing | to increase enrolment | fencing | 3110200 | construction of buildings | kajiado west | magadi |  | education | education | education | 2017-07-01 | 2017-08-01 | 2018-06-01 | 2018-06-01 | 1985189 | 1985189 | 1985189 | CGK |  | 1985189 | 0 |  |  | 1985189 |  |  | complete
| Construction of 2no.classroom at kimelok primary | Construction | to increase enrolment | Construction | 3110200 | construction of buildings | kajiado west | magadi |  | education | education | education | 2017-07-01 | 2017-08-01 | 2018-06-01 | 2018-06-01 | 1500000 | 1500000 | 1500000 | CGK |  | 1500000 | 0 |  |  | 1500000 |  |  | complete
| Construction of 1no.classroom at Ilaramatak pri.school | Construction | to increase enrolment | Construction | 3110200 | construction of buildings | kajiado west | magadi |  | education | education | education | 2017-07-01 | 2017-08-01 | 2018-06-01 | 2018-06-01 | 500000 | 500000 | 500000 | CGK |  | 500000 | 0 |  |  | 500000 |  |  | complete
| Construction of 1no.classroom at Losunyai pri.school | Construction | to increase enrolment | Construction | 3110200 | construction of buildings | kajiado west | magadi |  | education | education | education | 2017-07-01 | 2017-08-01 | 2018-06-01 | 2018-06-01 | 2000000 | 2000000 | 2000000 | CGK |  | 2000000 | 0 |  |  | 2000000 |  |  | complete
| Equiping of Shompole primary school | equiping | to increase enrolment | equiping | 3110200 | construction of buildings | kajiado west | magadi |  | education | education | education | 2017-07-01 | 2017-08-01 | 2018-06-01 | 2018-06-01 | 2498419 | 2498419 | 2498419 | CGK |  | 2498419 | 0 |  |  | 2498419 |  |  | complete
| Constructio of Teachers House and toilets at Komiti Primary sch. | Construction | to increase enrolment | Construction | 3110200 | construction of buildings | kajiado west | magadi |  | education | education | education | 2017-07-01 | 2017-08-01 | 2018-06-01 | 2018-06-01 | 2998704.4 | 2998704.4 | 2998704.4 | CGK |  | 2998704.4 | 0 |  |  | 2998704.4 |  |  | complete
| Constructio of Teachers House at Oldonyonyokie sec sch. | Construction | to increase enrolment | Construction | 3110200 | construction of buildings | kajiado west | magadi |  | education | education | education | 2017-07-01 | 2017-08-01 | 2018-06-01 | 2018-06-01 | 985628 | 985628 | 985628 | CGK |  | 985628 | 0 |  |  | 985628 |  |  | complete
| ADMINISTRATION BLOCK AT OLTARAJA PRIMARY SCHOOL | Construction | to increase enrolment | Construction | 3110200 | construction of buildings | kajiado west | magadi |  | education | education | education | 2017-07-01 | 2017-08-01 | 2018-06-01 | 2018-06-01 | 1994527.2 | 1994527.2 | 1994527.2 | CGK |  | 1994527.2 | 0 |  |  | 1994527.2 |  |  | complete
| Construction of Chainlink fence at Indarkalali pri.school | fencing | to increase enrolment | fencing | 3110200 | construction of buildings | kajiado west | magadi |  | education | education | education | 2017-07-01 | 2017-08-01 | 2018-06-01 | 2018-06-01 | 1499947 | 1499947 | 1499947 | CGK |  | 1499947 | 0 |  |  | 1499947 |  |  | complete
| 2 NO BEDROOM TEACHERS STAFF HOUSE AT ERORET PRIMARY SCHOOL | Construction | to increase enrolment | Construction | 3110200 | construction of buildings | kajiado west | magadi |  | education | education | education | 2017-07-01 | 2017-08-01 | 2018-06-01 | 2018-06-01 | 1498729.28 | 1498729.28 | 1498729.28 | CGK |  | 1498729.28 | 0 |  |  | 1498729.28 |  |  | complete
| 1 NO CLASSROOM AT ENTASOPIA PRIMARY SCHOOL | Construction | to increase enrolment | Construction | 3110200 | construction of buildings | kajiado west | magadi |  | education | education | education | 2017-07-01 | 2017-08-01 | 2018-06-01 | 2018-06-01 | 1096878 | 1096878 | 1096878 | CGK |  | 1096878 | 0 |  |  | 1096878 |  |  | complete
| CONSTRUCTION OF 1 NO CLASSROOM AT ENDONYIO OLASHO PRIMARY | Construction | to increase enrolment | Construction | 3110200 | construction of buildings | kajiado west | ewuaso cc nkidongi |  | education | education | education | 2017-07-01 | 2017-08-01 | 2018-06-01 | 2018-06-01 | 1490834.8 | 1490834.8 | 1490834.8 | CGK |  | 1490834.8 | 0 |  |  | 1490834.8 |  |  | complete
| Completion of a Classroom at Oloika secondary school | Construction | to increase enrolment | Construction | 3110200 | construction of buildings | kajiado west | ewuaso cc nkidongi |  | education | education | education | 2017-07-01 | 2017-08-01 | 2018-06-01 | 2018-06-01 | 1488929 | 1488929 | 1488929 | CGK |  | 1488929 | 0 |  |  | 1488929 |  |  | complete
| 1 NO CLASSROOM AT KIBIKO PRIMARY SCHOOL | Construction | to increase enrolment | Construction | 3110200 | construction of buildings | kajiado west | ewuaso cc nkidongi |  | education | education | education | 2017-07-01 | 2017-08-01 | 2018-06-01 | 2018-06-01 | 1480676 | 1480676 | 1480676 | CGK |  | 1480676 | 0 |  |  | 1480676 |  |  | complete
| Construction of Oiti ECDE centre | Construction | to increase enrolment | Construction | 3110200 | construction of buildings | kajiado west | ewuaso cc nkidongi |  | education | education | education | 2017-07-01 | 2017-08-01 | 2018-06-01 | 2018-06-01 | 2500000 | 2500000 | 2500000 | CGK |  | 2500000 | 0 |  |  | 2500000 |  |  | complete
| Construction of 1no. Classroom at Nasaru ECDE centre | Construction | to increase enrolment | Construction | 3110200 | construction of buildings | kajiado west | ewuaso cc nkidongi |  | education | education | education | 2017-07-01 | 2017-08-01 | 2018-06-01 | 2018-06-01 | 1500000 | 1500000 | 1500000 | CGK |  | 1500000 | 0 |  |  | 1500000 |  |  | complete
| Construction of teachers houses at Olorkidingi secondary school | equiping | to increase enrolment | equiping | 3110200 | construction of buildings | kajiado west | ewuaso cc nkidongi |  | education | education | education | 2017-07-01 | 2017-08-01 | 2018-06-01 | 2018-06-01 | 1498383.6 | 1498383.6 | 1498383.6 | CGK |  | 1498383.6 | 0 |  |  | 1498383.6 |  |  | complete
| Construction of 1no classroom at Saikeri Pri.School | Construction | to increase enrolment | Construction | 3110200 | construction of buildings | kajiado west | ewuaso cc nkidongi |  | education | education | education | 2017-07-01 | 2017-08-01 | 2018-06-01 | 2018-06-01 | 1477816.8 | 1477816.8 | 1477816.8 | CGK |  | 1477816.8 | 0 |  |  | 1477816.8 |  |  | complete
| 1 NO CLASSROOM AT INDERKES PRIMARY SCHOOL | Construction | to increase enrolment | Construction | 3110200 | construction of buildings | kajiado west | ewuaso cc nkidongi |  | education | education | education | 2017-07-01 | 2017-08-01 | 2018-06-01 | 2018-06-01 | 1495750 | 1495750 | 1495750 | CGK |  | 1495750 | 0 |  |  | 1495750 |  |  | complete
| 1 NO CLASSROOM AT OLOIKUMKUM PRIMARY SCHOOL | Construction | to increase enrolment | Construction | 3110200 | construction of buildings | kajiado west | Keekonyokie |  | education | education | education | 2017-07-01 | 2017-08-01 | 2018-06-01 | 2018-06-01 | 1499932 | 1499932 | 1499932 | CGK |  | 1499932 | 0 |  |  | 1499932 |  |  | complete
| construction of 1 no classroom at mpirishi primary school | fencing | to increase enrolment | fencing | 3110200 | construction of buildings | kajiado west | Keekonyokie |  | education | education | education | 2017-07-01 | 2017-08-01 | 2018-06-01 | 2018-06-01 | 1498686 | 1498686 | 1498686 | CGK |  | 1498686 | 0 |  |  | 1498686 |  |  | complete
| Construction of an ECDE centre at Esonorua Primary school | construction | to increase enrolment | construction | 3110200 | construction of buildings | kajiado west | Keekonyokie |  | education | education | education | 2017-07-01 | 2017-08-01 | 2018-06-01 | 2018-06-01 | 1500000 | 1500000 | 1500000 | CGK |  | 1500000 | 0 |  |  | 1500000 |  |  | complete
| Construction of an ECDE centre at Olomayiana west Primary school | Construction | to increase enrolment | Construction | 3110200 | construction of buildings | kajiado west | Keekonyokie |  | education | education | education | 2017-07-01 | 2017-08-01 | 2018-06-01 | 2018-06-01 | 2996465 | 2996465 | 2996465 | CGK |  | 2996465 | 0 |  |  | 2996465 |  |  | complete
| Construction of an ECDE centre at Enkorieroi Primary school | Construction | to increase enrolment | Construction | 3110200 | construction of buildings | kajiado west | Keekonyokie |  | education | education | education | 2017-07-01 | 2017-08-01 | 2018-06-01 | 2018-06-01 | 1486358 | 1486358 | 1486358 | CGK |  | 1486358 | 0 |  |  | 1486358 |  |  | complete
| Construction of 2no.Classroom at Inchorroi ECDE | Construction | to increase enrolment | Construction | 3110200 | construction of buildings | kajiado west | Keekonyokie |  | education | education | education | 2017-07-01 | 2017-08-01 | 2018-06-01 | 2018-06-01 | 2881741 | 2881741 | 2881741 | CGK |  | 2881741 | 0 |  |  | 2881741 |  |  | complete
| construction of 1 no classroom at naserian primary school | Construction | to increase enrolment | Construction | 3110200 | construction of buildings | kajiado west | Keekonyokie |  | education | education | education | 2017-07-01 | 2017-08-01 | 2018-06-01 | 2018-06-01 | 14000000 | 14000000 | 14000000 | CGK |  | 14000000 | 0 |  |  | 14000000 |  |  | complete
| Construction of 2 No classroom at Elangata oo Mayianat | construction | to increase enrolment | construction | 3110200 | construction of buildings | kajiado west | iloodokilani |  | education | education | education | 2017-07-01 | 2017-08-01 | 2018-06-01 | 2018-06-01 | 2996932 | 2996932 | 2996932 | CGK |  | 2996932 | 0 |  |  | 2996932 |  |  | complete
| Purchase of Land for Nkarusa ECDE | Construction | to increase enrolment | Construction | 3110200 | construction of buildings | kajiado west | iloodokilani |  | education | education | education | 2017-07-01 | 2017-08-01 | 2018-06-01 | 2018-06-01 | 3496611 | 3496611 | 3496611 | CGK |  | 3496611 | 0 |  |  | 3496611 |  |  | complete
| 2 no classroom at singiraine primary school | Construction | to increase enrolment | Construction | 3110200 | construction of buildings | kajiado west | iloodokilani |  | education | education | education | 2017-07-01 | 2017-08-01 | 2018-06-01 | 2018-06-01 | 1486438 | 1486438 | 1486438 | CGK |  | 1486438 | 0 |  |  | 1486438 |  |  | complete
| renovation of singiraine primary school | Construction | to increase enrolment | Construction | 3110200 | construction of buildings | kajiado north | Ongata Rongai |  | education | education | education | 2017-07-01 | 2017-08-01 | 2018-06-01 | 2018-06-01 | 10000000 | 10000000 | 10000000 | CGK |  | 10000000 | 0 |  |  | 10000000 |  |  | complete
| 1 no classroom at oloshaiki ecde | Construction | to increase enrolment | Construction | 3110200 | construction of buildings | kajiado north | Ongata Rongai |  | education | education | education | 2017-07-01 | 2017-08-01 | 2018-06-01 | 2018-06-01 | 6500000 | 6500000 | 6500000 | CGK |  | 6500000 | 0 |  |  | 6500000 |  |  | complete
| Construction of Multi-purpose hall at Olekasasi sec.school | construction | to increase enrolment | construction | 3110200 | construction of buildings | kajiado north | ngong |  | education | education | education | 2017-07-01 | 2017-08-01 | 2018-06-01 | 2018-06-01 | 1500000 | 1500000 | 1500000 | CGK |  | 1500000 | 0 |  |  | 1500000 |  |  | complete
| Construction of 3no workshop Olekasasi youth polytechnic | construction | to increase enrolment | construction | 3110200 | construction of buildings | kajiado north | ngong |  | education | education | education | 2017-07-01 | 2017-08-01 | 2018-06-01 | 2018-06-01 | 2992591 | 2992591 | 2992591 | CGK |  | 2992591 | 0 |  |  | 2992591 |  |  | complete
| Expansion and addition of 1no.classroom at Ngong sp school | Construction | to increase enrolment | Construction | 3110200 | construction of buildings | kajiado north | Oloolua |  | education | education | education | 2017-07-01 | 2017-08-01 | 2018-06-01 | 2018-06-01 | 4957003 | 4957003 | 4957003 | CGK |  | 4957003 | 0 |  |  | 4957003 |  |  | complete
| Construction of admistration Block at Ngong Township sec | Construction | to increase enrolment | Construction | 3110200 | construction of buildings | kajiado north | olkeri |  | education | education | education | 2017-07-01 | 2017-08-01 | 2018-06-01 | 2018-06-01 | 1964483 | 1964483 | 1964483 | CGK |  | 1964483 | 0 |  |  | 1964483 |  |  | complete
| Construction of ECDE centre at Oloolua primary | Construction | to increase enrolment | Construction | 3110200 | construction of buildings | kajiado north | olkeri |  | education | education | education | 2017-07-01 | 2017-08-01 | 2018-06-01 | 2018-06-01 | 1952250 | 1952250 | 1952250 | CGK |  | 1952250 | 0 |  |  | 1952250 |  |  | complete
| Construction of chainlink fence at Nalepo primary school | Construction | to increase enrolment | Construction | 3110200 | construction of buildings | kajiado south | kuku |  | education | education | education | 2017-07-01 | 2017-08-01 | 2018-06-01 | 2018-06-01 | 2980063.4 | 2980063.4 | 2980063.4 | CGK |  | 2980063.4 | 0 |  |  | 2980063.4 |  |  | complete
| construction of 1 no classroom and fence at dam area ECDE centre | Construction | to increase enrolment | Construction | 3110200 | construction of buildings | kajiado south | kuku |  | education | education | education | 2017-07-01 | 2017-08-01 | 2018-06-01 | 2018-06-01 | 2497433.6 | 2497433.6 | 2497433.6 | CGK |  | 2497433.6 | 0 |  |  | 2497433.6 |  |  | complete
| 2 NO CLASSROOM AT ENKOLILI PRIMARY SCHOOL | fencing | to increase enrolment | fencing | 3110200 | construction of buildings | kajiado south | kuku |  | education | education | education | 2017-07-01 | 2017-08-01 | 2018-06-01 | 2018-06-01 | 2996140.8 | 2996140.8 | 2996140.8 | CGK |  | 2996140.8 | 0 |  |  | 2996140.8 |  |  | complete
| construction of chainlink fence at ilkisonko sec sch | purchase | to increase enrolment | purchase | 3110200 | construction of buildings | kajiado south | kuku |  | education | education | education | 2017-07-01 | 2017-08-01 | 2018-06-01 | 2018-06-01 | 2999319 | 2999319 | 2999319 | CGK |  | 2999319 | 0 |  |  | 2999319 |  |  | complete
| 2 NO CLASSROOM AT OLEPOLOS IMURUTOT PRIMARY SCHOOL | Construction | to increase enrolment | Construction | 3110200 | construction of buildings | kajiado south | kuku |  | education | education | education | 2017-07-01 | 2017-08-01 | 2018-06-01 | 2018-06-01 | 1490613 | 1490613 | 1490613 | CGK |  | 1490613 | 0 |  |  | 1490613 |  |  | complete
| 2 NO CLASSROOM AT SAMAI PRIMARY SCHOOL | Renovation | to increase enrolment | Renovation | 3110200 | construction of buildings | kajiado south | rombo |  | education | education | education | 2017-07-01 | 2017-08-01 | 2018-06-01 | 2018-06-01 | 1999811 | 1999811 | 1999811 | CGK |  | 1999811 | 0 |  |  | 1999811 |  |  | complete
| 1 No Classroom at Lolmaroro pry school | Construction | to increase enrolment | Construction | 3110200 | construction of buildings | kajiado south | rombo |  | education | education | education | 2017-07-01 | 2017-08-01 | 2018-06-01 | 2018-06-01 | 2998145 | 2998145 | 2998145 | CGK |  | 2998145 | 0 |  |  | 2998145 |  |  | complete
| CONTRUCTION OF CHAINLINK FENCE AT ENTARARA PRIMARY SCHOOL | Construction | to increase enrolment | Construction | 3110200 | construction of buildings | kajiado south | imbrikani eselenkei |  | education | education | education | 2017-07-01 | 2017-08-01 | 2018-06-01 | 2018-06-01 | 2999226.4 | 2999226.4 | 2999226.4 | CGK |  | 2999226.4 | 0 |  |  | 2999226.4 |  |  | complete
| Construction of 2no classroom at Olmaroroi pry | construction | to increase enrolment | construction | 3110200 | construction of buildings | kajiado south | imbrikani eselenkei |  | education | education | education | 2017-07-01 | 2017-08-01 | 2018-06-01 | 2018-06-01 | 1499609 | 1499609 | 1499609 | CGK |  | 1499609 | 0 |  |  | 1499609 |  |  | complete
| 2 NO CLASSROOM AT OLMAPITIET PRIMARY SCHOOL | Construction | to increase enrolment | Construction | 3110200 | construction of buildings | kajiado south | imbrikani eselenkei |  | education
| 2 NO 2 DOOR PIT LATRINES AND 3 DOOR PIT LATRINE AT ISINET PRIMARY SCHOOL | Construction | to increase enrolment | Construction | 3110200 | construction of buildings | kajiado south | imbrikani eselenkei |  | education | education | education | 2018-07-01 | 2018-08-01 | 2019-06-01 | 2019-06-01 | 1999608 | 2000000 | 1999608 | CGK |  | 2000000 | 0 |  |  | 2000000 |  |  | complete
[11 empty] | education | education | 2018-07-01 | 2018-08-01 | 2019-06-01 | 2019-06-01 | 2999296 | 3000000 | 2999296 | CGK |  | 3000000 | 0 |  |  | 3000000 |  |  | complete
| Olsurutia ECDE Centre | Construction of toilets | to increase enrolment | Construction of toilets | 3110200 | construction of buildings | kajiado north | OLKERI |  | education | education | education | 2018-07-01 | 2018-08-01 | 2019-06-01 | 2019-06-01 | 28488057 | 10000000 | 28488057 | CGK |  | 10000000 | 0 |  |  | 10000000 |  |  | complete
| Oloolua primary school | Completion of Oloolua ECD | to increase enrolment | Completion of Oloolua ECD | 3110200 | construction of buildings | kajiado north | OLOOLUA |  | education | education | education | 2018-07-01 | 2018-08-01 | 2019-06-01 | 2019-06-01 | 8537019.04 | 9000000 | 8537019.04 | CGK |  | 9000000 | 0 |  |  | 9000000 |  |  | complete
| Ole Kasasi multi purpose hall | Ongoing construction of a multi purpose hall | to increase enrolment | Ongoing construction of a multi purpose hall | 3110200 | construction of buildings | kajiado north | ONGATA RONGAI |  | education | education | education | 2018-07-01 | 2018-08-01 | 2019-06-01 | 2019-06-01 | 3993996 | 4000000 | 3993996 | CGK |  | 4000000 | 0 |  |  | 4000000 |  |  | complete
| Nkoile Pri ECDE Centre | Construction of modern ECDE centre | to increase enrolment | Construction of modern ECDE centre | 3110200 | construction of buildings | kajiado central | PURKO |  | education | education | education | 2018-07-01 | 2018-08-01 | 2019-06-01 | 2019-06-01 | 2996220 | 3000000 | 2996220 | CGK |  | 3000000 | 0 |  |  | 3000000 |  |  | complete
| Letoire ECDE | Completion of Modern ECDE centre and equipping | to increase enrolment | Completion of Modern ECDE centre and equipping | 3110200 | construction of buildings | kajiado central | MATAPATO NORTH |  | education | education | education | 2018-07-01 | 2018-08-01 | 2019-06-01 | 2019-06-01 | 6755816.8 | 7000000 | 6755816.8 | CGK |  | 7000000 | 0 |  |  | 7000000 |  |  | complete
| Imporokua Pri school | Construction of two ECDE classrooms | to increase enrolment | Construction of two ECDE classrooms | 3110200 | construction of buildings | kajiado central | MATAPATO NORTH |  | education | education | education | 2018-07-01 | 2018-08-01 | 2019-06-01 | 2019-06-01 | 6964978.72 | 7000000 | 6964978.72 | CGK |  | 7000000 | 0 |  |  | 7000000 |  |  | complete
| Administration block | Construction of an Administration block at Paranae Sec School | to increase enrolment | Construction of an Administration block at Paranae Sec School | 3110200 | construction of buildings | kajiado central | ILDAMAT |  | education | education | education | 2018-07-01 | 2018-08-01 | 2019-06-01 | 2019-06-01 | 1497368 | 1500000 | 1497368 | CGK |  | 1500000 | 0 |  |  | 1500000 |  |  | complete
| Paranae School | Construction of four classes-Paranae | to increase enrolment | Construction of four classes-Paranae | 3110200 | construction of buildings | kajiado central | ILDAMAT |  | education | education | education | 2018-07-01 | 2018-08-01 | 2019-06-01 | 2019-06-01 | 10000000 | 5000000 | 10000000 | CGK |  | 5000000 | 0 |  |  | 5000000 |  |  | complete
| Orinie Ecd | Construction of one ECDE Classroom | to increase enrolment | Construction of one ECDE Classroom | 3110200 | construction of buildings | kajiado central | DALALEKUTUK |  | education | education | education | 2018-07-01 | 2018-08-01 | 2019-06-01 | 2019-06-01 | 2486993 | 2500000 | 2486993 | CGK |  | 2500000 | 0 |  |  | 2500000 |  |  | complete
| Enkorika secondary school | Construction of a dinning hall | to increase enrolment | Construction of a dinning hall | 3110200 | construction of buildings | kajiado central | DALALEKUTUK |  | education | education | education | 2018-07-01 | 2018-08-01 | 2019-06-01 | 2019-06-01 | 2492642 | 2500000 | 2492642 | CGK |  | 2500000 | 0 |  |  | 2500000 |  |  | complete
| Oloomunyi primary Ecd | Completion of ECDE Centre and equipping | to increase enrolment | Completion of ECDE Centre and equipping | 3110200 | construction of buildings | kajiado central | DALALEKUTUK |  | education | education | education | 2018-07-01 | 2018-08-01 | 2019-06-01 | 2019-06-01 | 997721 | 1000000 | 997721 | CGK |  | 1000000 | 0 |  |  | 1000000 |  |  | complete
| Modern ECDE Centre/isilale | Completion of ECDE Centre and equipping | to increase enrolment | Completion of ECDE Centre and equipping | 3110200 | construction of buildings | kajiado central | DALALEKUTUK |  | education | education | education | 2018-07-01 | 2018-08-01 | 2019-06-01 | 2019-06-01 | 1497000 | 1500000 | 1497000 | CGK |  | 1500000 | 0 |  |  | 1500000 |  |  | complete
| Iseuri primary Renovation | Renovation of Iseuri primary school | to increase enrolment | Renovation of Iseuri primary school | 3110200 | construction of buildings | kajiado central | DALALEKUTUK |  | education | education | education | 2018-07-01 | 2018-08-01 | 2019-06-01 | 2019-06-01 | 1998622 | 2000000 | 1998622 | CGK |  | 2000000 | 0 |  |  | 2000000 |  |  | complete
| Olobelibel ecd classes | Construction of Ecd class | to increase enrolment | Construction of Ecd class | 3110200 | construction of buildings | kajiado central | DALALEKUTUK |  | education | education | education | 2018-07-01 | 2018-08-01 | 2019-06-01 | 2019-06-01 | 2997532.8 | 3000000 | 2997532.8 | CGK |  | 3000000 | 0 |  |  | 3000000 |  |  | complete
| Iltaretto ECD classes | Construction of Ecd class | to increase enrolment | Construction of Ecd class | 3110200 | construction of buildings | kajiado central | DALALEKUTUK |  | education | education | education | 2018-07-01 | 2018-08-01 | 2019-06-01 | 2019-06-01 | 2499876 | 2500000 | 2499876 | CGK |  | 2500000 | 0 |  |  | 2500000 |  |  | complete
| Soita murt primary school | Construction of two ECDE classrooms | to increase enrolment | Construction of two ECDE classrooms | 3110200 | construction of buildings | kajiado west | EWUASO KEDONG |  | education | education | education | 2018-07-01 | 2018-08-01 | 2019-06-01 | 2019-06-01 | 2998102 | 3000000 | 2998102 | CGK |  | 3000000 | 0 |  |  | 3000000 |  |  | complete
| Olodungoro primary | Fencing | to increase enrolment | Fencing | 3110200 | construction of buildings | kajiado west | EWUASO KEDONG |  | education | education | education | 2018-07-01 | 2018-08-01 | 2019-06-01 | 2019-06-01 | 2997498 | 3000000 | 2997498 | CGK |  | 3000000 | 0 |  |  | 3000000 |  |  | complete
| Ormeroi primary | Construction of two ECDE classrooms | to increase enrolment | Construction of two ECDE classrooms | 3110200 | construction of buildings | kajiado west | EWUASO KEDONG |  | education | education | education | 2018-07-01 | 2018-08-01 | 2019-06-01 | 2019-06-01 | 1496771.2 | 1500000 | 1496771.2 | CGK |  | 1500000 | 0 |  |  | 1500000 |  |  | complete
| Kibiko Primary school | Construction of 2 ECDE classrooms | to increase enrolment | Construction of 2 ECDE classrooms | 3110200 | construction of buildings | kajiado west | EWUASO KEDONG |  | education | education | education | 2018-07-01 | 2018-08-01 | 2019-06-01 | 2019-06-01 | 1997090 | 2000000 | 1997090 | CGK |  | 2000000 | 0 |  |  | 2000000 |  |  | complete
| Ilparakuo ECDE | Construction of 1 ECDE classroom | to increase enrolment | Construction of 1 ECDE classroom | 3110200 | construction of buildings | kajiado west | EWUASO KEDONG |  | education | education | education | 2018-07-01 | 2018-08-01 | 2019-06-01 | 2019-06-01 | 997500 | 1000000 | 997500 | CGK |  | 1000000 | 0 |  |  | 1000000 |  |  | complete
| Intarshat primary school | Fencing and construction of toilets | to increase enrolment | Fencing and construction of toilets | 3110200 | construction of buildings | kajiado west | EWUASO KEDONG |  | education | education | education | 2018-07-01 | 2018-08-01 | 2019-06-01 | 2019-06-01 | 1497884 | 1500000 | 1497884 | CGK |  | 1500000 | 0 |  |  | 1500000 |  |  | complete
| Shompole pri school | Equipping of Shompole primary school | to increase enrolment | Equipping of Shompole primary school | 3110200 | construction of buildings | kajiado west | MAGADI |  | education | education | education | 2018-07-01 | 2018-08-01 | 2019-06-01 | 2019-06-01 | 1499276 | 1500000 | 1499276 | CGK |  | 1500000 | 0 |  |  | 1500000 |  |  | complete
| Oltulel ogol ECDE Classroom | Construction of one ECDE classroom | to increase enrolment | Construction of one ECDE classroom | 3110200 | construction of buildings | kajiado west | MAGADI |  | education | education | education | 2018-07-01 | 2018-08-01 | 2019-06-01 | 2019-06-01 | 2996338 | 3000000 | 2996338 | CGK |  | 3000000 | 0 |  |  | 3000000 |  |  | complete
| Endorkooonkishu ECDE | Construction of one ECDE Classroom | to increase enrolment | Construction of one ECDE Classroom | 3110200 | construction of buildings | kajiado west | MAGADI |  | education | education | education | 2018-07-01 | 2018-08-01 | 2019-06-01 | 2019-06-01 | 2997440 | 3000000 | 2997440 | CGK |  | 3000000 | 0 |  |  | 3000000 |  |  | complete
| Olkeri Sec school | Construction of two classrooms | to increase enrolment | Construction of two classrooms | 3110200 | construction of buildings | kajiado west | MAGADI |  | education | education | education | 2018-07-01 | 2018-08-01 | 2019-06-01 | 2019-06-01 | 2996454 | 3000000 | 2996454 | CGK |  | 3000000 | 0 |  |  | 3000000 |  |  | complete
| Oltiyani ECDE | Construction of two ECDE classrooms | to increase enrolment | Construction of two ECDE classrooms | 3110200 | construction of buildings | kajiado west | KEEKONYOKIE |  | education | education | education | 2018-07-01 | 2018-08-01 | 2019-06-01 | 2019-06-01 | 996324 | 1000000 | 996324 | CGK |  | 1000000 | 0 |  |  | 1000000 |  |  | complete
| Nado enterit ECDE | Construction of two ECDE classrooms | to increase enrolment | Construction of two ECDE classrooms | 3110200 | construction of buildings | kajiado west | KEEKONYOKIE |  | education | education | education | 2018-07-01 | 2018-08-01 | 2019-06-01 | 2019-06-01 | 2997440 | 3000000 | 2997440 | CGK |  | 3000000 | 0 |  |  | 3000000 |  |  | complete
| Oloirien pri school | Rehabilitation | to increase enrolment | Rehabilitation | 3110200 | construction of buildings | kajiado west | KEEKONYOKIE |  | education | education | education | 2018-07-01 | 2018-08-01 | 2019-06-01 | 2019-06-01 | 2989700 | 3000000 | 2989700 | CGK |  | 3000000 | 0 |  |  | 3000000 |  |  | complete
| Olooloitikoshi ECDE | Construction of two classrooms | to increase enrolment | Construction of two classrooms | 3110200 | construction of buildings | kajiado west | KEEKONYOKIE |  | education | education | education | 2018-07-01 | 2018-08-01 | 2019-06-01 | 2019-06-01 | 2985016 | 3000000 | 2985016 | CGK |  | 3000000 | 0 |  |  | 3000000 |  |  | complete
| Oloonkurmen ECDE | Contruction of two ECDE classrooms | to increase enrolment | Contruction of two ECDE classrooms | 3110200 | construction of buildings | kajiado west | KEEKONYOKIE |  | education | education | education | 2018-07-01 | 2018-08-01 | 2019-06-01 | 2019-06-01 | 2999987 | 3000000 | 2999987 | CGK |  | 3000000 | 0 |  |  | 3000000 |  |  | complete
| Embarbal pri school Admin block | Construction of an administration block at Embarbal pri school | to increase enrolment | Construction of an administration block at Embarbal pri school | 3110200 | construction of buildings | kajiado west | MOSIRO |  | education | education | education | 2018-07-01 | 2018-08-01 | 2019-06-01 | 2019-06-01 | 1418987 | 1500000 | 1418987 | CGK |  | 1500000 | 0 |  |  | 1500000 |  |  | complete
| Oldepe pri school | Construction of two ECDE classrooms at Oldepe pri school | to increase enrolment | Construction of two ECDE classrooms at Oldepe pri school | 3110200 | construction of buildings | kajiado west | MOSIRO |  | education | education | education | 2018-07-01 | 2018-08-01 | 2019-06-01 | 2019-06-01 | 1418987 | 1500000 | 1418987 | CGK |  | 1500000 | 0 |  |  | 1500000 |  |  | complete
| Imariani ECDE | Construction of one ECDE Classroom | to increase enrolment | Construction of one ECDE Classroom | 3110200 | construction of buildings | kajiado west | MOSIRO |  | education | education | education | 2018-07-01 | 2018-08-01 | 2019-06-01 | 2019-06-01 | 1418987 | 1500000 | 1418987 | CGK |  | 1500000 | 0 |  |  | 1500000 |  |  | complete
| Endapidapoi ECDE | Construction of one ECDE Classroom | to increase enrolment | Construction of one ECDE Classroom | 3110200 | construction of buildings | kajiado west | MOSIRO |  | education | education | education | 2018-07-01 | 2018-08-01 | 2019-06-01 | 2019-06-01 | 2993960 | 3000000 | 2993960 | CGK |  | 3000000 | 0 |  |  | 3000000 |  |  | complete
| Olepolos ECDE | Construction of one ECDE Classroom | to increase enrolment | Construction of one ECDE Classroom | 3110200 | construction of buildings | kajiado west | MOSIRO |  | education | education | education | 2018-07-01 | 2018-08-01 | 2019-06-01 | 2019-06-01 | 4997092 | 5000000 | 4997092 | CGK |  | 5000000 | 0 |  |  | 5000000 |  |  | complete
| Imbirikani Siana ECDE | Construction two ECDE classrooms | to increase enrolment | Construction two ECDE classrooms | 3110200 | construction of buildings | kajiado south | IMBIRIKANI |  | education | education | education | 2018-07-01 | 2018-08-01 | 2019-06-01 | 2019-06-01 | 3494094 | 3500000 | 3494094 | CGK |  | 3500000 | 0 |  |  | 3500000 |  |  | complete
| Enkii/Engosuani ECDE Centre | Construction of an ecde centre | to increase enrolment | Construction of an ecde centre | 3110200 | construction of buildings | kajiado south | IMBIRIKANI |  | education | education | education | 2018-07-01 | 2018-08-01 | 2019-06-01 | 2019-06-01 | 2994560 | 3000000 | 2994560 | CGK |  | 3000000 | 0 |  |  | 3000000 |  |  | complete
| A.I.C Girls sec school | Construction of Domitory at A.I.C | to increase enrolment | Construction of Domitory at A.I.C | 3110200 | construction of buildings | kajiado south | KUKU |  | education | education | education | 2018-07-01 | 2018-08-01 | 2019-06-01 | 2019-06-01 | 2992040 | 3000000 | 2992040 | CGK |  | 3000000 | 0 |  |  | 3000000 |  |  | complete
| Olgumaek ECDE two classrooms | Construction of two ECDE classrooms | to increase enrolment | Construction of two ECDE classrooms | 3110200 | construction of buildings | kajiado south | ROMBO |  | education | education | education | 2018-07-01 | 2018-08-01 | 2019-06-01 | 2019-06-01 | 1493094 | 1500000 | 1493094 | CGK |  | 1500000 | 0 |  |  | 1500000 |  |  | complete
| Oloyiapase ECDE Two Classrooms | Construction of two ECDE classrooms | to increase enrolment | Construction of two ECDE classrooms | 3110200 | construction of buildings | kajiado south | ROMBO |  | education | education | education | 2018-07-01 | 2018-08-01 | 2019-06-01 | 2019-06-01 | 993424 | 1000000 | 993424 | CGK |  | 1000000 | 0 |  |  | 1000000 |  |  | complete
| Orarait ECDE | Construction of one ECDE classrooms | to increase enrolment | Construction of one ECDE classrooms | 3110200 | construction of buildings | kajiado south | ROMBO |  | education | education | education | 2018-07-01 | 2018-08-01 | 2019-06-01 | 2019-06-01 | 1995988 | 2000000 | 1995988 | CGK |  | 2000000 | 0 |  |  | 2000000 |  |  | complete
| Kitengela boarding ECDE Latrine | Construction of latrine | to increase enrolment | Construction of latrine | 3110200 | construction of buildings | kajiado east | OLSIRKON |  | education | education | education | 2018-07-01 | 2018-08-01 | 2019-06-01 | 2019-06-01 | 2990439 | 3000000 | 2990439 | CGK |  | 3000000 | 0 |  |  | 3000000 |  |  | complete
| Ereteti sec school toilets | Contruction of latrine | to increase enrolment | Contruction of latrine | 3110200 | construction of buildings | kajiado east | KITENGELA |  | education | education | education | 2018-07-01 | 2018-08-01 | 2019-06-01 | 2019-06-01 | 4988000 | 5000000 | 4988000 | CGK |  | 5000000 | 0 |  |  | 5000000 |  |  | complete
| Enkasiti primary school | Construction of 70 bed domintory | to increase enrolment | Construction of 70 bed domintory | 3110200 | construction of buildings | kajiado east | KITENGELA |  | education | education | education | 2018-07-01 | 2018-08-01 | 2019-06-01 | 2019-06-01 | 1491412 | 1500000 | 1491412 | CGK |  | 1500000 | 0 |  |  | 1500000 |  |  | complete
| Oldirkish Ecd | Construction of modern Ecd centre | to increase enrolment | Construction of modern Ecd centre | 3110200 | construction of buildings | kajiado east | KENYAWA POKA |  | education | education | education | 2018-07-01 | 2018-08-01 | 2019-06-01 | 2019-06-01 | 1496165 | 1500000 | 1496165 | CGK |  | 1500000 | 0 |  |  | 1500000 |  |  | complete
| Entaretoi Primary School | Fencing | to increase enrolment | Fencing | 3110200 | construction of buildings | kajiado east | KENYAWA POKA |  | education | education | education | 2018-07-01 | 2018-08-01 | 2019-06-01 | 2019-06-01 | 1491017 | 1500000 | 1491017 | CGK |  | 1500000 | 0 |  |  | 1500000 |  |  | complete
| Samuli Primary School | Fencing | to increase enrolment | Fencing | 3110200 | construction of buildings | kajiado east | KENYAWA POKA |  | education | education | education | 2018-07-01 | 2018-08-01 | 2019-06-01 | 2019-06-01 | 1499346 | 1500000 | 1499346 | CGK |  | 1500000 | 0 |  |  | 1500000 |  |  | complete
| Nkaatu ECD class | Construction of Ecd class | to increase enrolment | Construction of Ecd class | 3110200 | construction of buildings | kajiado east | IMARORO |  | education | education | education | 2018-07-01 | 2018-08-01 | 2019-06-01 | 2019-06-01 | 1483640 | 1500000 | 1483640 | CGK |  | 1500000 | 0 |  |  | 1500000 |  |  | complete
| Naretoi ECD class | Construction of Ecd class | to increase enrolment | Construction of Ecd class | 3110200 | construction of buildings | kajiado east | IMARORO |  | education | education | education | 2018-07-01 | 2018-08-01 | 2019-06-01 | 2019-06-01 | 1497444 | 1500000 | 1497444 | CGK |  | 1500000 | 0 |  |  | 1500000 |  |  | complete
| Oloitiko Ecd class | Construction of a class | to increase enrolment | Construction of a class | 3110200 | construction of buildings | kajiado east | IMARORO |  | education | education | education | 2018-07-01 | 2018-08-01 | 2019-06-01 | 2019-06-01 | 3000000 | 3000000 | 3000000 | CGK |  | 3000000 | 0 |  |  | 3000000 |  |  | complete
| Olepolos Ecd | Construction of Ecd class | to increase enrolment | Construction of Ecd class | 3110200 | construction of buildings | kajiado east | KAPUTIEI NORTH |  | education
| Isinya primary | Construction of a girl dormitory | to increase enrolment | Construction of a girl dormitory | 3110200 | construction of buildings | kajiado east | KAPUTIEI NORTH |  | education | education | education | 2019-07-01 | 2019-08-01 | 2020-06-01 | 2020-06-01 | 700000 | 700000 | 700000 | CGK |  | 700000 | 0 |  |  | 700000 |  |  | on going
[11 empty] | education | education | 2019-07-01 | 2019-08-01 | 2020-06-01 | 2020-06-01 | 5000000 | 5000000 | 5000000 | CGK |  | 5000000 | 0 |  |  | 5000000 |  |  | Complete
| Precious gems pre school | Finishing works | to increase enrolment | Finishing works | 3110200 | construction of buildings | kajiado central | Dalalekutuk |  | education | education | education | 2019-07-01 | 2019-08-01 | 2020-06-01 | 2020-06-01 | 1497444 | 1497444 | 1497444 | CGK |  | 1497444 | 0 |  |  | 1497444 |  |  | Complete
| Oloontulugum dinning hall | Construction of a new dinning hall | to increase enrolment | Construction of a new dinning hall | 3110200 | construction of buildings | kajiado central | Dalalekutuk |  | education | education | education | 2019-07-01 | 2019-08-01 | 2020-06-01 | 2020-06-01 | 1500000 | 1500000 | 1500000 | CGK |  | 1500000 | 0 |  |  | 1500000 |  |  | Complete
| Naibala ECDE class | Consruction of a new classroom | to increase enrolment | Consruction of a new classroom | 3110200 | construction of buildings | kajiado central | Dalalekutuk |  | education | education | education | 2019-07-01 | 2019-08-01 | 2020-06-01 | 2020-06-01 | 1500000 | 1500000 | 1500000 | CGK |  | 1500000 | 0 |  |  | 1500000 |  |  | Complete
| Imanyat ECDE class | Consruction of a new classroom | to increase enrolment | Consruction of a new classroom | 3110200 | construction of buildings | kajiado central | Dalalekutuk |  | education | education | education | 2019-07-01 | 2019-08-01 | 2020-06-01 | 2020-06-01 | 2500000 | 2500000 | 2500000 | CGK |  | 2500000 | 0 |  |  | 2500000 |  |  | Complete
| Malilima ECDE class | Consruction of a new classroom | to increase enrolment | Consruction of a new classroom | 3110200 | construction of buildings | kajiado central | Dalalekutuk |  | education | education | education | 2019-07-01 | 2019-08-01 | 2020-06-01 | 2020-06-01 | 1995687 | 1995687 | 1995687 | CGK |  | 1995687 | 0 |  |  | 1995687 |  |  | Complete
| Enkutoto ECDE | Construction of 2 class rooms | to increase enrolment | Construction of 2 class rooms | 3110200 | construction of buildings | kajiado central | Dalalekutuk |  | education | education | education | 2019-07-01 | 2019-08-01 | 2020-06-01 | 2020-06-01 | 998100 | 998100 | 998100 | CGK |  | 998100 | 0 |  |  | 998100 |  |  | Complete
| Enyonyor ECDE | Construction of Teachers Quarters | to increase enrolment | Construction of Teachers Quarters | 3110200 | construction of buildings | kajiado central | Dalalekutuk |  | education | education | education | 2019-07-01 | 2019-08-01 | 2020-06-01 | 2020-06-01 | 1000000 | 1000000 | 1000000 | CGK |  | 1000000 | 0 |  |  | 1000000 |  |  | Complete
| Omoti ECDE | Construction of toilet | to increase enrolment | Construction of toilet | 3110200 | construction of buildings | kajiado south | Entonet |  | education | education | education | 2019-07-01 | 2019-08-01 | 2020-06-01 | 2020-06-01 | 1000000 | 1000000 | 1000000 | CGK |  | 1000000 | 0 |  |  | 1000000 |  |  | Complete
| Oldule ECDE | Construction of toilet | to increase enrolment | Construction of toilet | 3110200 | construction of buildings | kajiado south | Entonet |  | education | education | education | 2019-07-01 | 2019-08-01 | 2020-06-01 | 2020-06-01 | 983013 | 983013 | 983013 | CGK |  | 983013 | 0 |  |  | 983013 |  |  | Complete
| Naiperra ECDE | Construction of toilet | to increase enrolment | Construction of toilet | 3110200 | construction of buildings | kajiado south | Entonet |  | education | education | education | 2019-07-01 | 2019-08-01 | 2020-06-01 | 2020-06-01 | 3000000 | 3000000 | 3000000 | CGK |  | 3000000 | 0 |  |  | 3000000 |  |  | Complete
| Lemaai ECDE | Construction of toilet | to increase enrolment | Construction of toilet | 3110200 | construction of buildings | kajiado south | Entonet |  | education | education | education | 2019-07-01 | 2019-08-01 | 2020-06-01 | 2020-06-01 | 2995978 | 2995978 | 2995978 | CGK |  | 2995978 | 0 |  |  | 2995978 |  |  | Complete
| Nkarampuni ECDE | Construction of 2 ECDE classes at Nkarampuni | to increase enrolment | Construction of 2 ECDE classes at Nkarampuni | 3110200 | construction of buildings | kajiado south | Entonet |  | education | education | education | 2019-07-01 | 2019-08-01 | 2020-06-01 | 2020-06-01 | 2984123 | 2984123 | 2984123 | CGK |  | 2984123 | 0 |  |  | 2984123 |  |  | Complete
| Enkusero ECDE | Construction of two ECDE classrooms | to increase enrolment | Construction of two ECDE classrooms | 3110200 | construction of buildings | kajiado south | Entonet |  | education | education | education | 2019-07-01 | 2019-08-01 | 2020-06-01 | 2020-06-01 | 2955250 | 2955250 | 2955250 | CGK |  | 2955250 | 0 |  |  | 2955250 |  |  | on going
| Olgumi Classroom | Construction of 2 ECDE clasrooms | to increase enrolment | Construction of 2 ECDE clasrooms | 3110200 | construction of buildings | kajiado west | Ewuaso |  | education | education | education | 2019-07-01 | 2019-08-01 | 2020-06-01 | 2020-06-01 | 3000000 | 3000000 | 3000000 | CGK |  | 3000000 | 0 |  |  | 3000000 |  |  | Complete
| Najile pri school | Construction of 2 ECDE clasrooms | to increase enrolment | Construction of 2 ECDE clasrooms | 3110200 | construction of buildings | kajiado west | Ewuaso |  | education | education | education | 2019-07-01 | 2019-08-01 | 2020-06-01 | 2020-06-01 | 1995316 | 1995316 | 1995316 | CGK |  | 1995316 | 0 |  |  | 1995316 |  |  | Complete
| Osupuko pri school | Fencing of Osupuko pri school | to increase enrolment | Fencing of Osupuko pri school | 3110200 | construction of buildings | kajiado west | Ewuaso |  | education | education | education | 2019-07-01 | 2019-08-01 | 2020-06-01 | 2020-06-01 | 2000000 | 2000000 | 2000000 | CGK |  | 2000000 | 0 |  |  | 2000000 |  |  | Complete
| Olmaroroi pri school | fencing of Olmaroroi pri school | to increase enrolment | fencing of Olmaroroi pri school | 3110200 | construction of buildings | kajiado west | Ewuaso |  | education | education | education | 2019-07-01 | 2019-08-01 | 2020-06-01 | 2020-06-01 | 1500000 | 1500000 | 1500000 | CGK |  | 1500000 | 0 |  |  | 1500000 |  |  | Complete
| Computer lab in kajiado township | Construction of a new computer lab | to increase enrolment | Construction of a new computer lab | 3110200 | construction of buildings | kajiado west | Ildamat |  | education | education | education | 2019-07-01 | 2019-08-01 | 2020-06-01 | 2020-06-01 | 3000000 | 3000000 | 3000000 | CGK |  | 3000000 | 0 |  |  | 3000000 |  |  | on going
| Oltaraja ECDE | Construction of one classroom | to increase enrolment | Construction of one classroom | 3110200 | construction of buildings | kajiado west | Ildamat |  | education | education | education | 2019-07-01 | 2019-08-01 | 2020-06-01 | 2020-06-01 | 1500000 | 1500000 | 1500000 | CGK |  | 1500000 | 0 |  |  | 1500000 |  |  | on going
| 2 classroooms at Kora Primary School | Construction of two ECDE classrooms | to increase enrolment | Construction of two ECDE classrooms | 3110200 | construction of buildings | kajiado west | Iloodokilani |  | education | education | education | 2019-07-01 | 2019-08-01 | 2020-06-01 | 2020-06-01 | 3000000 | 3000000 | 3000000 | CGK |  | 3000000 | 0 |  |  | 3000000 |  |  | on going
| Ewangan ECDE | Consruction of 1 ECDE classroom | to increase enrolment | Consruction of 1 ECDE classroom | 3110200 | construction of buildings | kajiado west | Iloodokilani |  | education | education | education | 2019-07-01 | 2019-08-01 | 2020-06-01 | 2020-06-01 | 3999000 | 3999000 | 3999000 | CGK |  | 3999000 | 0 |  |  | 3999000 |  |  | Complete
| Olodonterit ECDE | Consruction of 2 ECDE classroom | to increase enrolment | Consruction of 2 ECDE classroom | 3110200 | construction of buildings | kajiado west | Iloodokilani |  | education | education | education | 2019-07-01 | 2019-08-01 | 2020-06-01 | 2020-06-01 | 2000000 | 2000000 | 2000000 | CGK |  | 2000000 | 0 |  |  | 2000000 |  |  | terminated
| KMQ ECDE | Construction of two ECDE classrooms and a toilet | to increase enrolment | Construction of two ECDE classrooms and a toilet | 3110200 | construction of buildings | kajiado west | Iloodokilani |  | education | education | education | 2019-07-01 | 2019-08-01 | 2020-06-01 | 2020-06-01 | 2000000 | 2000000 | 2000000 | CGK |  | 2000000 | 0 |  |  | 2000000 |  |  | complete
| Entashata ECDE | Construction of ECDE classroom and pit Latrine | to increase enrolment | Construction of ECDE classroom and pit Latrine | 3110200 | construction of buildings | kajiado west | Iloodokilani |  | education | education | education | 2019-07-01 | 2019-08-01 | 2020-06-01 | 2020-06-01 | 1497502 | 1497502 | 1497502 | CGK |  | 1497502 | 0 |  |  | 1497502 |  |  | Complete
| Entepesi ECDE | construction of one ECDE classroom and a pit latrine | to increase enrolment | construction of one ECDE classroom and a pit latrine | 3110200 | construction of buildings | kajiado west | Iloodokilani |  | education | education | education | 2019-07-01 | 2019-08-01 | 2020-06-01 | 2020-06-01 | 1000000 | 1000000 | 1000000 | CGK |  | 1000000 | 0 |  |  | 1000000 |  |  | complete
| Oltanki ECDE | Construction of 1 classroom | to increase enrolment | Construction of 1 classroom | 3110200 | construction of buildings | kajiado west | Iloodokilani |  | education | education | education | 2019-07-01 | 2019-08-01 | 2020-06-01 | 2020-06-01 | 2000000 | 2000000 | 2000000 | CGK |  | 2000000 | 0 |  |  | 2000000 |  |  | Complete
| Olooltoi ECDE | Purchase of desks and construction of a toilet | to increase enrolment | Purchase of desks and construction of a toilet | 3110200 | construction of buildings | kajiado west | Iloodokilani |  | education | education | education | 2019-07-01 | 2019-08-01 | 2020-06-01 | 2020-06-01 | 499800 | 499800 | 499800 | CGK |  | 499800 | 0 |  |  | 499800 |  |  | Complete
| Noonkujit ECDE | Construction of one ECDE classroom and toilet | to increase enrolment | Construction of one ECDE classroom and toilet | 3110200 | construction of buildings | kajiado west | Iloodokilani |  | education | education | education | 2019-07-01 | 2019-08-01 | 2020-06-01 | 2020-06-01 | 1500000 | 1500000 | 1500000 | CGK |  | 1500000 | 0 |  |  | 1500000 |  |  | Complete
| Indupa ECDE | Purchase of desks | to increase enrolment | Purchase of desks | 3110200 | construction of buildings | kajiado west | Iloodokilani |  | education | education | education | 2019-07-01 | 2019-08-01 | 2020-06-01 | 2020-06-01 | 2998716 | 2998716 | 2998716 | CGK |  | 2998716 | 0 |  |  | 2998716 |  |  | Complete
|  | Construction of ECDE 1(one) classroom | to increase enrolment | Construction of ECDE 1(one) classroom | 3110200 | construction of buildings |  |  |  | education | education | education | 2019-07-01 | 2019-08-01 | 2020-06-01 | 2020-06-01 | 2997579 | 2997579 | 2997579 | CGK |  | 2997579 | 0 |  |  | 2997579 |  |  | Complete
| kalebweni pri school | fencing of kalebweni pri school | to increase enrolment | fencing of kalebweni pri school | 3110200 | construction of buildings | kajiado east | Imaroro |  | education | education | education | 2019-07-01 | 2019-08-01 | 2020-06-01 | 2020-06-01 | 1000000 | 1000000 | 1000000 | CGK |  | 1000000 | 0 |  |  | 1000000 |  |  | Complete
| Illoirero ECDE | Construction of two ECDE classrooms | to increase enrolment | Construction of two ECDE classrooms | 3110200 | construction of buildings | kajiado south | Imbirikani |  | education | education | education | 2019-07-01 | 2019-08-01 | 2020-06-01 | 2020-06-01 | 1500000 | 1500000 | 1500000 | CGK |  | 1500000 | 0 |  |  | 1500000 |  |  | Complete
| enkongu primary school | construction of toilets | to increase enrolment | construction of toilets | 3110200 | construction of buildings | kajiado south | Imbirikani |  | education | education | education | 2019-07-01 | 2019-08-01 | 2020-06-01 | 2020-06-01 | 1500000 | 1500000 | 1500000 | CGK |  | 1500000 | 0 |  |  | 1500000 |  |  | Complete
| Naserian ECDE | Construction one ECDE classroom at Naserian primary school | to increase enrolment | Construction one ECDE classroom at Naserian primary school | 3110200 | construction of buildings | kajiado east | Kaputie North |  | education | education | education | 2019-07-01 | 2019-08-01 | 2020-06-01 | 2020-06-01 | 1480670 | 1480670 | 1480670 | CGK |  | 1480670 | 0 |  |  | 1480670 |  |  | Complete
| Ilpolosat ECDE | Construction of one ECDE classroom at Ilpolosat primary school | to increase enrolment | Construction of one ECDE classroom at Ilpolosat primary school | 3110200 | construction of buildings | kajiado east | Kaputie North |  | education | education | education | 2019-07-01 | 2019-08-01 | 2020-06-01 | 2020-06-01 | 1500000 | 1500000 | 1500000 | CGK |  | 1500000 | 0 |  |  | 1500000 |  |  | Complete
| Kaputiei ECDE | Construction one ECDE classroom at Kaputei primary school | to increase enrolment | Construction one ECDE classroom at Kaputei primary school | 3110200 | construction of buildings | kajiado east | Kaputie North |  | education | education | education | 2019-07-01 | 2019-08-01 | 2020-06-01 | 2020-06-01 | 2000000 | 2000000 | 2000000 | CGK |  | 2000000 | 0 |  |  | 2000000 |  |  | on going
| Ketuura ECDE | Construction one ECDE classroom at Ketuura primary school | to increase enrolment | Construction one ECDE classroom at Ketuura primary school | 3110200 | construction of buildings | kajiado east | Kaputie North |  | education | education | education | 2019-07-01 | 2019-08-01 | 2020-06-01 | 2020-06-01 | 1999998 | 1999998 | 1999998 | CGK |  | 1999998 | 0 |  |  | 1999998 |  |  | Complete
| Isinya pri school | Completion of construction of Isinya pri school dormitory | to increase enrolment | Completion of construction of Isinya pri school dormitory | 3110200 | construction of buildings | kajiado east | Kaputie North |  | education | education | education | 2019-07-01 | 2019-08-01 | 2020-06-01 | 2020-06-01 | 5362169 | 5362169 | 5362169 | CGK |  | 5362169 | 0 |  |  | 5362169 |  |  | Complete
| Ole Lenku pri school | Fencing of Ole Lenku primary school | to increase enrolment | Fencing of Ole Lenku primary school | 3110200 | construction of buildings | kajiado east | Kaputie North |  | education | education | education | 2019-07-01 | 2019-08-01 | 2020-06-01 | 2020-06-01 | 3000000 | 3000000 | 3000000 | CGK |  | 3000000 | 0 |  |  | 3000000 |  |  | Complete
| Kikayaya pri school | construction of teacher quarter at Kikayaya pri school | to increase enrolment | construction of teacher quarter at Kikayaya pri school | 3110200 | construction of buildings | kajiado east | Kaputie North |  | education | education | education | 2019-07-01 | 2019-08-01 | 2020-06-01 | 2020-06-01 | 1500000 | 1500000 | 1500000 | CGK |  | 1500000 | 0 |  |  | 1500000 |  |  | Complete
| Olosurutia ECDE | Construction of classroom for PWDs at Olosurutia | to increase enrolment | Construction of classroom for PWDs at Olosurutia | 3110200 | construction of buildings | kajiado west | Keekonyokie |  | education | education | education | 2019-07-01 | 2019-08-01 | 2020-06-01 | 2020-06-01 | 3000000 | 3000000 | 3000000 | CGK |  | 3000000 | 0 |  |  | 3000000 |  |  | Complete
| Endonyiosidai Primary ECDE | Construction of ECDE classroom | to increase enrolment | Construction of ECDE classroom | 3110200 | construction of buildings | kajiado west | Keekonyokie |  | education | education | education | 2019-07-01 | 2019-08-01 | 2020-06-01 | 2020-06-01 | 3999000 | 3999000 | 3999000 | CGK |  | 3999000 | 0 |  |  | 3999000 |  |  | Complete
| Oloirien day secondary school | Construction of a new secondary school | to increase enrolment | Construction of a new secondary school | 3110200 | construction of buildings | kajiado west | Keekonyokie |  | education | education | education | 2019-07-01 | 2019-08-01 | 2020-06-01 | 2020-06-01 | 2000000 | 2000000 | 2000000 | CGK |  | 2000000 | 0 |  |  | 2000000 |  |  | Complete
| Engumi ECDE | Fencing of Engumi ECDE | to increase enrolment | Fencing of Engumi ECDE | 3110200 | construction of buildings | kajiado south | Kimana |  | education | education | education | 2019-07-01 | 2019-08-01 | 2020-06-01 | 2020-06-01 | 2000000 | 2000000 | 2000000 | CGK |  | 2000000 | 0 |  |  | 2000000 |  |  | Complete
| Kimana primary school | construction of two ECDE Classrooms at Kimana primary school | to increase enrolment | construction of two ECDE Classrooms at Kimana primary school | 3110200 | construction of buildings | kajiado south | Kimana |  | education | education | education | 2019-07-01 | 2019-08-01 | 2020-06-01 | 2020-06-01 | 1497502 | 1497502 | 1497502 | CGK |  | 1497502 | 0 |  |  | 1497502 |  |  | Complete
| Oloile primary school | fencing of Oloile primary school | to increase enrolment | fencing of Oloile primary school | 3110200 | construction of buildings | kajiado south | Kimana |  | education | education | education | 2019-07-01 | 2019-08-01 | 2020-06-01 | 2020-06-01 | 1000000 | 1000000 | 1000000 | CGK |  | 1000000 | 0 |  |  | 1000000 |  |  | Complete
| Esoit Pus | Construction of 1 ECDE class at Esoit Pus | to increase enrolment | Construction of 1 ECDE class at Esoit Pus | 3110200 | construction of buildings | kajiado south | Kuku |  | education | education | education | 2019-07-01 | 2019-08-01 | 2020-06-01 | 2020-06-01 | 2000000 | 2000000 | 2000000 | CGK |  | 2000000 | 0 |  |  | 2000000 |  |  | Complete
| Elangata Enkima primary school | completion of Construction of an administration block at elangata enkima pri school | to increase enrolment | completion of Construction of an administration block at elangata enkima pri school | 3110200 | construction of buildings | kajiado south | Kuku |  | education | education | education | 2019-07-01 | 2019-08-01 | 2020-06-01 | 2020-06-01 | 499800 | 499800 | 499800 | CGK |  | 499800 | 0 |  |  | 499800 |  |  | Complete
| Olmatasia ECDE | Construction of one ECDE classroom at Olmatasia ECDE | to increase enrolment | Construction of one ECDE classroom at Olmatasia ECDE | 3110200 | construction of buildings | kajiado south | Kuku |  | education | education | education | 2019-07-01 | 2019-08-01 | 2020-06-01 | 2020-06-01 | 1500000 | 1500000 | 1500000 | CGK |  | 1500000 | 0 |  |  | 1500000 |  |  | Complete
| Lenkaitole ECDE | Construction of one ECDE classroom at Lenkatole ECDE | to increase enrolment | Construction of one ECDE classroom at Lenkatole ECDE | 3110200 | construction of buildings | kajiado south | Kuku |  | education | education | education | 2019-07-01 | 2019-08-01 | 2020-06-01 | 2020-06-01 | 2998716 | 2998716 | 2998716 | CGK |  | 2998716 | 0 |  |  | 2998716 |  |  | Complete
| naikishomi ECDE | Construction of ECDE classroom | to increase enrolment | Construction of ECDE classroom | 3110200 | construction of buildings | kajiado west | Magadi |  | education | education | education | 2019-07-01 | 2019-08-01 | 2020-06-01 | 2020-06-01 | 2997579 | 2997579 | 2997579 | CGK |  | 2997579 | 0 |  |  | 2997579 |  |  | stalled
| Oloililai ECDE | Construction of class | to increase enrolment | Construction of class | 3110200 | construction of buildings | kajiado west | Magadi |  | education | education | education | 2019-07-01 | 2019-08-01 | 2020-06-01 | 2020-06-01 | 1000000 | 1000000 | 1000000 | CGK |  | 1000000 | 0 |  |  | 1000000 |  |  | stalled
| Entasopia ECDE | Construction of one ECDE classroom | to increase enrolment | Construction of one ECDE classroom | 3110200 | construction of buildings | kajiado west | Magadi |  | education | education | education | 2019-07-01 | 2019-08-01 | 2020-06-01 | 2020-06-01 | 1500000 | 1500000 | 1500000 | CGK |  | 1500000 | 0 |  |  | 1500000 |  |  | Complete
| Lorngosua ECDE | Construction of one ECDE classroom | to increase enrolment | Construction of one ECDE classroom | 3110200 | construction of buildings | kajiado west | Magadi |  | education | education | education | 2019-07-01 | 2019-08-01 | 2020-06-01 | 2020-06-01 | 1500000 | 1500000 | 1500000 | CGK |  | 1500000 | 0 |  |  | 1500000 |  |  | Complete
| Kayior ECDE | Construction of one ECDE classroom | to increase enrolment | Construction of one ECDE classroom | 3110200 | construction of buildings | kajiado west | Magadi |  | education | education | education | 2019-07-01 | 2019-08-01 | 2020-06-01 | 2020-06-01 | 1480670 | 1480670 | 1480670 | CGK |  | 1480670 | 0 |  |  | 1480670 |  |  | Complete
| Oldonyonyokie girls secondary school | Fencing of school | to increase enrolment | Fencing of school | 3110200 | construction of buildings | kajiado west | Magadi |  | education | education | education | 2019-07-01 | 2019-08-01 | 2020-06-01 | 2020-06-01 | 1500000 | 1500000 | 1500000 | CGK |  | 1500000 | 0 |  |  | 1500000 |  |  | Complete
| Oleleshwa ECDE classroom | Construction of a new classroom and a toilet | to increase enrolment | Construction of a new classroom and a toilet | 3110200 | construction of buildings | kajiado central | Matapato North |  | education | education | education | 2019-07-01 | 2019-08-01 | 2020-06-01 | 2020-06-01 | 2000000 | 2000000 | 2000000 | CGK |  | 2000000 | 0 |  |  | 2000000 |  |  | Complete
| Lele ECDE class | Construction of a new classroom and a toilet | to increase enrolment | Construction of a new classroom and a toilet | 3110200 | construction of buildings | kajiado central | Matapato North |  | education | education | education | 2019-07-01 | 2019-08-01 | 2020-06-01 | 2020-06-01 | 1999998 | 1999998 | 1999998 | CGK |  | 1999998 | 0 |  |  | 1999998 |  |  | Complete
| Enkeju erap ECDE class | Construction of 2 class rooms | to increase enrolment | Construction of 2 class rooms | 3110200 | construction of buildings | kajiado central | Matapato North |  | education | education | education | 2019-07-01 | 2019-08-01 | 2020-06-01 | 2020-06-01 | 5362169 | 5362169 | 5362169 | CGK |  | 5362169 | 0 |  |  | 5362169 |  |  | on going
| Namelok ECDE class | Construction of 1 classroom | to increase enrolment | Construction of 1 classroom | 3110200 | construction of buildings | kajiado central | Matapato North |  | education | education | education | 2019-07-01 | 2019-08-01 | 2020-06-01 | 2020-06-01 | 1000000 | 1000000 | 1000000 | CGK |  | 1000000 | 0 |  |  | 1000000 |  |  | Complete
| Oiti emotoroki ECDE | Construction of 1 classroom | to increase enrolment | Construction of 1 classroom | 3110200 | construction of buildings | kajiado central | Matapato North |  | education | education | education | 2019-07-01 | 2019-08-01 | 2020-06-01 | 2020-06-01 | 2000000 | 2000000 | 2000000 | CGK |  | 2000000 | 0 |  |  | 2000000 |  |  | Complete
| Lorngósua primary sch | Construction of 6 doors toilets | to increase enrolment | Construction of 6 doors toilets | 3110200 | construction of buildings | kajiado central | Matapato North |  | education | education | education | 2019-07-01 | 2019-08-01 | 2020-06-01 | 2020-06-01 | 3000000 | 3000000 | 3000000 | CGK |  | 3000000 | 0 |  |  | 3000000 |  |  | oongoing
| Oloibor soit pry school | Construction of a classroom and a toilet | to increase enrolment | Construction of a classroom and a toilet | 3110200 | construction of buildings | kajiado central | Matapato North |  | education | education | education | 2019-07-01 | 2019-08-01 | 2020-06-01 | 2020-06-01 | 1500000 | 1500000 | 1500000 | CGK |  | 1500000 | 0 |  |  | 1500000 |  |  | oongoing
| Engolili ECDE | Construction of two ECDE classrooms | to increase enrolment | Construction of two ECDE classrooms | 3110200 | construction of buildings | kajiado central | Matapato North |  | education | education | education | 2019-07-01 | 2019-08-01 | 2020-06-01 | 2020-06-01 | 1498720 | 1498720 | 1498720 | CGK |  | 1498720 | 0 |  |  | 1498720 |  |  | Complete
| Noomayai primary | construction of one ECDE classroom | to increase enrolment | construction of one ECDE classroom | 3110200 | construction of buildings | kajiado central | Matapato North |  | education | education | education | 2019-07-01 | 2019-08-01 | 2020-06-01 | 2020-06-01 | 1500000 | 1500000 | 1500000 | CGK |  | 1500000 | 0 |  |  | 1500000 |  |  | on going
| Nalepo Primary ECDE | construction of one ECDE classroom | to increase enrolment | construction of one ECDE classroom | 3110200 | construction of buildings | kajiado central | Matapato North |  | education | education | education | 2019-07-01 | 2019-08-01 | 2020-06-01 | 2020-06-01 | 5998169 | 5998169 | 5998169 | CGK |  | 5998169 | 0 |  |  | 5998169 |  |  | Complete
| Naibala primary | construction of one ECDE classroom | to increase enrolment | construction of one ECDE classroom | 3110200 | construction of buildings | kajiado central | Matapato North |  | education | education | education | 2019-07-01 | 2019-08-01 | 2020-06-01 | 2020-06-01 | 5500000 | 5500000 | 5500000 | CGK |  | 5500000 | 0 |  |  | 5500000 |  |  | Complete
| Mailwa ECDE center at Mailwa primary school | Construction and equipping of ECDE centre | to increase enrolment | Construction and equipping of ECDE centre | 3110200 | construction of buildings | kajiado central | Matapato South |  | education | education | education | 2019-07-01 | 2019-08-01 | 2020-06-01 | 2020-06-01 | 5477140 | 5477140 | 5477140 | CGK |  | 5477140 | 0 |  |  | 5477140 |  |  | Complete
| Embarbal primary school | Construction 3 ECDE classrooms | to increase enrolment | Construction 3 ECDE classrooms | 3110200 | construction of buildings | kajiado west | Mosiro |  | education | education | education | 2019-07-01 | 2019-08-01 | 2020-06-01 | 2020-06-01 | 1000000 | 1000000 | 1000000 | CGK |  | 1000000 | 0 |  |  | 1000000 |  |  | stalled
| Oldepe Primary dormitory | Construction 3 ECDE classrooms | to increase enrolment | Construction 3 ECDE classrooms | 3110200 | construction of buildings | kajiado west | Mosiro |  | education | education | education | 2019-07-01 | 2019-08-01 | 2020-06-01 | 2020-06-01 | 1499068 | 1499068 | 1499068 | CGK |  | 1499068 | 0 |  |  | 1499068 |  |  | Complete
| lebitira Primary School | Construction of one teacher quarter and a toilet | to increase enrolment | Construction of one teacher quarter and a toilet | 3110200 | construction of buildings | kajiado west | Mosiro |  | education | education | education | 2019-07-01 | 2019-08-01 | 2020-06-01 | 2020-06-01 | 2000000 | 2000000 | 2000000 | CGK |  | 2000000 | 0 |  |  | 2000000 |  |  | stalled
| Eiti primary school | Construction of one classroom | to increase enrolment | Construction of one classroom | 3110200 | construction of buildings | kajiado west | Mosiro |  | education | education | education | 2019-07-01 | 2019-08-01 | 2020-06-01 | 2020-06-01 | 1499068 | 1499068 | 1499068 | CGK |  | 1499068 | 0 |  |  | 1499068 |  |  | Complete
| Olokeri Primary school | Construction of 3 teachers houses | to increase enrolment | Construction of 3 teachers houses | 3110200 | construction of buildings | kajiado west | Mosiro |  | education | education | education | 2019-07-01 | 2019-08-01 | 2020-06-01 | 2020-06-01 | 500000 | 500000 | 500000 | CGK |  | 500000 | 0 |  |  | 500000 |  |  | Complete
| Kurja primary school | Construction of ECDE classroom | to increase enrolment | Construction of ECDE classroom | 3110200 | construction of buildings | kajiado west | Mosiro |  | education | education | education | 2019-07-01 | 2019-08-01 | 2020-06-01 | 2020-06-01 | 1500000 | 1500000 | 1500000 | CGK |  | 1500000 | 0 |  |  | 1500000 |  |  | Complete
| Oldorko primary school | purchase of beds | to increase enrolment | purchase of beds | 3110200 | construction of buildings | kajiado west | Mosiro |  | education | education | education | 2019-07-01 | 2019-08-01 | 2020-06-01 | 2020-06-01 | 3000000 | 3000000 | 3000000 | CGK |  | 3000000 | 0 |  |  | 3000000 |  |  | Complete
| Nalepo Primary ECDE | Construction and equipping of 1 ECDE classroom | to increase enrolment | Construction and equipping of 1 ECDE classroom | 3110200 | construction of buildings | kajiado north | Olkeri |  | education | education | education | 2019-07-01 | 2019-08-01 | 2020-06-01 | 2020-06-01 | 3000000 | 3000000 | 3000000 | CGK |  | 3000000 | 0 |  |  | 3000000 |  |  | complete
| Kerarapon pri schhool | Fencing -Brick fence, 600 Meters | to increase enrolment | Fencing -Brick fence, 600 Meters | 3110200 | construction of buildings | kajiado north | Oloolua |  | education | education | education | 2019-07-01 | 2019-08-01 | 2020-06-01 | 2020-06-01 | 1200000 | 1200000 | 1200000 | CGK |  | 1200000 | 0 |  |  | 1200000 |  |  | ongoing
| Embulul community field | Fencing, lighting, tree planting around the field | to increase enrolment | Fencing, lighting, tree planting around the field | 3110200 | construction of buildings | kajiado north | Oloolua |  | education | education | education | 2019-07-01 | 2019-08-01 | 2020-06-01 | 2020-06-01 | 700000 | 700000 | 700000 | CGK |  | 700000 | 0 |  |  | 700000 |  |  | Complete
| Ole kasasi primary school | Construction of special classroom | to increase enrolment | Construction of special classroom | 3110200 | construction of buildings | kajiado north | Ongata Rongai |  | education | education | education | 2019-07-01 | 2019-08-01 | 2020-06-01 | 2020-06-01 | 600000 | 600000 | 600000 | CGK |  | 600000 | 0 |  |  | 600000 |  |  | Complete
| Ole kasasi primary school | construction toilets | to increase enrolment | construction toilets | 3110200 | construction of buildings | kajiado north | Ongata Rongai |  | education | education | education | 2019-07-01 | 2019-08-01 | 2020-06-01 | 2020-06-01 | 500000 | 500000 | 500000 | CGK |  | 500000 | 0 |  |  | 500000 |  |  | Complete
| Ole kasasi primary school | purchase of desks | to increase enrolment | purchase of desks | 3110200 | construction of buildings | kajiado north | Ongata Rongai |  | education | education | education | 2019-07-01 | 2019-08-01 | 2020-06-01 | 2020-06-01 | 1500000 | 1500000 | 1500000 | CGK |  | 1500000 | 0 |  |  | 1500000 |  |  | Complete
| ole pasha ECDE | Purchase of play equipment (swings) | to increase enrolment | Purchase of play equipment (swings) | 3110200 | construction of buildings | kajiado north | Ongata Rongai |  | education | education | education | 2019-07-01 | 2019-08-01 | 2020-06-01 | 2020-06-01 | 4000000 | 4000000 | 4000000 | CGK |  | 4000000 | 0 |  |  | 4000000 |  |  | Complete
| ole pasha ECDE | construction of kitchan and purchase of kitchen ware | to increase enrolment | construction of kitchan and purchase of kitchen ware | 3110200 | construction of buildings | kajiado north | Ongata Rongai |  | education | education | education | 2019-07-01 | 2019-08-01 | 2020-06-01 | 2020-06-01 | 3000000 | 3000000 | 3000000 | CGK |  | 3000000 | 0 |  |  | 3000000 |  |  | Complete
| ole Kasasi secondary school | construction of 2No classrom and fence | to increase enrolment | construction of 2No classrom and fence | 3110200 | construction of buildings | kajiado north | Ongata Rongai |  | education | education | education | 2019-07-01 | 2019-08-01 | 2020-06-01 | 2020-06-01 | 3000000 | 3000000 | 3000000 | CGK |  | 3000000 | 0 |  |  | 3000000 |  |  | Complete
| Nkasakinoi ECDE | Construction of 2 ECDE classes at Nkasakinoi | to increase enrolment | Construction of 2 ECDE classes at Nkasakinoi | 3110200 | construction of buildings | kajiado south | Rombo |  | education | education | education | 2019-07-01 | 2019-08-01 | 2020-06-01 | 2020-06-01 | 1500000 | 1500000 | 1500000 | CGK |  | 1500000 | 0 |  |  | 1500000 |  |  | stalled
| Olbak ECDE | Construction of two ECDE classrooms | to increase enrolment | Construction of two ECDE classrooms | 3110200 | construction of buildings | kajiado south | Rombo |  | education | education | education | 2019-07-01 | 2019-08-01 | 2020-06-01 | 2020-06-01 | 1500000 | 1500000 | 1500000 | CGK |  | 1500000 | 0 |  |  | 1500000 |  |  | Complete
| Nakeel pri school | Construction of one ECDE classroom | to increase enrolment | Construction of one ECDE classroom | 3110200 | construction of buildings | kajiado north | Nkaimurunya |  | education | education | education | 2019-07-01 | 2019-08-01 | 2020-06-01 | 2020-06-01 | 1500000 | 1500000 | 1500000 | CGK |  | 1500000 | 0 |  |  | 1500000 |  |  | Complete
| Ongata Rongai pri school | Construction of one ECDE classroom | to increase enrolment | Construction of one ECDE classroom | 3110200 | construction of buildings | kajiado north | Nkaimurunya |  | education | education | education | 2019-07-01 | 2019-08-01 | 2020-06-01 | 2020-06-01 | 2000000 | 2000000 | 2000000 | CGK |  | 2000000 | 0 |  |  | 2000000 |  |  | Complete
| Nkaimurunya pri school | Construction of one ECDE classroom | to increase enrolment | Construction of one ECDE classroom | 3110200 | construction of buildings | kajiado north | Nkaimurunya |  | education | education | education | 2019-07-01 | 2019-08-01 | 2020-06-01 | 2020-06-01 | 400000 | 400000 | 400000 | CGK |  | 400000 | 0 |  |  | 400000 |  |  | Complete
| Nkaimurunya pri school | Levelling of playing field and filling with redsoil | to increase enrolment | Levelling of playing field and filling with redsoil | 3110200 | construction of buildings | kajiado north | Nkaimurunya |  | education | education | education | 2019-07-01 | 2019-08-01 | 2020-06-01 | 2020-06-01 | 400000 | 400000 | 400000 | CGK |  | 400000 | 0 |  |  | 400000 |  |  | Complete
| Nakeel pri school | Purchase of ECDE play equipment | to increase enrolment | Purchase of ECDE play equipment | 3110200 | construction of buildings | kajiado north | Nkaimurunya |  | education | education | education | 2019-07-01 | 2019-08-01 | 2020-06-01 | 2020-06-01 | 400000 | 400000 | 400000 | CGK |  | 400000 | 0 |  |  | 400000 |  |  | Complete
| Ongata Rongai pri school | Purchase of ECDE play equipment | to increase enrolment | Purchase of ECDE play equipment | 3110200 | construction of buildings | kajiado north | Nkaimurunya |  | education | education | education | 2019-07-01 | 2019-08-01 | 2020-06-01 | 2020-06-01 | 1499346 | 1499346 | 1499346 | CGK |  | 1499346 | 0 |  |  | 1499346 |  |  | Complete
| Nkaimurunya pri school | Purchase of ECDE play equipment | to increase enrolment | Purchase of ECDE play equipment | 3110200 | construction of buildings | kajiado north | Nkaimurunya |  | education | education | education | 2019-07-01 | 2019-08-01 | 2020-06-01 | 2020-06-01 | 2992463 | 2992463 | 2992463 | CGK |  | 2992463 | 0 |  |  | 2992463 |  |  | Complete
| Naserian ECDE | Construction of one ECDE classroom | to increase enrolment | Construction of one ECDE classroom | 3110200 | construction of buildings | kajiado east | Kenyewa/Poka |  | education | education | education | 2019-07-01 | 2019-08-01 | 2020-06-01 | 2020-06-01 | 2999950 | 2999950 | 2999950 | CGK |  | 2999950 | 0 |  |  | 2999950 |  |  | Complete
| Kitengela Primary | Construction of dormitory | to increase enrolment | Construction of dormitory | 3110200 | construction of buildings | kajiado east | Oloosirkon/Sholinke |  | education | education | education | 2019-07-01 | 2019-08-01 | 2020-06-01 | 2020-06-01
| Oloika Primary | Construction of 2 No classroom at Oloika | to increase enrolment | Construction of 2 No classroom at Oloika | 3110200 | construction of buildings | kajiado east | Oloosirkon/Sholinke |  | education | education | education | 2019-07-01 | 2019-08-01 | 2020-06-01 | 2020-06-01 | 5000000 | 5000000 | 5000000 | CGK |  | 5000000 | 0 |  |  | 5000000 |  |  | ongoing
[17 empty] | 3000000 | 3000000 | 3000000 | CGK |  | 3000000 | 0 |  |  | 3000000 |  |  | Complete
| Collins Davies | Construction of Collins Davies Lab | to increase enrolment | Construction of Collins Davies Lab | 3110202 | construction of buildings | kajiado south | Rombo |  | education | education | education | 2022-07-01 | 2022-08-01 | 2023-06-01 | 2023-06-01 | 2000000 | 2000000 | 2000000 | CGK |  | 2000000 | 0 |  |  | 2000000 |  |  | Complete
| Amboseli primary school | Construction of 3 ECDE classrooms | to increase enrolment | Construction of 3 ECDE classrooms | 3110202 | construction of buildings | kajiado south | Entonet/Lenkism |  | education | education | education | 2022-07-01 | 2022-08-01 | 2023-06-01 | 2023-06-01 | 4000000 | 4000000 | 4000000 | CGK |  | 4000000 | 0 |  |  | 4000000 |  |  | Complete
| Risa teachers quarters | Construction of teachers quarters | to increase enrolment | Construction of teachers quarters | 3110202 | construction of buildings | kajiado south | Entonet/Lenkism |  | education | education | education | 2022-07-01 | 2022-08-01 | 2023-06-01 | 2023-06-01 | 5000000 | 5000000 | 5000000 | CGK |  | 5000000 | 0 |  |  | 5000000 |  |  | Complete
| Olchoro Secondary | Construction of 2 classrooms | to increase enrolment | Construction of 2 classrooms | 3110202 | construction of buildings | kajiado south | Entonet/Lenkism |  | education | education | education | 2022-07-01 | 2022-08-01 | 2023-06-01 | 2023-06-01 | 3000000 | 3000000 | 3000000 | CGK |  | 3000000 | 0 |  |  | 3000000 |  |  | Complete
| Osero Onyokie Dormitory | Complition of a Boarding Facility | to increase enrolment | Complition of a Boarding Facility | 3110202 | construction of buildings | kajiado west | Ewuaso Oonkidongi |  | education | education | education | 2022-07-01 | 2022-08-01 | 2023-06-01 | 2023-06-01 | 3000000 | 3000000 | 3000000 | CGK |  | 3000000 | 0 |  |  | 3000000 |  |  | Complete
| Tariki ECDE | Construction of two classrooms | to increase enrolment | Construction of two classrooms | 3110202 | construction of buildings | kajiado west | Ewuaso Oonkidongi |  | education | education | education | 2022-07-01 | 2022-08-01 | 2023-06-01 | 2023-06-01 | 3000000 | 3000000 | 3000000 | CGK |  | 3000000 | 0 |  |  | 3000000 |  |  | Complete
| Enajoole ECDE | Construction of two classrooms | to increase enrolment | Construction of two classrooms | 3110202 | construction of buildings | kajiado west | Ewuaso Oonkidongi |  | education | education | education | 2022-07-01 | 2022-08-01 | 2023-06-01 | 2023-06-01 | 3000000 | 3000000 | 3000000 | CGK |  | 3000000 | 0 |  |  | 3000000 |  |  | Complete
| Sairashie ECDE | Construction of two classrooms | to increase enrolment | Construction of two classrooms | 3110202 | construction of buildings | kajiado west | Ewuaso Oonkidongi |  | education | education | education | 2022-07-01 | 2022-08-01 | 2023-06-01 | 2023-06-01 | 3000000 | 3000000 | 3000000 | CGK |  | 3000000 | 0 |  |  | 3000000 |  |  | Complete
| Ilparakuo ECDE | Construction of two classrooms | to increase enrolment | Construction of two classrooms | 3110202 | construction of buildings | kajiado west | Ewuaso Oonkidongi |  | education | education | education | 2022-07-01 | 2022-08-01 | 2023-06-01 | 2023-06-01 | 1500000 | 1500000 | 1500000 | CGK |  | 1500000 | 0 |  |  | 1500000 |  |  | Complete
| Osupuko ECDE | Construction of two classrooms | to increase enrolment | Construction of two classrooms | 3110202 | construction of buildings | kajiado west | Ewuaso Oonkidongi |  | education | education | education | 2022-07-01 | 2022-08-01 | 2023-06-01 | 2023-06-01 | 1500000 | 1500000 | 1500000 | CGK |  | 1500000 | 0 |  |  | 1500000 |  |  | Complete
| Mpirishi ECDE | Construction of classrooms | to increase enrolment | Construction of classrooms | 3110202 | construction of buildings | kajiado west | Ewuaso Oonkidongi |  | education | education | education | 2022-07-01 | 2022-08-01 | 2023-06-01 | 2023-06-01 | 7000000 | 7000000 | 7000000 | CGK |  | 7000000 | 0 |  |  | 7000000 |  |  | ongoing
| Seventh Day Olgumi | Construction of one class room | to increase enrolment | Construction of one class room | 3110202 | construction of buildings | kajiado west | Ewuaso Oonkidongi |  | education | education | education | 2022-07-01 | 2022-08-01 | 2023-06-01 | 2023-06-01 | 3000000 | 3000000 | 3000000 | CGK |  | 3000000 | 0 |  |  | 3000000 |  |  | ongoing
| Ildamat Boys | Construction of a domitory | to increase enrolment | Construction of a domitory | 3110202 | construction of buildings | kajiado central | Ildamat |  | education | education | education | 2022-07-01 | 2022-08-01 | 2023-06-01 | 2023-06-01 | 3000000 | 3000000 | 3000000 | CGK |  | 3000000 | 0 |  |  | 3000000 |  |  | Complete
| Ildamat Boys | Construction of teachers quarters | to increase enrolment | Construction of teachers quarters | 3110202 | construction of buildings | kajiado central | Ildamat |  | education | education | education | 2022-07-01 | 2022-08-01 | 2023-06-01 | 2023-06-01 | 1500000 | 1500000 | 1500000 | CGK |  | 1500000 | 0 |  |  | 1500000 |  |  | ongoing
| Oltaraja ECDE | Construction of shool Fence | to increase enrolment | Construction of shool Fence | 3110202 | construction of buildings | kajiado central | Ildamat |  | education | education | education | 2022-07-01 | 2022-08-01 | 2023-06-01 | 2023-06-01 | 2000000 | 2000000 | 2000000 | CGK |  | 2000000 | 0 |  |  | 2000000 |  |  | Complete
| Oloilalei Pry ECDE | Construction of toilets | to increase enrolment | Construction of toilets | 3110202 | construction of buildings | kajiado central | Ildamat |  | education | education | education | 2022-07-01 | 2022-08-01 | 2023-06-01 | 2023-06-01 | 3000000 | 3000000 | 3000000 | CGK |  | 3000000 | 0 |  |  | 3000000 |  |  | Complete
| Senior Chief Risa Sec Sch | Completion of domitory | to increase enrolment | Completion of domitory | 3110202 | construction of buildings | kajiado central | Ildamat |  | education | education | education | 2022-07-01 | 2022-08-01 | 2023-06-01 | 2023-06-01 | 5000000 | 5000000 | 5000000 | CGK |  | 5000000 | 0 |  |  | 5000000 |  |  | ongoing
| Oloserian Pri sch, | Construction of two classes | to increase enrolment | Construction of two classes | 3110202 | construction of buildings | kajiado west | Ilkeekonyokie |  | education | education | education | 2022-07-01 | 2022-08-01 | 2023-06-01 | 2023-06-01 | 1000000 | 1000000 | 1000000 | CGK |  | 1000000 | 0 |  |  | 1000000 |  |  | Complete
| Nkarusa ECDE | Purchase of Land | to increase enrolment | Purchase of Land | 3110202 | construction of buildings | kajiado west | Ilkeekonyokie |  | education | education | education | 2022-07-01 | 2022-08-01 | 2023-06-01 | 2023-06-01 | 2000000 | 2000000 | 2000000 | CGK |  | 2000000 | 0 |  |  | 2000000 |  |  | ongoing
| Olomayiana ECDE | Rehabilitation and repair of toilets | to increase enrolment | Rehabilitation and repair of toilets | 3110202 | construction of buildings | kajiado west | Ilkeekonyokie |  | education | education | education | 2022-07-01 | 2022-08-01 | 2023-06-01 | 2023-06-01 | 3000000 | 3000000 | 3000000 | CGK |  | 3000000 | 0 |  |  | 3000000 |  |  | ongoing
| Enkoilalei ECDE | Construction of ECDE class room | to increase enrolment | Construction of ECDE class room | 3110202 | construction of buildings | kajiado west | Mosiro |  | education | education | education | 2022-07-01 | 2022-08-01 | 2023-06-01 | 2023-06-01 | 3000000 | 3000000 | 3000000 | CGK |  | 3000000 | 0 |  |  | 3000000 |  |  | Complete
| Embarabal Primary School Staff houses | Construction of 3 staff houses | to increase enrolment | Construction of 3 staff houses | 3110202 | construction of buildings | kajiado west | Mosiro |  | education | education | education | 2022-07-01 | 2022-08-01 | 2023-06-01 | 2023-06-01 | 1700000 | 1700000 | 1700000 | CGK |  | 1700000 | 0 |  |  | 1700000 |  |  | Complete
| Oldepe pry Sch Staff houses | Construction of 3 staff houses | to increase enrolment | Construction of 3 staff houses | 3110202 | construction of buildings | kajiado west | Mosiro |  | education | education | education | 2022-07-01 | 2022-08-01 | 2023-06-01 | 2023-06-01 | 1700000 | 1700000 | 1700000 | CGK |  | 1700000 | 0 |  |  | 1700000 |  |  | Complete
| Oldorko ECDE | Construction ECDE classroom | to increase enrolment | Construction ECDE classroom | 3110202 | construction of buildings | kajiado west | Magadi |  | education | education | education | 2022-07-01 | 2022-08-01 | 2023-06-01 | 2023-06-01 | 1700000 | 1700000 | 1700000 | CGK |  | 1700000 | 0 |  |  | 1700000 |  |  | Complete
| Komiti ECDE | Construction ECDE classroom | to increase enrolment | Construction ECDE classroom | 3110202 | construction of buildings | kajiado west | Magadi |  | education | education | education | 2022-07-01 | 2022-08-01 | 2023-06-01 | 2023-06-01 | 700000 | 700000 | 700000 | CGK |  | 700000 | 0 |  |  | 700000 |  |  | Complete
| Oloibortototo Sec | Construction of Classroom | to increase enrolment | Construction of Classroom | 3110202 | construction of buildings | kajiado west | Magadi |  | education | education | education | 2022-07-01 | 2022-08-01 | 2023-06-01 | 2023-06-01 | 1700000 | 1700000 | 1700000 | CGK |  | 1700000 | 0 |  |  | 1700000 |  |  | Complete
| Oloibortototo pri. Desks | Purchase of desks | to increase enrolment | Purchase of desks | 3110202 | construction of buildings | kajiado west | Magadi |  | education | education | education | 2022-07-01 | 2022-08-01 | 2023-06-01 | 2023-06-01 | 1000000 | 1000000 | 1000000 | CGK |  | 1000000 | 0 |  |  | 1000000 |  |  | Complete
| Ololepo ECDE | Construction ECDE classroom | to increase enrolment | Construction ECDE classroom | 3110202 | construction of buildings | kajiado west | Magadi |  | education | education | education | 2022-07-01 | 2022-08-01 | 2023-06-01 | 2023-06-01 | 1700000 | 1700000 | 1700000 | CGK |  | 1700000 | 0 |  |  | 1700000 |  |  | Complete
| Entaamo ECDE | Purchase of desks | to increase enrolment | Purchase of desks | 3110202 | construction of buildings | kajiado west | Magadi |  | education | education | education | 2022-07-01 | 2022-08-01 | 2023-06-01 | 2023-06-01 | 2600000 | 2600000 | 2600000 | CGK |  | 2600000 | 0 |  |  | 2600000 |  |  | Complete
| Naserian ECDE | Construction of ECDE class room | to increase enrolment | Construction of ECDE class room | 3110202 | construction of buildings | kajiado west | Magadi |  | education | education | education | 2022-07-01 | 2022-08-01 | 2023-06-01 | 2023-06-01 | 1700000 | 1700000 | 1700000 | CGK |  | 1700000 | 0 |  |  | 1700000 |  |  | Complete
| Losinyai Teachers quarters | Construction of teachers quarters | to increase enrolment | Construction of teachers quarters | 3110202 | construction of buildings | kajiado west | Magadi |  | education | education | education | 2022-07-01 | 2022-08-01 | 2023-06-01 | 2023-06-01 | 3000000 | 3000000 | 3000000 | CGK |  | 3000000 | 0 |  |  | 3000000 |  |  | ongoing
| Losinyai ECDE | Construction of ECDE class room | to increase enrolment | Construction of ECDE class room | 3110202 | construction of buildings | kajiado west | Magadi |  | education | education | education | 2022-07-01 | 2022-08-01 | 2023-06-01 | 2023-06-01 | 3000000 | 3000000 | 3000000 | CGK |  | 3000000 | 0 |  |  | 3000000 |  |  | Complete
| Nkariarokena ECDE | Construction and equipping of 2classes | to increase enrolment | Construction and equipping of 2classes | 3110202 | construction of buildings | kajiado south | Kimana |  | education | education | education | 2022-07-01 | 2022-08-01 | 2023-06-01 | 2023-06-01 | 3000000 | 3000000 | 3000000 | CGK |  | 3000000 | 0 |  |  | 3000000 |  |  | Complete
| Olorika Primary School Fencing | Fencing of school with Chainlink wire | to increase enrolment | Fencing of school with Chainlink wire | 3110202 | construction of buildings | kajiado south | kuku |  | education | education | education | 2022-07-01 | 2022-08-01 | 2023-06-01 | 2023-06-01 | 3000000 | 3000000 | 3000000 | CGK |  | 3000000 | 0 |  |  | 3000000 |  |  | Complete
| Shurie Primary School | Construction of Two Classes | to increase enrolment | Construction of Two Classes | 3110202 | construction of buildings | kajiado south | Kuku |  | education | education | education | 2022-07-01 | 2022-08-01 | 2023-06-01 | 2023-06-01 | 2000000 | 2000000 | 2000000 | CGK |  | 2000000 | 0 |  |  | 2000000 |  |  | Complete
| Losoitok Primary School | Construction of Two Classes | to increase enrolment | Construction of Two Classes | 3110202 | construction of buildings | kajiado south | Kuku |  | education | education | education | 2022-07-01 | 2022-08-01 | 2023-06-01 | 2023-06-01 | 6000000 | 6000000 | 6000000 | CGK |  | 6000000 | 0 |  |  | 6000000 |  |  | ongoing
| Lekatote ECDE | Construction of Classroom and toilet | to increase enrolment | Construction of Classroom and toilet | 3110202 | construction of buildings | kajiado south | Kuku |  | education | education | education | 2022-07-01 | 2022-08-01 | 2023-06-01 | 2023-06-01 | 6000000 | 6000000 | 6000000 | CGK |  | 6000000 | 0 |  |  | 6000000 |  |  | ongoing
| Endoinyio Ewuas ECDE | Construction of an ECDE centre | to increase enrolment | Construction of an ECDE centre | 3110202 | construction of buildings | kajiado central | Matapato North |  | education | education | education | 2022-07-01 | 2022-08-01 | 2023-06-01 | 2023-06-01 | 4000000 | 4000000 | 4000000 | CGK |  | 4000000 | 0 |  |  | 4000000 |  |  | Complete
| Intinyika ECDE | Construction of an ECDE centre | to increase enrolment | Construction of an ECDE centre | 3110202 | construction of buildings | kajiado central | Matapato North |  | education | education | education | 2022-07-01 | 2022-08-01 | 2023-06-01 | 2023-06-01 | 1500000 | 1500000 | 1500000 | CGK |  | 1500000 | 0 |  |  | 1500000 |  |  | Complete
| Oloika Primary | Construction of school fence | to increase enrolment | Construction of school fence | 3110202 | construction of buildings | kajiado central | Matapato North |  | education | education | education | 2022-07-01 | 2022-08-01 | 2023-06-01 | 2023-06-01 | 4000000 | 4000000 | 4000000 | CGK |  | 4000000 | 0 |  |  | 4000000 |  |  | ongoing
| Enoo Sampurumpur ECDE | Construction of ECDE class room | to increase enrolment | Construction of ECDE class room | 3110202 | construction of buildings | kajiado central | Matapato South |  | education | education | education | 2022-07-01 | 2022-08-01 | 2023-06-01 | 2023-06-01 | 2000000 | 2000000 | 2000000 | CGK |  | 2000000 | 0 |  |  | 2000000 |  |  | ongoing
| Nkiurunya Primary | Constrruction of 2 ECDE classrooms | to increase enrolment | Constrruction of 2 ECDE classrooms | 3110202 | construction of buildings | kajiado north | Nkaimurunya |  | education | education | education | 2022-07-01 | 2022-08-01 | 2023-06-01 | 2023-06-01 | 2000000 | 2000000 | 2000000 | CGK |  | 2000000 | 0 |  |  | 2000000 |  |  | ongoing
| Nakeel Primary School | Construction of one class room | to increase enrolment | Construction of one class room | 3110202 | construction of buildings | kajiado north | Nkaimurunya |  | education | education | education | 2022-07-01 | 2022-08-01 | 2023-06-01 | 2023-06-01 | 7000000 | 7000000 | 7000000 | CGK |  | 7000000 | 0 |  |  | 7000000 |  |  | ongoing
| Rongai Primary School | Construction of one class room | to increase enrolment | Construction of one class room | 3110202 | construction of buildings | kajiado north | Nkaimurunya |  | education | education | education | 2022-07-01 | 2022-08-01 | 2023-06-01 | 2023-06-01 | 2000000 | 2000000 | 2000000 | CGK |  | 2000000 | 0 |  |  | 2000000 |  |  | Complete
| Purchase of Land | Purchase of School Land | to increase enrolment | Purchase of School Land | 3110202 | construction of buildings | kajiado north | Oloolua |  | education | education | education | 2022-07-01 | 2022-08-01 | 2023-06-01 | 2023-06-01 | 3000000 | 3000000 | 3000000 | CGK |  | 3000000 | 0 |  |  | 3000000 |  |  | Complete
| Enkaroni ECDE | Completion (Finshing works) ecde centre and staff house | to increase enrolment | Completion (Finshing works) ecde centre and staff house | 3110202 | construction of buildings | kajiado central | Purko |  | education | education | education | 2022-07-01 | 2022-08-01 | 2023-06-01 | 2023-06-01 | 2000000 | 2000000 | 2000000 | CGK |  | 2000000 | 0 |  |  | 2000000 |  |  | Complete
| Munyura ECDE | Construction of 2 classes | to increase enrolment | Construction of 2 classes | 3110202 | construction of buildings | kajiado south | Rombo |  | education | education | education | 2022-07-01 | 2022-08-01 | 2023-06-01 | 2023-06-01 | 3000000 | 3000000 | 3000000 | CGK |  | 3000000 | 0 |  |  | 3000000 |  |  | Complete
| Matepes ECDE | Fencing | to increase enrolment | Fencing | 3110202 | construction of buildings | kajiado south | Rombo |  | education | education | education | 2022-07-01 | 2022-08-01 | 2023-06-01 | 2023-06-01 | 3000000 | 3000000 | 3000000 | CGK |  | 3000000 | 0 |  |  | 3000000 |  |  | Complete
| Lemongo ECDE | Construction of 2 classes | to increase enrolment | Construction of 2 classes | 3110202 | construction of buildings | kajiado south | Rombo |  | education | education | education | 2022-07-01 | 2022-08-01 | 2023-06-01 | 2023-06-01 | 6000000 | 6000000 | 6000000 | CGK |  | 6000000 | 0 |  |  | 6000000 |  |  | Complete
| Nasipa ECDE | Construction of 2 classes | to increase enrolment | Construction of 2 classes | 3110202 | construction of buildings | kajiado south | Rombo |  | education | education | education | 2022-07-01 | 2022-08-01 | 2023-06-01 | 2023-06-01 | 4000000 | 4000000 | 4000000 | CGK |  | 4000000 | 0 |  |  | 4000000 |  |  | Complete
| Dr.Likimani Pri | Construction of four Classes | to increase enrolment | Construction of four Classes | 3110202 | construction of buildings | kajiado east | Kitengela |  | education | education | education | 2022-07-01 | 2022-08-01 | 2023-06-01 | 2023-06-01 | 3000000 | 3000000 | 3000000 | CGK |  | 3000000 | 0 |  |  | 3000000 |  |  | Complete
| Railways / Ole Mpuya ECDE | Construction of two Classes | to increase enrolment | Construction of two Classes | 3110202 | construction of buildings | kajiado east | Oloosirkon/Sholinke |  | education | education | education | 2022-07-01 | 2022-08-01 | 2023-06-01 | 2023-06-01 | 2000000 | 2000000 | 2000000 | CGK |  | 2000000 | 0 |  |  | 2000000 |  |  | ongoing
| Saina Primary | Construction of two classes | to increase enrolment | Construction of two classes | 3110202 | construction of buildings | kajiado central | Dalalekutuk |  | education | education | education | 2022-07-01 | 2022-08-01 | 2023-06-01 | 2023-06-01 | 2000000 | 2000000 | 2000000 | CGK |  | 2000000 | 0 |  |  | 2000000 |  |  | Complete
| Orinie Primary | Construction of staff quarters | to increase enrolment | Construction of staff quarters | 3110202 | construction of buildings | kajiado central | Dalalekutuk |  | education | education | education | 2022-07-01 | 2022-08-01 | 2023-06-01 | 2023-06-01 | 4000000 | 4000000 | 4000000 | CGK |  | 4000000 | 0 |  |  | 4000000 |  |  | Complete
| Olpolosie Primary | Construction of staff quarters | to increase enrolment | Construction of staff quarters | 3110202 | construction of buildings | kajiado central | Dalalekutuk |  | education | education | education | 2022-07-01 | 2022-08-01 | 2023-06-01 | 2023-06-01 | 2000000 | 2000000 | 2000000 | CGK |  | 2000000 | 0 |  |  | 2000000 |  |  | Complete
| Nkuseron pri | Fencing and Construction of Toilets | to increase enrolment | Fencing and Construction of Toilets | 3110202 | construction of buildings | kajiado central | Dalalekutuk |  | education | education | education | 2022-07-01 | 2022-08-01 | 2023-06-01 | 2023-06-01 | 4000000 | 4000000 | 4000000 | CGK |  | 4000000 | 0 |  |  | 4000000 |  |  | Complete
| Enyonyor Pri Staff Quarters | Construction of staff quarters | to increase enrolment | Construction of staff quarters | 3110202 | construction of buildings | kajiado central | Dalalekutuk |  | education | education | education | 2022-07-01 | 2022-08-01 | 2023-06-01 | 2023-06-01 | 4000000 | 4000000 | 4000000 | CGK |  | 4000000 | 0 |  |  | 4000000 |  |  | Complete
| Enkasurayi Pri. Fencing | School Fencing and Construction of toilets | to increase enrolment | School Fencing and Construction of toilets | 3110202 | construction of buildings | kajiado central | Dalalekutuk |  | education | education | education | 2022-07-01 | 2022-08-01 | 2023-06-01 | 2023-06-01 | 3000000 | 3000000 | 3000000 | CGK |  | 3000000 | 0 |  |  | 3000000 |  |  | ongoing
| Paranae Kiserian ECDE | Construction of two classes | to increase enrolment | Construction of two classes | 3110202 | construction of buildings | kajiado south | Imbirikani |  | education | education | education | 2022-07-01 | 2022-08-01 | 2023-06-01 | 2023-06-01 | 3000000 | 3000000 | 3000000 | CGK |  | 3000000 | 0 |  |  | 3000000 |  |  | Complete
| Oldonyio Wuas Ecde | Construction of two classes | to increase enrolment | Construction of two classes | 3110202 | construction of buildings | kajiado south | Imbirikani |  | education | education | education | 2022-07-01 | 2022-08-01 | 2023-06-01 | 2023-06-01 | 7000000 | 7000000 | 7000000 | CGK |  | 7000000 | 0 |  |  | 7000000 |  |  | ongoing
| Ilngosuani ECDE | Construction of 2 cassrooms | to increase enrolment | Construction of 2 cassrooms | 3110202 | construction of buildings | kajiado south | Imbirikani |  | education | education | education | 2022-07-01 | 2022-08-01 | 2023-06-01 | 2023-06-01 | 4000000 | 4000000 | 4000000 | CGK |  | 4000000 | 0 |  |  | 4000000 |  |  | Complete
| Singiraine Pri, Sch | Construction of staff Quarters | to increase enrolment | Construction of staff Quarters | 3110202 | construction of buildings | kajiado west | Iloodokilan |  | education | education | education | 2022-07-01 | 2022-08-01 | 2023-06-01 | 2023-06-01 | 4000000 | 4000000 | 4000000 | CGK |  | 4000000 | 0 |  |  | 4000000 |  |  | ongoing
| Enchoro Esenteu Ecde | Construction of two classes | to increase enrolment | Construction of two classes | 3110202 | construction of buildings | kajiado west | Iloodokilan |  | education | education | education | 2022-07-01 | 2022-08-01 | 2023-06-01 | 2023-06-01 | 2000000 | 2000000 | 2000000 | CGK |  | 2000000 | 0 |  |  | 2000000 |  |  | Complete
| Rroya Ecde | Construction of two classes | to increase enrolment | Construction of two classes | 3110202 | construction of buildings | kajiado west | Iloodokilan |  | education | education | education | 2022-07-01 | 2022-08-01 | 2023-06-01 | 2023-06-01 | 700000 | 700000 | 700000 | CGK |  | 700000 | 0 |  |  | 700000 |  |  | Complete
| Ngong township Primary Toilets | Construction of abolution | to increase enrolment | Construction of abolution | 3110202 | construction of buildings | kajiado north | Ngong |  | education | education | education | 2022-07-01 | 2022-08-01 | 2023-06-01 | 2023-06-01 | 2500000 | 2500000 | 2500000 | CGK |  | 2500000 | 0 |  |  | 2500000 |  |  | ongoing
| Ngong stadium | Grading, leveling, installation of stadium benches | to increase enrolment | Grading, leveling, installation of stadium benches | 3110202 | construction of buildings | kajiado north | Ngong |  | education | education | education | 2022-07-01 | 2022-08-01 | 2023-06-01 | 2023-06-01 | 4000000 | 4000000 | 4000000 | CGK |  | 4000000 | 0 |  |  | 4000000 |  |  | ongoing
| ECD DAM | Grading and leveling of ground | to increase enrolment | Grading and leveling of ground | 3110202 | construction of buildings | kajiado north | Olkeri |  | education
| Bul bul stadium | Constrution of a perimeter wall | to enhance security | Constrution of a perimeter wall | 3110202 | construction of buildings | kajiado north | Oloolua |  | education | education | education | 2023-07-01 | 2023-08-01 | 2024-06-01 | 2024-06-01 | 2000000 | 2000000 | 2000000 | CGK |  | 2000000 | 0 |  |  | 2000000 |  |  | ongoing
[11 empty] | education | education | 2023-07-01 | 2023-08-01 | 2024-06-01 | 2024-06-01 | 1500000 | 1500000 | 1500000 | CGK |  | 1500000 | 0 |  |  | 1500000 |  |  | Not started
| Leboo ECDE | Finishing & equipping | increase enronment | Finishing & equipping | 3110200 | construction of buildings | Kajiado Central | Matapato South |  | education | education | education | 2023-07-01 | 2023-08-01 | 2024-06-01 | 2024-06-01 | 1000000 | 1000000 | 1000000 | CGK |  | 1000000 | 0 |  |  | 1000000 |  |  | Not started
| Oloirimirimi Pri school | Constuction of one ECDE class | increase enronment | Constuction of one ECDE class | 3110200 | construction of buildings | Kajiado Central | Matapato South |  | education | education | education | 2023-07-01 | 2023-08-01 | 2024-06-01 | 2024-06-01 | 1000000 | 1000000 | 1000000 | CGK |  | 1000000 | 0 |  |  | 1000000 |  |  | complete
| Oldonyo Sambu pri school | Completion of Admin Block | increase enronment | Completion of Admin Block | 3110200 | construction of buildings | Kajiado Central | Matapato South |  | education | education | education | 2023-07-01 | 2023-08-01 | 2024-06-01 | 2024-06-01 | 1500000 | 1500000 | 1500000 | CGK |  | 1500000 | 0 |  |  | 1500000 |  |  | Not started
| Enkoilele Pry School | Completion and equipping of 1No. ECDE classroom | increase enronment | Completion and equipping of 1No. ECDE classroom | 3110200 | construction of buildings | Kajiado Central | Matapato North |  | education | education | education | 2023-07-01 | 2023-08-01 | 2024-06-01 | 2024-06-01 | 1500000 | 1500000 | 1500000 | CGK |  | 1500000 | 0 |  |  | 1500000 |  |  | Not started
| Ilmotiok Pry School | Construction of ECDE 1 no. Class | increase enronment | Construction of ECDE 1 no. Class | 3110200 | construction of buildings | Kajiado Central | Matapato North |  | education | education | education | 2023-07-01 | 2023-08-01 | 2024-06-01 | 2024-06-01 | 1500000 | 1500000 | 1500000 | CGK |  | 1500000 | 0 |  |  | 1500000 |  |  | Not started
| Ilmisigyo Pry School | Construction of ECDE 1 no. Class | increase enronment | Construction of ECDE 1 no. Class | 3110200 | construction of buildings | Kajiado Central | Matapato North |  | education | education | education | 2023-07-01 | 2023-08-01 | 2024-06-01 | 2024-06-01 | 1500000 | 1500000 | 1500000 | CGK |  | 1500000 | 0 |  |  | 1500000 |  |  | Not started
| Lenkishon Pry School | Construction of ECDE 1 no. Class | increase enronment | Construction of ECDE 1 no. Class | 3110200 | construction of buildings | Kajiado Central | Matapato North |  | education | education | education | 2023-07-01 | 2023-08-01 | 2024-06-01 | 2024-06-01 | 3000000 | 3000000 | 3000000 | CGK |  | 3000000 | 0 |  |  | 3000000 |  |  | ongoing
| Lositeti ECDE | Construction of ECDE 1 no. Class | increase enronment | Construction of ECDE 1 no. Class | 3110200 | construction of buildings | Kajiado Central | Matapato North |  | education | education | education | 2023-07-01 | 2023-08-01 | 2024-06-01 | 2024-06-01 | 1500000 | 1500000 | 1500000 | CGK |  | 1500000 | 0 |  |  | 1500000 |  |  | complete
| Chief Muturi ECDE | Construction of two ECDE Classroom | increase enronment | Construction of two ECDE Classroom | 3110200 | construction of buildings | Kajiado South | Kuku |  | education | education | education | 2023-07-01 | 2023-08-01 | 2024-06-01 | 2024-06-01 | 3000000 | 3000000 | 3000000 | CGK |  | 3000000 | 0 |  |  | 3000000 |  |  | ongoing
| Olkaria ECDE | Construction of one ECDE Classroom | increase enronment | Construction of one ECDE Classroom | 3110200 | construction of buildings | Kajiado South | Kuku |  | education | education | education | 2023-07-01 | 2023-08-01 | 2024-06-01 | 2024-06-01 | 3000000 | 3000000 | 3000000 | CGK |  | 3000000 | 0 |  |  | 3000000 |  |  | Not started
| Lemongo ECDE | Construction of two ECDE Classroom | increase enronment | Construction of two ECDE Classroom | 3110200 | construction of buildings | Kajiado South | Kimana |  | education | education | education | 2023-07-01 | 2023-08-01 | 2024-06-01 | 2024-06-01 | 3000000 | 3000000 | 3000000 | CGK |  | 3000000 | 0 |  |  | 3000000 |  |  | ongoing
| Inklsuk primary school | Construction of two ECDE Classroom | increase enronment | Construction of two ECDE Classroom | 3110200 | construction of buildings | Kajiado South | Imbirikani/Eselenkei |  | education | education | education | 2023-07-01 | 2023-08-01 | 2024-06-01 | 2024-06-01 | 1000000 | 1000000 | 1000000 | CGK |  | 1000000 | 0 |  |  | 1000000 |  |  | ongoing
| Loolepo ECDE | Construction of two ECDE Classroom | increase enronment | Construction of two ECDE Classroom | 3110200 | construction of buildings | Kajiado South | Imbirikani/Eselenkei |  | education | education | education | 2023-07-01 | 2023-08-01 | 2024-06-01 | 2024-06-01 | 1000000 | 1000000 | 1000000 | CGK |  | 1000000 | 0 |  |  | 1000000 |  |  | ongoing
| Ole-polos ECDE | Completion | increase enronment | Completion | 3110200 | construction of buildings | Kajiado South | Imbirikani/Eselenkei |  | education | education | education | 2023-07-01 | 2023-08-01 | 2024-06-01 | 2024-06-01 | 1000000 | 1000000 | 1000000 | CGK |  | 1000000 | 0 |  |  | 1000000 |  |  | complete
| Olmapitei ECDE | Completion(at lintel level) | increase enronment | Completion(at lintel level) | 3110200 | construction of buildings | Kajiado South | Imbirikani/Eselenkei |  | education | education | education | 2023-07-01 | 2023-08-01 | 2024-06-01 | 2024-06-01 | 5000000 | 5000000 | 5000000 | CGK |  | 5000000 | 0 |  |  | 5000000 |  |  | complete
| Leingati Primary | Completion(at roofing level) | increase enronment | Completion(at roofing level) | 3110200 | construction of buildings | Kajiado South | Imbirikani/Eselenkei |  | education | education | education | 2023-07-01 | 2023-08-01 | 2024-06-01 | 2024-06-01 | 2000000 | 2000000 | 2000000 | CGK |  | 2000000 | 0 |  |  | 2000000 |  |  | complete
| Lenkisim Secondary School | Construction of classrrom | increase enronment | Construction of classrrom | 3110200 | construction of buildings | Kajiado South | Imbirikani/Eselenkei |  | education | education | education | 2023-07-01 | 2023-08-01 | 2024-06-01 | 2024-06-01 | 3000000 | 3000000 | 3000000 | CGK |  | 3000000 | 0 |  |  | 3000000 |  |  | Not started
| Iltuleta primary | Finishing Construction of 2 classrooms | increase enronment | Finishing Construction of 2 classrooms | 3110200 | construction of buildings | Kajiado South | Imbirikani/Eselenkei |  | education | education | education | 2023-07-01 | 2023-08-01 | 2024-06-01 | 2024-06-01 | 5000000 | 5000000 | 5000000 | CGK |  | 5000000 | 0 |  |  | 5000000 |  |  | ongoing
| Esiteti Pry School ECDE | Construction of 2No. ECD lassrrooms | increase enronment | Construction of 2No. ECD lassrrooms | 3110200 | construction of buildings | Kajiado South | Entonet/Lenkism |  | education | education | education | 2023-07-01 | 2023-08-01 | 2024-06-01 | 2024-06-01 | 5000000 | 5000000 | 5000000 | CGK |  | 5000000 | 0 |  |  | 5000000 |  |  | complete
| Lemkism | Contruction and equipping of classrooms | increase enronment | Contruction and equipping of classrooms | 3110200 | construction of buildings | Kajiado South | Entonet/Lenkism |  | education | education | education | 2023-07-01 | 2023-08-01 | 2024-06-01 | 2024-06-01 | 2000000 | 2000000 | 2000000 | CGK |  | 2000000 | 0 |  |  | 2000000 |  |  | complete
| St Maria Gorreti Sec School( Rombo Girtls) | Construction and equipping of 5 classroom | increase enronment | Construction and equipping of 5 classroom | 3110200 | construction of buildings | Kajiado South | Rombo |  | education | education | education | 2023-07-01 | 2023-08-01 | 2024-06-01 | 2024-06-01 | 1000000 | 1000000 | 1000000 | CGK |  | 1000000 | 0 |  |  | 1000000 |  |  | complete
| Oloibor Soit ECDE | Construction of 1. ECDE Class and equipping | increase enronment | Construction of 1. ECDE Class and equipping | 3110200 | construction of buildings | Kajiado South | Rombo |  | education | education | education | 2023-07-01 | 2023-08-01 | 2024-06-01 | 2024-06-01 | 3000000 | 3000000 | 3000000 | CGK |  | 3000000 | 0 |  |  | 3000000 |  |  | complete
| Olmaroroi Pri school | Completion of ECDE Class | increase enronment | Completion of ECDE Class | 3110200 | construction of buildings | Kajiado South | Rombo |  | education | education | education | 2023-07-01 | 2023-08-01 | 2024-06-01 | 2024-06-01 | 3000000 | 3000000 | 3000000 | CGK |  | 3000000 | 0 |  |  | 3000000 |  |  | complete
| Lempei pri school | Fencing of the school | increase enronment | Fencing of the school | 3110200 | construction of buildings | Kajiado East | Imaroro |  | education | education | education | 2023-07-01 | 2023-08-01 | 2024-06-01 | 2024-06-01 | 3000000 | 3000000 | 3000000 | CGK |  | 3000000 | 0 |  |  | 3000000 |  |  | terminated
| FPFK Lesoit pri | Fencing of the school | increase enronment | Fencing of the school | 3110200 | construction of buildings | Kajiado East | Imaroro |  | education | education | education | 2023-07-01 | 2023-08-01 | 2024-06-01 | 2024-06-01 | 3000000 | 3000000 | 3000000 | CGK |  | 3000000 | 0 |  |  | 3000000 |  |  | ongoing
| Enkutoto ECDE | Construction of two ECDE Classroom | increase enronment | Construction of two ECDE Classroom | 3110200 | construction of buildings | Kajiado East | Imaroro |  | education | education | education | 2023-07-01 | 2023-08-01 | 2024-06-01 | 2024-06-01 | 1500000 | 1500000 | 1500000 | CGK |  | 1500000 | 0 |  |  | 1500000 |  |  | Not started
| Mashuru pri school | Construction of two ECDE Classroom | increase enronment | Construction of two ECDE Classroom | 3110200 | construction of buildings | Kajiado East | Imaroro |  | education | education | education | 2023-07-01 | 2023-08-01 | 2024-06-01 | 2024-06-01 | 3000000 | 3000000 | 3000000 | CGK |  | 3000000 | 0 |  |  | 3000000 |  |  | terminated
| Ilnkidemi ECDE | Construction of one ECDE classroom | increase enronment | Construction of one ECDE classroom | 3110200 | construction of buildings | Kajiado East | Imaroro |  | education | education | education | 2023-07-01 | 2023-08-01 | 2024-06-01 | 2024-06-01 | 1400000 | 1400000 | 1400000 | CGK |  | 1400000 | 0 |  |  | 1400000 |  |  | Not started
| Edonyo Enker ECDE | Construction of two ECDE Classroom | increase enronment | Construction of two ECDE Classroom | 3110200 | construction of buildings | Kajiado East | Kenyewa/Poka |  | education | education | education | 2023-07-01 | 2023-08-01 | 2024-06-01 | 2024-06-01 | 3000000 | 3000000 | 3000000 | CGK |  | 3000000 | 0 |  |  | 3000000 |  |  | Not started
| Empiris ECDE | Fencing | increase enronment | Fencing | 3110200 | construction of buildings | Kajiado East | Kenyewa/Poka |  | education | education | education | 2023-07-01 | 2023-08-01 | 2024-06-01 | 2024-06-01 | 4300000 | 4300000 | 4300000 | CGK |  | 4300000 | 0 |  |  | 4300000 |  |  | complete
| Kunchu Pri school | Construction of two ECDE Classroom | increase enronment | Construction of two ECDE Classroom | 3110200 | construction of buildings | Kajiado East | Kenyewa/Poka |  | education | education | education | 2023-07-01 | 2023-08-01 | 2024-06-01 | 2024-06-01 | 1300000 | 1300000 | 1300000 | CGK |  | 1300000 | 0 |  |  | 1300000 |  |  | complete
| Merrueshi pri school | Fencing | increase enronment | Fencing | 3110200 | construction of buildings | Kajiado East | Kenyewa/Poka |  | education | education | education | 2023-07-01 | 2023-08-01 | 2024-06-01 | 2024-06-01 | 3000000 | 3000000 | 3000000 | CGK |  | 3000000 | 0 |  |  | 3000000 |  |  | complete
| Elerai pri school | Fencing of school | increase enronment | Fencing of school | 3110200 | construction of buildings | Kajiado East | Kenyewa/Poka |  | education | education | education | 2023-07-01 | 2023-08-01 | 2024-06-01 | 2024-06-01 | 2000000 | 2000000 | 2000000 | CGK |  | 2000000 | 0 |  |  | 2000000 |  |  | Not started
| Naningoi ECDE | Construction of two ECDE Classroom | increase enronment | Construction of two ECDE Classroom | 3110200 | construction of buildings | Kajiado East | Kenyewa/Poka |  | education | education | education | 2023-07-01 | 2023-08-01 | 2024-06-01 | 2024-06-01 | 2000000 | 2000000 | 2000000 | CGK |  | 2000000 | 0 |  |  | 2000000 |  |  | complete
| Oltinka primary school | Completion of ECD classes | increase enronment | Completion of ECD classes | 3110200 | construction of buildings | Kajiado East | Kenyewa/Poka |  | education | education | education | 2023-07-01 | 2023-08-01 | 2024-06-01 | 2024-06-01 | 2000000 | 2000000 | 2000000 | CGK |  | 2000000 | 0 |  |  | 2000000 |  |  | complete
| Supply of 10,000 ltrs. Plastic tanks to 5 schools | Completion of laboratory | increase enronment | Completion of laboratory | 3110200 | construction of buildings | Kajiado East | Kenyewa/Poka |  | education | education | education | 2023-07-01 | 2023-08-01 | 2024-06-01 | 2024-06-01 | 1500000 | 1500000 | 1500000 | CGK |  | 1500000 | 0 |  |  | 1500000 |  |  | complete
| Ndarkalali ECDE | Construction of 1 ECDE Classroom | increase enronment | Construction of 1 ECDE Classroom | 3110200 | construction of buildings | Kajiado West | Magadi |  | education | education | education | 2023-07-01 | 2023-08-01 | 2024-06-01 | 2024-06-01 | 1500000 | 1500000 | 1500000 | CGK |  | 1500000 | 0 |  |  | 1500000 |  |  | complete
| Endorko oonkishu ECDE | Construction of toilets and Purchase of desks | increase enronment | Construction of toilets and Purchase of desks | 3110200 | construction of buildings | Kajiado West | Magadi |  | education | education | education | 2023-07-01 | 2023-08-01 | 2024-06-01 | 2024-06-01 | 2000000 | 2000000 | 2000000 | CGK |  | 2000000 | 0 |  |  | 2000000 |  |  | complete
| Musenke ECDE | Completion of 1 ECDE Classrooms and purchase of desks | increase enronment | Completion of 1 ECDE Classrooms and purchase of desks | 3110200 | construction of buildings | Kajiado West | Magadi |  | education | education | education | 2023-07-01 | 2023-08-01 | 2024-06-01 | 2024-06-01 | 3000000 | 3000000 | 3000000 | CGK |  | 3000000 | 0 |  |  | 3000000 |  |  | ongoing
| Kayior ECDE | Purchase of desks and construction of toilets | increase enronment | Purchase of desks and construction of toilets | 3110200 | construction of buildings | Kajiado West | Magadi |  | education | education | education | 2023-07-01 | 2023-08-01 | 2024-06-01 | 2024-06-01 | 2500000 | 2500000 | 2500000 | CGK |  | 2500000 | 0 |  |  | 2500000 |  |  | complete
| Olkeri Israel ECDE | Construction of two classrooms | increase enronment | Construction of two classrooms | 3110200 | construction of buildings | Kajiado West | Magadi |  | education | education | education | 2023-07-01 | 2023-08-01 | 2024-06-01 | 2024-06-01 | 1500000 | 1500000 | 1500000 | CGK |  | 1500000 | 0 |  |  | 1500000 |  |  | complete
| Eroret Primary school | Completion of teachers quarters | increase enronment | Completion of teachers quarters | 3110200 | construction of buildings | Kajiado West | Magadi |  | education | education | education | 2023-07-01 | 2023-08-01 | 2024-06-01 | 2024-06-01 | 1000000 | 1000000 | 1000000 | CGK |  | 1000000 | 0 |  |  | 1000000 |  |  | finishing
| Illuamat ECDE | Completion of ECDE | increase enronment | Completion of ECDE | 3110200 | construction of buildings | Kajiado West | Magadi |  | education | education | education | 2023-07-01 | 2023-08-01 | 2024-06-01 | 2024-06-01 | 1000000 | 1000000 | 1000000 | CGK |  | 1000000 | 0 |  |  | 1000000 |  |  | complete
| Osupuko pri school | Completion works | increase enronment | Completion works | 3110200 | construction of buildings | Kajiado West | Ewuaso |  | education | education | education | 2023-07-01 | 2023-08-01 | 2024-06-01 | 2024-06-01 | 1500000 | 1500000 | 1500000 | CGK |  | 1500000 | 0 |  |  | 1500000 |  |  | complete
| Kimuka ECDE classroom | Renovation of classroom | increase enronment | Renovation of classroom | 3110200 | construction of buildings | Kajiado West | Ewuaso |  | education | education | education | 2023-07-01 | 2023-08-01 | 2024-06-01 | 2024-06-01 | 500000 | 500000 | 500000 | CGK |  | 500000 | 0 |  |  | 500000 |  |  | underbudgeted
| Iyerat Primary Classroom | Construction of classroom | increase enronment | Construction of classroom | 3110200 | construction of buildings | Kajiado West | Ewuaso |  | education | education | education | 2023-07-01 | 2023-08-01 | 2024-06-01 | 2024-06-01 | 2000000 | 2000000 | 2000000 | CGK |  | 2000000 | 0 |  |  | 2000000 |  |  | complete
| Kibiko Primary Classroom | Completion of classroom | increase enronment | Completion of classroom | 3110200 | construction of buildings | Kajiado West | Ewuaso |  | education | education | education | 2023-07-01 | 2023-08-01 | 2024-06-01 | 2024-06-01 | 2000000 | 2000000 | 2000000 | CGK |  | 2000000 | 0 |  |  | 2000000 |  |  | complete
| Kilonito ECDE | Renovation of 2 ECDE classrooms | increase enronment | Renovation of 2 ECDE classrooms | 3110200 | construction of buildings | Kajiado West | Iloodokilani |  | education | education | education | 2023-07-01 | 2023-08-01 | 2024-06-01 | 2024-06-01 | 1500000 | 1500000 | 1500000 | CGK |  | 1500000 | 0 |  |  | 1500000 |  |  | complete
| Indupa ECDE | Construction of 1 ECDE Classroom | increase enronment | Construction of 1 ECDE Classroom | 3110200 | construction of buildings | Kajiado West | Iloodokilani |  | education | education | education | 2023-07-01 | 2023-08-01 | 2024-06-01 | 2024-06-01 | 1500000 | 1500000 | 1500000 | CGK |  | 1500000 | 0 |  |  | 1500000 |  |  | complete
| Enkereyian ECDE | Construction of one ECDE classroom | increase enronment | Construction of one ECDE classroom | 3110200 | construction of buildings | Kajiado West | Keekonyokie |  | education | education | education | 2023-07-01 | 2023-08-01 | 2024-06-01 | 2024-06-01 | 1500000 | 1500000 | 1500000 | CGK |  | 1500000 | 0 |  |  | 1500000 |  |  | complete
| Elangata o mayianat ECDE | Construction of one ECDE classroom | increase enronment | Construction of one ECDE classroom | 3110200 | construction of buildings | Kajiado West | Keekonyokie |  | education | education | education | 2023-07-01 | 2023-08-01 | 2024-06-01 | 2024-06-01 | 1000000 | 1000000 | 1000000 | CGK |  | 1000000 | 0 |  |  | 1000000 |  |  | Complete
| Naboisho ECDE | Construction of one ECDE classroom | increase enronment | Construction of one ECDE classroom | 3110200 | construction of buildings | Kajiado West | Keekonyokie |  | education | education | education | 2023-07-01 | 2023-08-01 | 2024-06-01 | 2024-06-01 | 1000000 | 1000000 | 1000000 | CGK |  | 1000000 | 0 |  |  | 1000000 |  |  | Complete
| Ole Kasasi Stadium | Leveling of Ole kasasi Stadium | increase enronment | Leveling of Ole kasasi Stadium | 3110200 | construction of buildings | Kajiado North | Ongata Rongai |  | education | education | education | 2023-07-01 | 2023-08-01 | 2024-06-01 | 2024-06-01 | 3000000 | 3000000 | 3000000 | CGK |  | 3000000 | 0 |  |  | 3000000 |  |  | Complete
| Ole Kasasi Stadium | Renovation of toilet blocks | increase enronment | Renovation of toilet blocks | 3110200 | construction of buildings | Kajiado North | Ongata Rongai |  | education | education | education | 2023-07-01 | 2023-08-01 | 2024-06-01 | 2024-06-01 | 4500000 | 4500000 | 4500000 | CGK |  | 4500000 | 0 |  |  | 4500000 |  |  | Ongoing
| Ole Kasasi Multi-purpose | Completion of Ole Kasasi Multi-purpose hall | increase enronment | Completion of Ole Kasasi Multi-purpose hall | 3110200 | construction of buildings | Kajiado North | Ongata Rongai |  | education | education | education | 2023-07-01 | 2023-08-01 | 2024-06-01 | 2024-06-01 | 3000000 | 3000000 | 3000000 | CGK |  | 3000000 | 0 |  |  | 3000000 |  |  | Not started
| Nkaimurunya ECDE | Fencing of Nkaimurunya ECDE | increase enronment | Fencing of Nkaimurunya ECDE | 3110200 | construction of buildings | Kajiado North | Nkaimurunya |  | education | education | education | 2023-07-01 | 2023-08-01 | 2024-06-01 | 2024-06-01 | 2000000 | 2000000 | 2000000 | CGK |  | 2000000 | 0 |  |  | 2000000 |  |  | Not started
| Nakeel Stadium | Landscaping & other works | increase enronment | Landscaping & other works | 3110200 | construction of buildings | Kajiado North | Nkaimurunya |  | education | education | education | 2023-07-01 | 2023-08-01 | 2024-06-01 | 2024-06-01 | 2500000 | 2500000 | 2500000 | CGK |  | 2500000 | 0 |  |  | 2500000 |  |  | Complete
| Ngong Township ECDE | Construction of special needs toilet block | increase enronment | Construction of special needs toilet block | 3110200 | construction of buildings | Kajiado North | Ngong |  | education | education | education | 2023-07-01 | 2023-08-01 | 2024-06-01 | 2024-06-01 | 2000000 | 2000000 | 2000000 | CGK |  | 2000000 | 0 |  |  | 2000000 |  |  | Not started
| Oloolua ECDE | Completion of Oloolua ECDE | increase enronment | Completion of Oloolua ECDE | 3110200 | construction of buildings | Kajiado North | Oloolua |  | education | education | education | 2023-07-01 | 2023-08-01 | 2024-06-01 | 2024-06-01 | 2000000 | 2000000 | 2000000 | CGK |  | 2000000 | 0 |  |  | 2000000 |  |  | Complete
| Embulbul Community Field | Landscaping of Embulbul Community Field | increase enronment | Landscaping of Embulbul Community Field | 3110200 | construction of buildings | Kajiado North | Oloolua |  | education | education | education | 2023-07-01 | 2023-08-01 | 2024-06-01 | 2024-06-01 | 5000000 | 5000000 | 5000000 | CGK |  | 5000000 | 0 |  |  | 5000000 |  |  | Complete
| Enkasiti ECDE | Renovations of Enkasiti ECDE | increase enronment | Renovations of Enkasiti ECDE | 3110200 | construction of buildings | Kajiado East | Kitengela |  | education | education | education | 2023-07-01 | 2023-08-01 | 2024-06-01 | 2024-06-01 | 4000000 | 4000000 | 4000000 | CGK |  | 4000000 | 0 |  |  | 4000000 |  |  | Complete
| Kisaju Dipak Girls Secondary School | Construction of a Dormitory | increase enronment | Construction of a Dormitory | 3110200 | construction of buildings | Kajiado East | Kaputiei North |  | education | education | education | 2023-07-01 | 2023-08-01 | 2024-06-01 | 2024-06-01 | 2000000 | 2000000 | 2000000 | CGK |  | 2000000 | 0 |  |  | 2000000 |  |  | On-going
| Moi Girls Isinya | Construction of two classrooms | increase enronment | Construction of two classrooms | 3110200 | construction of buildings | Kajiado East | Kaputiei North |  | education | education | education | 2023-07-01 | 2023-08-01 | 2024-06-01 | 2024-06-01 | 2000000 | 2000000 | 2000000 | CGK |  | 2000000 | 0 |  |  | 2000000 |  |  | Not started
| Sautet ECDE | Construction of 1 ECDE Classroom | increase enronment | Construction of 1 ECDE Classroom | 3110200 | construction of buildings | Kajiado East | Kaputiei North |  | education | education | education | 2023-07-01 | 2023-08-01 | 2024-06-01 | 2024-06-01 | 1500000 | 1500000 | 1500000 | CGK |  | 1500000 | 0 |  |  | 1500000 |  |  | ongoing
| Olepolos ECDE | Construction of 1 ECDE Classroom | increase enronment | Construction of 1 ECDE Classroom | 3110200 | construction of buildings | Kajiado East | Kaputiei North |  | education | education | education | 2023-07-01 | 2023-08-01 | 2024-06-01 | 2024-06-01 | 1500000 | 1500000 | 1500000 | CGK |  | 1500000 | 0 |  |  | 1500000 |  |  | ongoing
| Enkorika ECDE | Construction of 1 ECDE Classroom | increase enronment | Construction of 1 ECDE Classroom | 3110200 | construction of buildings | Kajiado Central | Dalalekutuk |  | education | education | education | 2023-07-01 | 2023-08-01 | 2024-06-01 | 2024-06-01 | 2000000 | 2000000 | 2000000 | CGK |  | 2000000 | 0 |  |  | 2000000 |  |  | Complete
| Eiti ECDE | Construction of 1 ECDE Classroom | increase enronment | Construction of 1 ECDE Classroom | 3110200 | construction of buildings | Kajiado Central | Dalalekutuk |  | education
| Oliorum Primary | Construction of toilet blocks | increase enronment | Construction of toilet blocks | 3110200 | construction of buildings | Kajiado Central | Ildamat |  | education
| Ilesai ECDE classroom | Construction of 2 ECDE Classroom at Maparasha primary | increase enronment | Construction of 2 ECDE Classroom at Maparasha primary | 3110200 | construction of buildings | Kajiado Central | Matapato North |  | education | education | education | 2024-07-01 | 2024-08-01 | 2025-06-01 | 2025-06-01 | 4000000 | 4000000 | 4000000 | CGK |  | 4000000 | 0 |  |  | 4000000 |  |  | 0ngoing
| Oloserian ECDE classroom | Construction of 2 ECDE Classrooms | increase enronment | Construction of 2 ECDE Classrooms | 3110200 | construction of buildings | Kajiado Central | Matapato North |  | education | education | education | 2024-07-01 | 2024-08-01 | 2025-06-01 | 2025-06-01 | 3000000 | 3000000 | 3000000 | CGK |  | 3000000 | 0 |  |  | 3000000 |  |  | ongoing
| Emashani ECDE | Construction of 1 ECDE Classroom | increase enronment | Construction of 1 ECDE Classroom | 3110200 | construction of buildings | Kajiado Central | Matapato North |  | education | education | education | 2024-07-01 | 2024-08-01 | 2025-06-01 | 2025-06-01 | 1800000 | 1800000 | 1800000 | CGK |  | 1800000 | 0 |  |  | 1800000 |  |  | ongoing
| Bisil Township ECDE | Construction of 2 ECDE Classrooms | increase enronment | Construction of 2 ECDE Classrooms | 3110200 | construction of buildings | Kajiado Central | Matapato North |  | education | education | education | 2024-07-01 | 2024-08-01 | 2025-06-01 | 2025-06-01 | 3000000 | 3000000 | 3000000 | CGK |  | 3000000 | 0 |  |  | 3000000 |  |  | complete
| Mpoori Primary School | Construction of 1 Classroom | increase enronment | Construction of 1 Classroom | 3110200 | construction of buildings | Kajiado Central | Matapato South |  | education | education | education | 2024-07-01 | 2024-08-01 | 2025-06-01 | 2025-06-01 | 2000000 | 2000000 | 2000000 | CGK |  | 2000000 | 0 |  |  | 2000000 |  |  | complete
| Namelok-Entepesi ECDE | Completion of ECDE Eluanata | increase enronment | Completion of ECDE Eluanata | 3110200 | construction of buildings | Kajiado Central | Matapato South |  | education | education | education | 2024-07-01 | 2024-08-01 | 2025-06-01 | 2025-06-01 | 1000000 | 1000000 | 1000000 | CGK |  | 1000000 | 0 |  |  | 1000000 |  |  | ongoing
| Ilikushin Primary School | Fencing of the School | increase enronment | Fencing of the School | 3110200 | construction of buildings | Kajiado East | Imaroro |  | education | education | education | 2024-07-01 | 2024-08-01 | 2025-06-01 | 2025-06-01 | 3000000 | 3000000 | 3000000 | CGK |  | 3000000 | 0 |  |  | 3000000 |  |  | ongoing
| Oloilalei Primary School | Fencing of the School | increase enronment | Fencing of the School | 3110200 | construction of buildings | Kajiado East | Imaroro |  | education | education | education | 2024-07-01 | 2024-08-01 | 2025-06-01 | 2025-06-01 | 3000000 | 3000000 | 3000000 | CGK |  | 3000000 | 0 |  |  | 3000000 |  |  | ongoing
| Indonyo Primary School | Construction of 2 ECDE Classrooms | increase enronment | Construction of 2 ECDE Classrooms | 3110200 | construction of buildings | Kajiado East | Imaroro |  | education | education | education | 2024-07-01 | 2024-08-01 | 2025-06-01 | 2025-06-01 | 3000000 | 3000000 | 3000000 | CGK |  | 3000000 | 0 |  |  | 3000000 |  |  | ongoing
| Osarai Primary School | Construction of 2 ECDE Classrooms | increase enronment | Construction of 2 ECDE Classrooms | 3110200 | construction of buildings | Kajiado east | Imaroro |  | education | education | education | 2024-07-01 | 2024-08-01 | 2025-06-01 | 2025-06-01 | 3000000 | 3000000 | 3000000 | CGK |  | 3000000 | 0 |  |  | 3000000 |  |  | ongoing
| Oloserian Primary School | Construction of 2 ECDE Classrooms | increase enronment | Construction of 2 ECDE Classrooms | 3110200 | construction of buildings | Kajiado east | Imaroro |  | education | education | education | 2024-07-01 | 2024-08-01 | 2025-06-01 | 2025-06-01 | 3000000 | 3000000 | 3000000 | CGK |  | 3000000 | 0 |  |  | 3000000 |  |  | ongoing
| Enkaji naibor ECDE | Contruction of 2 classrooms | increase enronment | Contruction of 2 classrooms | 3110200 | construction of buildings | Kajiado South | Imbirikani |  | education | education | education | 2024-07-01 | 2024-08-01 | 2025-06-01 | 2025-06-01 | 3500000 | 3500000 | 3500000 | CGK |  | 3500000 | 0 |  |  | 3500000 |  |  | complete
| Lenkati Primary School | Construction of teachers quarters | increase enronment | Construction of teachers quarters | 3110200 | construction of buildings | Kajiado South | Imbirikani |  | education | education | education | 2024-07-01 | 2024-08-01 | 2025-06-01 | 2025-06-01 | 3500000 | 3500000 | 3500000 | CGK |  | 3500000 | 0 |  |  | 3500000 |  |  | complete
| Esoit ECDE | Completion of 1 classroom & toilet | increase enronment | Completion of 1 classroom & toilet | 3110200 | construction of buildings | Kajiado South | Kuku |  | education | education | education | 2024-07-01 | 2024-08-01 | 2025-06-01 | 2025-06-01 | 2000000 | 2000000 | 2000000 | CGK |  | 2000000 | 0 |  |  | 2000000 |  |  | ongoing
| Kuku Primary School | Construction of 2 ECDE classrooms | increase enronment | Construction of 2 ECDE classrooms | 3110200 | construction of buildings | Kajiado South | Kuku |  | education | education | education | 2024-07-01 | 2024-08-01 | 2025-06-01 | 2025-06-01 | 3000000 | 3000000 | 3000000 | CGK |  | 3000000 | 0 |  |  | 3000000 |  |  | ongoing
| Neiti ECDE | Construction of 1 ECDE classroom & toilet | increase enronment | Construction of 1 ECDE classroom & toilet | 3110200 | construction of buildings | Kajiado South | Kuku |  | education | education | education | 2024-07-01 | 2024-08-01 | 2025-06-01 | 2025-06-01 | 2000000 | 2000000 | 2000000 | CGK |  | 2000000 | 0 |  |  | 2000000 |  |  | ongoing
| Eluai ECDE | Construction of 2 ECDE classroom | increase enronment | Construction of 2 ECDE classroom | 3110200 | construction of buildings | Kajiado South | Lenkism |  | education | education | education | 2024-07-01 | 2024-08-01 | 2025-06-01 | 2025-06-01 | 3000000 | 3000000 | 3000000 | CGK |  | 3000000 | 0 |  |  | 3000000 |  |  | complete
| Kimana Primary School | Construction of 10 doors Toilets | increase enronment | Construction of 10 doors Toilets | 3110200 | construction of buildings | Kajiado South | Kimana |  | education | education | education | 2024-07-01 | 2024-08-01 | 2025-06-01 | 2025-06-01 | 1500000 | 1500000 | 1500000 | CGK |  | 1500000 | 0 |  |  | 1500000 |  |  | ongoing
| Nkorio Ronkena | Fencing | increase enronment | Fencing | 3110200 | construction of buildings | Kajiado South | Kimana |  | education | education | education | 2024-07-01 | 2024-08-01 | 2025-06-01 | 2025-06-01 | 3000000 | 3000000 | 3000000 | CGK |  | 3000000 | 0 |  |  | 3000000 |  |  | ongoing
| Esukuta ECDE | Construction of 2 new classrooms | increase enronment | Construction of 2 new classrooms | 3110200 | construction of buildings | Kajiado South | Rombo |  | education | education | education | 2024-07-01 | 2024-08-01 | 2025-06-01 | 2025-06-01 | 3000000 | 3000000 | 3000000 | CGK |  | 3000000 | 0 |  |  | 3000000 |  |  | ongoing
| Enkoireroi ECDE | Construction of 2 classrooms | increase enronment | Construction of 2 classrooms | 3110200 | construction of buildings | Kajiado West | Ewuaso |  | education | education | education | 2024-07-01 | 2024-08-01 | 2025-06-01 | 2025-06-01 | 3000000 | 3000000 | 3000000 | CGK |  | 3000000 | 0 |  |  | 3000000 |  |  | ongoing
| Olomayian ECDE | Construction of 1 Classroom | increase enronment | Construction of 1 Classroom | 3110200 | construction of buildings | Kajiado West | Ewuaso |  | education | education | education | 2024-07-01 | 2024-08-01 | 2025-06-01 | 2025-06-01 | 1500000 | 1500000 | 1500000 | CGK |  | 1500000 | 0 |  |  | 1500000 |  |  | ongoing
| Ilmasharen ECDE | Construction of 1 Classroom | increase enronment | Construction of 1 Classroom | 3110200 | construction of buildings | Kajiado West | Ewuaso |  | education | education | education | 2024-07-01 | 2024-08-01 | 2025-06-01 | 2025-06-01 | 1500000 | 1500000 | 1500000 | CGK |  | 1500000 | 0 |  |  | 1500000 |  |  | ongoing
| Kisharu ECDE | Construction of 1 Classroom | increase enronment | Construction of 1 Classroom | 3110200 | construction of buildings | Kajiado West | Ewuaso |  | education | education | education | 2024-07-01 | 2024-08-01 | 2025-06-01 | 2025-06-01 | 1500000 | 1500000 | 1500000 | CGK |  | 1500000 | 0 |  |  | 1500000 |  |  | not started
| Iyarat ECDE | Construction of 1 classroom | increase enronment | Construction of 1 classroom | 3110200 | construction of buildings | Kajiado West | Iloodokilani |  | education | education | education | 2024-07-01 | 2024-08-01 | 2025-06-01 | 2025-06-01 | 1500000 | 1500000 | 1500000 | CGK |  | 1500000 | 0 |  |  | 1500000 |  |  | complete
| Inkulukuo Naibor ECDE classroom | Construction of 1 classroom | increase enronment | Construction of 1 classroom | 3110200 | construction of buildings | Kajiado West | Iloodokilani |  | education | education | education | 2024-07-01 | 2024-08-01 | 2025-06-01 | 2025-06-01 | 1500000 | 1500000 | 1500000 | CGK |  | 1500000 | 0 |  |  | 1500000 |  |  | complete
| Endonyo Sidai ECDE | Construction of 1 classroom | increase enronment | Construction of 1 classroom | 3110200 | construction of buildings | Kajiado West | Keekonyokie |  | education | education | education | 2024-07-01 | 2024-08-01 | 2025-06-01 | 2025-06-01 | 1500000 | 1500000 | 1500000 | CGK |  | 1500000 | 0 |  |  | 1500000 |  |  | complete
| Oloika Primary School | Construction of toilets | increase enronment | Construction of toilets | 3110200 | construction of buildings | Kajiado West | Keekonyokie |  | education | education | education | 2024-07-01 | 2024-08-01 | 2025-06-01 | 2025-06-01 | 1500000 | 1500000 | 1500000 | CGK |  | 1500000 | 0 |  |  | 1500000 |  |  | complete
| Oloombaluani ECDE | Construction of 1 classroom | increase enronment | Construction of 1 classroom | 3110200 | construction of buildings | Kajiado West | Keekonyokie |  | education | education | education | 2024-07-01 | 2024-08-01 | 2025-06-01 | 2025-06-01 | 1500000 | 1500000 | 1500000 | CGK |  | 1500000 | 0 |  |  | 1500000 |  |  | complete
| Oloropil ECDE | Construction of 1 Classroom | increase enronment | Construction of 1 Classroom | 3110200 | construction of buildings | Kajiado West | Keekonyokie |  | education | education | education | 2024-07-01 | 2024-08-01 | 2025-06-01 | 2025-06-01 | 1500000 | 1500000 | 1500000 | CGK |  | 1500000 | 0 |  |  | 1500000 |  |  | complete
| Enchoro- Elerai Primary School | Construction of toilets | increase enronment | Construction of toilets | 3110200 | construction of buildings | Kajiado West | Keekonyokie |  | education | education | education | 2024-07-01 | 2024-08-01 | 2025-06-01 | 2025-06-01 | 1500000 | 1500000 | 1500000 | CGK |  | 1500000 | 0 |  |  | 1500000 |  |  | ongoing
| Nkarusa ECDE | Construction of 2 classrooms | increase enronment | Construction of 2 classrooms | 3110200 | construction of buildings | Kajiado West | Keekonyokie |  | education | education | education | 2024-07-01 | 2024-08-01 | 2025-06-01 | 2025-06-01 | 3000000 | 3000000 | 3000000 | CGK |  | 3000000 | 0 |  |  | 3000000 |  |  | complete
| Enduata ECDE | Construction of 1 classroom | increase enronment | Construction of 1 classroom | 3110200 | construction of buildings | Kajiado West | Magadi |  | education | education | education | 2024-07-01 | 2024-08-01 | 2025-06-01 | 2025-06-01 | 1800000 | 1800000 | 1800000 | CGK |  | 1800000 | 0 |  |  | 1800000 |  |  | ongoing
| Ilankeruani Primary School | Construction of teachers quarters | increase enronment | Construction of teachers quarters | 3110200 | construction of buildings | Kajiado West | Magadi |  | education | education | education | 2024-07-01 | 2024-08-01 | 2025-06-01 | 2025-06-01 | 3000000 | 3000000 | 3000000 | CGK |  | 3000000 | 0 |  |  | 3000000 |  |  | ongoing
| Shompole Primary School | Construction of 1 ECDE classroom | increase enronment | Construction of 1 ECDE classroom | 3110200 | construction of buildings | Kajiado West | Magadi |  | education | education | education | 2024-07-01 | 2024-08-01 | 2025-06-01 | 2025-06-01 | 1800000 | 1800000 | 1800000 | CGK |  | 1800000 | 0 |  |  | 1800000 |  |  | complete
| Endonyoolasho & Oloika Primary Schools | Purchase of desks | increase enronment | Purchase of desks | 3110200 | construction of buildings | Kajiado West | Magadi |  | education | education | education | 2024-07-01 | 2024-08-01 | 2025-06-01 | 2025-06-01 | 2000000 | 2000000 | 2000000 | CGK |  | 2000000 | 0 |  |  | 2000000 |  |  | ongoing
| Entasopia V.T.C | Construction of 2 classrooms | increase enronment | Construction of 2 classrooms | 3110200 | construction of buildings | Kajiado West | Magadi |  | education | education | education | 2024-07-01 | 2024-08-01 | 2025-06-01 | 2025-06-01 | 4000000 | 4000000 | 4000000 | CGK |  | 4000000 | 0 |  |  | 4000000 |  |  | ongoing
| Komiya teachers' quarters | Construction of teachers quarters | increase enronment | Construction of teachers quarters | 3110200 | construction of buildings | Kajiado West | Magadi |  | education | education | education | 2024-07-01 | 2024-08-01 | 2025-06-01 | 2025-06-01 | 2000000 | 2000000 | 2000000 | CGK |  | 2000000 | 0 |  |  | 2000000 |  |  | ongoing
| Magadi Primary School | Completion of works JSS lab | increase enronment | Completion of works JSS lab | 3110200 | construction of buildings | Kajiado West | Magadi |  | education | education | education | 2024-07-01 | 2024-08-01 | 2025-06-01 | 2025-06-01 | 1800000 | 1800000 | 1800000 | CGK |  | 1800000 | 0 |  |  | 1800000 |  |  | ongoing
| Enkirgirri Primary School | Fencing of the School | increase enronment | Fencing of the School | 3110200 | construction of buildings | Kajiado East | Kaputiei North |  | education | education | education | 2024-07-01 | 2024-08-01 | 2025-06-01 | 2025-06-01 | 3000000 | 3000000 | 3000000 | CGK |  | 3000000 | 0 |  |  | 3000000 |  |  | complete
| ECDE centre Isinya | Equipping & renovation | increase enronment | Equipping & renovation | 3110200 | construction of buildings | Kajiado east | Kaputiei North |  | education | education | education | 2024-07-01 | 2024-08-01 | 2025-06-01 | 2025-06-01 | 3000000 | 3000000 | 3000000 | CGK |  | 3000000 | 0 |  |  | 3000000 |  |  | complete
| Elerai ECDE | Completion of Fencing | increase enronment | Completion of Fencing | 3110200 | construction of buildings | Kajiado East | Kenyawa/poka |  | education | education | education | 2024-07-01 | 2024-08-01 | 2025-06-01 | 2025-06-01 | 2000000 | 2000000 | 2000000 | CGK |  | 2000000 | 0 |  |  | 2000000 |  |  | complete
| Ololaiser High School | Construction of modern gate at Ololaiser High School | increase enronment | Construction of modern gate at Ololaiser High School | 3110200 | construction of buildings | Kajiado North | Kajiado North |  | education | education | education | 2024-07-01 | 2024-08-01 | 2025-06-01 | 2025-06-01 | 2000000 | 2000000 | 2000000 | CGK |  | 2000000 | 0 |  |  | 2000000 |  |  | ongoing
| Prof. Saitoti Primary School | Construction of 2 ECDE classrooms at Prof Saitoti Pri School | increase enronment | Construction of 2 ECDE classrooms at Prof Saitoti Pri School | 3110200 | construction of buildings | Kajiado North | Kajiado North |  | education | education | education | 2024-07-01 | 2024-08-01 | 2025-06-01 | 2025-06-01 | 3000000 | 3000000 | 3000000 | CGK |  | 3000000 | 0 |  |  | 3000000 |  |  | ongoing
| Enoomatasiani ECDE | Construction of 4 toilets,kitchen & painting of ECDE Classes | increase enronment | Construction of 4 toilets,kitchen & painting of ECDE Classes | 3110200 | construction of buildings | Kajaido North | Kajaido North |  | education | education | education | 2024-07-01 | 2024-08-01 | 2025-06-01 | 2025-06-01 | 3500000 | 3500000 | 3500000 | CGK |  | 3500000 | 0 |  |  | 3500000 |  |  | ongoing
| Rongai | Equipping of the ECDE | increase enronment | Equipping of the ECDE | 3110200 | construction of buildings | Kajiado North | Kajiado North |  | education | education | education | 2024-07-01 | 2024-08-01 | 2025-06-01 | 2025-06-01 | 1000000 | 1000000 | 1000000 | CGK |  | 1000000 | 0 |  |  | 1000000 |  |  | ongoing
| Rongai | Purchase of a boxing ring at talanta hall | increase enronment | Purchase of a boxing ring at talanta hall | 3110200 | construction of buildings | Kajiado North | Kajiado North |  | education | education | education | 2024-07-01 | 2024-08-01 | 2025-06-01 | 2025-06-01 | 1500000 | 1500000 | 1500000 | CGK |  | 1500000 | 0 |  |  | 1500000 |  |  | ongoing
| Rongai | Installation of goal post | increase enronment | Installation of goal post | 3110200 | construction of buildings | Kajiado North | Kajiado North |  | education | education | education | 2024-07-01 | 2024-08-01 | 2025-06-01 | 2025-06-01 | 500000 | 500000 | 500000 | CGK |  | 500000 | 0 |  |  | 500000 |  |  | ongoing
| Metro Kirikau Land aquizition | Purchase of land for ECDE construction | increase enronment | Purchase of land for ECDE construction | 3110200 | construction of buildings | Kajiado East | Kajiado East |  | education | education | education | 2024-07-01 | 2024-08-01 | 2025-06-01 | 2025-06-01 | 10000000 | 10000000 | 10000000 | CGK |  | 10000000 | 0 |  |  | 10000000 |  |  | ongoing
| Arap Moi ECDE | Construction of 4 in one toilets | increase enronment | Construction of 4 in one toilets | 3110200 | construction of buildings | Kajiado North | Olkeri |  | education | education | education | 2024-07-01 | 2024-08-01 | 2025-06-01 | 2025-06-01 | 1500000 | 1500000 | 1500000 | CGK |  | 1500000 | 0 |  |  | 1500000 |  |  | ongoing
| Isilale primay school | Constuction of 1 ECDE classroom | increase enronment | Constuction of 1 ECDE classroom | 3110200 | construction of buildings | Kajiado Central | Dalalekutuk |  | education | education | education | 2024-07-01 | 2024-08-01 | 2025-06-01 | 2025-06-01 | 1800000 | 1800000 | 1800000 | CGK |  | 1800000 | 0 |  |  | 1800000 |  |  | ongoing
| Nalala ECDE | Construction of 1 ECDE Classroom | increase enronment | Construction of 1 ECDE Classroom | 3110200 | construction of buildings | Kajiado Central | Dalalekutuk |  | education | education | education | 2024-07-01 | 2024-08-01 | 2025-06-01 | 2025-06-01 | 1800000 | 1800000 | 1800000 | CGK |  | 1800000 | 0 |  |  | 1800000 |  |  | ongoing
| Nenkashe primary | Construction of 1 ECDE Classroom | increase enronment | Construction of 1 ECDE Classroom | 3110200 | construction of buildings | Kajiado Central | Dalalekutuk |  | education | education | education | 2024-07-01 | 2024-08-01 | 2025-06-01 | 2025-06-01 | 1800000 | 1800000 | 1800000 | CGK |  | 1800000 | 0 |  |  | 1800000 |  |  | ongoing
| Iseuri primary school | Construction of 1 ECDE Classroom | increase enronment | Construction of 1 ECDE Classroom | 3110200 | construction of buildings | Kajiado Central | Dalalekutuk |  | education | education | education | 2024-07-01 | 2024-08-01 | 2025-06-01 | 2025-06-01 | 1800000 | 1800000 | 1800000 | CGK |  | 1800000 | 0 |  |  | 1800000 |  |  | ongoing
| Saina Annet | Construction of 1 ECDE Classroom | increase enronment | Construction of 1 ECDE Classroom | 3110200 | construction of buildings | Kajiado Central | Dalalekutuk |  | education | education | education | 2024-07-01 | 2024-08-01 | 2025-06-01 | 2025-06-01 | 1800000 | 1800000 | 1800000 | CGK |  | 1800000 | 0 |  |  | 1800000 |  |  | ongoing

## Sheet1
to increase enrolment | 3110200
to increase enrolment | 3110200
to increase enrolment | 3110200
to increase enrolment | 3110200
to increase enrolment | 3110200
to increase enrolment | 3110200
to increase enrolment | 3110200
to increase enrolment | 3110200
to increase enrolment | 3110200
to increase enrolment | 3110200
to increase enrolment | 3110200
to increase enrolment | 3110200
to increase enrolment | 3110200
to increase enrolment | 3110200
to increase enrolment | 3110200
to increase enrolment | 3110200
to increase enrolment | 3110200
to increase enrolment | 3110200
to increase enrolment | 3110200
to increase enrolment | 3110200
to increase enrolment | 3110200
to increase enrolment | 3110200
to increase enrolment | 3110200
to increase enrolment | 3110200
to increase enrolment | 3110200
to increase enrolment | 3110200
to increase enrolment | 3110200
to increase enrolment | 3110200
to increase enrolment | 3110200
to increase enrolment | 3110200
to increase enrolment | 3110200
to increase enrolment | 3110200
to increase enrolment | 3110200
to increase enrolment | 3110200
to increase enrolment | 3110200
to increase enrolment | 3110200
to increase enrolment | 3110200
to increase enrolment | 3110200
to increase enrolment | 3110200
3110200
to increase enrolment | 3110200
to increase enrolment | 3110200
to increase enrolment | 3110200
to increase enrolment | 3110200
to increase enrolment | 3110200
to increase enrolment | 3110200
to increase enrolment | 3110200
to increase enrolment | 3110200
to increase enrolment | 3110200
to increase enrolment | 3110200
to increase enrolment | 3110200
to increase enrolment | 3110200
to increase enrolment | 3110200
to increase enrolment | 3110200
to increase enrolment | 3110200
to increase enrolment | 3110200
to increase enrolment | 3110200
to increase enrolment | 3110200
to increase enrolment | 3110200
to increase enrolment | 3110200
to increase enrolment | 3110200
to increase enrolment | 3110200
to increase enrolment | 3110200
to increase enrolment | 3110200
to increase enrolment | 3110200
to increase enrolment | 3110200
to increase enrolment | 3110200
to increase enrolment | 3110200
to increase enrolment
to increase enrolment
to increase enrolment
to increase enrolment
to increase enrolment
to increase enrolment
to increase enrolment
to increase enrolment
to increase enrolment
to increase enrolment
to increase enrolment
to increase enrolment
to increase enrolment
to increase enrolment
to increase enrolment
to increase enrolment
to increase enrolment
to increase enrolment
to increase enrolment
to increase enrolment
to increase enrolment
to increase enrolment
to increase enrolment
to increase enrolment
to increase enrolment
to increase enrolment
to increase enrolment
to increase enrolment
to increase enrolment
to increase enrolment
to increase enrolment
to increase enrolment
to increase enrolment
to increase enrolment
to increase enrolment
to increase enrolment
to increase enrolment
to increase enrolment
to increase enrolment
to increase enrolment
to increase enrolment
to increase enrolment
to increase enrolment
to increase enrolment
to increase enrolment
to increase enrolment
to increase enrolment
to increase enrolment
to increase enrolment
to increase enrolment
to increase enrolment
to increase enrolment
to increase enrolment
to increase enrolment
to increase enrolment
to increase enrolment
to increase enrolment
to increase enrolment
to increase enrolment
to increase enrolment
to increase enrolment
to increase enrolment
to increase enrolment
to increase enrolment
to increase enrolment
to increase enrolment
to increase enrolment
to increase enrolment
to increase enrolment
to increase enrolment
to increase enrolment
to increase enrolment
to increase enrolment
to increase enrolment
to increase enrolment
to increase enrolment
to increase enrolment
to increase enrolment
to increase enrolment
to increase enrolment
to increase enrolment
to increase enrolment
to increase enrolment
to increase enrolment
to increase enrolment
to increase enrolment
to increase enrolment
to increase enrolment
to increase enrolment
to increase enrolment
to increase enrolment
to increase enrolment
to increase enrolment
to increase enrolment
to increase enrolment
to increase enrolment
to increase enrolment
to increase enrolment
to increase enrolment
to increase enrolment
to increase enrolment
to increase enrolment
to increase enrolment
to increase enrolment
to increase enrolment
to increase enrolment
to increase enrolment
to increase enrolment
to increase enrolment
to increase enrolment
to increase enrolment
to increase enrolment
to increase enrolment
to increase enrolment
to increase enrolment
to increase enrolment
to increase enrolment
to increase enrolment
to increase enrolment
to increase enrolment
to increase enrolment
to increase enrolment
to increase enrolment
to increase enrolment
to increase enrolment
to increase enrolment
to increase enrolment
to increase enrolment
to increase enrolment
to increase enrolment
to increase enrolment
to increase enrolment
to increase enrolment
to increase enrolment
to increase enrolment
to increase enrolment
to increase enrolment
to increase enrolment
to increase enrolment
to increase enrolment
to increase enrolment
to increase enrolment
to increase enrolment
to increase enrolment
to increase enrolment
to increase enrolment
to increase enrolment
to increase enrolment
to increase enrolment
to increase enrolment
to increase enrolment
to increase enrolment
to increase enrolment
to increase enrolment
to increase enrolment
to increase enrolment
to increase enrolment
to increase enrolment
to increase enrolment
to increase enrolment
to increase enrolment
to increase enrolment
to increase enrolment
to increase enrolment
to increase enrolment
to increase enrolment
to increase enrolment
to increase enrolment
to increase enrolment
to increase enrolment
to increase enrolment
to increase enrolment
to increase enrolment
to increase enrolment
to increase enrolment
to increase enrolment
to increase enrolment
to increase enrolment
to increase enrolment
to increase enrolment
to increase enrolment
to increase enrolment
to increase enrolment
to increase enrolment
to increase enrolment
to increase enrolment
to increase enrolment
to increase enrolment
to increase enrolment
to increase enrolment
to increase enrolment
to increase enrolment
to increase enrolment
to increase enrolment
to increase enrolment
to increase enrolment
to increase enrolment
to increase enrolment
to increase enrolment
to increase enrolment
to increase enrolment
to increase enrolment
to increase enrolment
to increase enrolment
to increase enrolment
to increase enrolment
to increase enrolment
to increase enrolment
to increase enrolment
to increase enrolment
to increase enrolment
to increase enrolment
to increase enrolment
to increase enrolment
to increase enrolment
to increase enrolment
to increase enrolment
to increase enrolment
to increase enrolment
to increase enrolment
to increase enrolment
to increase enrolment
to increase enrolment
to increase enrolment
to increase enrolment
to increase enrolment
to increase enrolment
to increase enrolment
to increase enrolment
to increase enrolment
to increase enrolment
to increase enrolment
to increase enrolment
to increase enrolment
to increase enrolment
to increase enrolment
to increase enrolment
to increase enrolment
to increase enrolment
to increase enrolment
to increase enrolment
to increase enrolment
to increase enrolment
to increase enrolment
to increase enrolment
to increase enrolment
to increase enrolment
to increase enrolment
to increase enrolment
to increase enrolment
to increase enrolment
to increase enrolment
to increase enrolment
to increase enrolment
to increase enrolment
to increase enrolment
to increase enrolment
to increase enrolment
to increase enrolment
to increase enrolment
to increase enrolment
to increase enrolment
to increase enrolment
to increase enrolment
to increase enrolment
to increase enrolment
to increase enrolment
to increase enrolment
to increase enrolment
to increase enrolment
to increase enrolment
to increase enrolment
to increase enrolment
to increase enrolment
to increase enrolment
to increase enrolment
to increase enrolment
to increase enrolment
to increase enrolment
to increase enrolment
to increase enrolment
to increase enrolment
to increase enrolment
to increase enrolment
to increase enrolment
to increase enrolment
to increase enrolment
to increase enrolment
to increase enrolment
to increase enrolment
to increase enrolment
to increase enrolment
to increase enrolment
to increase enrolment
to increase enrolment
to increase enrolment
to increase enrolment
to increase enrolment
to increase enrolment
to increase enrolment
to increase enrolment
to increase enrolment
to increase enrolment
to increase enrolment
to increase enrolment
to increase enrolment
to increase enrolment
to increase enrolment
to increase enrolment
to increase enrolment
to increase enrolment
to increase enrolment
to increase enrolment
to increase enrolment
to increase enrolment
to increase enrolment
to increase enrolment
to increase enrolment
to increase enrolment
to increase enrolment
to increase enrolment
to increase enrolment
to increase enrolment
to increase enrolment
to increase enrolment
to increase enrolment
to increase enrolment
to increase enrolment
to increase enrolment
to increase enrolment
to increase enrolment
to increase enrolment
to increase enrolment
to increase enrolment
to increase enrolment
to increase enrolment
to increase enrolment
to increase enrolment
to increase enrolment
to increase enrolment
to increase enrolment
to increase enrolment
to increase enrolment
to increase enrolment
to increase enrolment
to increase enrolment
to increase enrolment
to increase enrolment
to increase enrolment
to increase enrolment
to increase enrolment
to increase enrolment
to increase enrolment
to increase enrolment
to increase enrolment
to increase enrolment
to increase enrolment
to increase enrolment
to increase enrolment
to increase enrolment
to increase enrolment
to increase enrolment
to increase enrolment
to increase enrolment
to increase enrolment
to increase enrolment
to increase enrolment
to increase enrolment
to increase enrolment
to increase enrolment
to increase enrolment
to increase enrolment
to increase enrolment
to increase enrolment
to increase enrolment
to increase enrolment
to increase enrolment
to increase enrolment
to increase enrolment
to increase enrolment
to increase enrolment
to increase enrolment
to increase enrolment
to increase enrolment
to increase enrolment
to increase enrolment
to increase enrolment
to increase enrolment
to increase enrolment
to increase enrolment
to increase enrolment
to increase enrolment
to increase enrolment
to increase enrolment
to increase enrolment
to increase enrolment
to increase enrolment
to increase enrolment
to increase enrolment
to increase enrolment
to increase enrolment
to increase enrolment
to increase enrolment
to increase enrolment
to increase enrolment
to increase enrolment
to increase enrolment
to increase enrolment
to increase enrolment
to increase enrolment
to increase enrolment
to increase enrolment
to increase enrolment
to increase enrolment
to increase enrolment
to increase enrolment
to increase enrolment
to increase enrolment
to increase enrolment
to increase enrolment
to increase enrolment
to increase enrolment
to increase enrolment
to increase enrolment
to increase enrolment
to increase enrolment
to increase enrolment
to increase enrolment
to increase enrolment
to increase enrolment
to increase enrolment
to increase enrolment
to increase enrolment
to increase enrolment
to increase enrolment
to increase enrolment
to increase enrolment
to increase enrolment
to increase enrolment
to increase enrolment
to increase enrolment
to increase enrolment
to increase enrolment
to increase enrolment
to increase enrolment
to increase enrolment
to increase enrolment
to increase enrolment
to increase enrolment
to increase enrolment
to increase enrolment
to increase enrolment
to increase enrolment
to increase enrolment
to increase enrolment
to increase enrolment
to increase enrolment
to increase enrolment
to increase enrolment
to increase enrolment
to increase enrolment
to increase enrolment
to increase enrolment
to increase enrolment
to increase enrolment
to increase enrolment
to increase enrolment
to increase enrolment
to increase enrolment
to increase enrolment
to increase enrolment
to increase enrolment
to increase enrolment
to increase enrolment
to increase enrolment
to increase enrolment
to increase enrolment
to increase enrolment
to increase enrolment
to increase enrolment
to increase enrolment
to increase enrolment
to increase enrolment
to increase enrolment
to increase enrolment
to increase enrolment
to increase enrolment
to increase enrolment
to increase enrolment
to increase enrolment
to increase enrolment
to increase enrolment
to increase enrolment
to increase enrolment
to increase enrolment
to increase enrolment
to increase enrolment
to increase enrolment
to increase enrolment
to increase enrolment
to increase enrolment
to increase enrolment
to increase enrolment
to increase enrolment
to increase enrolment
to increase enrolment
to increase enrolment
to increase enrolment
to increase enrolment
to increase enrolment
to increase enrolment
to increase enrolment
to increase enrolment
to increase enrolment
to increase enrolment
to increase enrolment
to increase enrolment
to increase enrolment
to increase enrolment
to increase enrolment
to increase enrolment
to increase enrolment
to increase enrolment
to increase enrolment
to increase enrolment
to increase enrolment
to increase enrolment
to increase enrolment
to increase enrolment
to increase enrolment
to increase enrolment
to increase enrolment
to increase enrolment
to increase enrolment
to increase enrolment
to increase enrolment
to increase enrolment
to increase enrolment
to increase enrolment
to increase enrolment
to increase enrolment
to increase enrolment
to increase enrolment
to enhance security
to increase enrolment
to increase enrolment
to increase enrolment
to increase enrolment
to increase enrolment
to increase enrolment
to increase enrolment
to increase enrolment
to increase enrolment
to increase enrolment
to increase enrolment
to increase enrolment
to increase enrolment
to increase enrolment
to increase enrolment
to increase enrolment
to increase enrolment
to increase enrolment
to increase enrolment
to increase enrolment
to increase enrolment
to increase enrolment
to increase enrolment
to increase enrolment
to increase enrolment
to increase enrolment
to increase enrolment
to increase enrolment
to increase enrolment
to increase enrolment
to increase enrolment
to increase enrolment
to increase enrolment
to increase enrolment
to increase enrolment
to increase enrolment
to increase enrolment
to increase enrolment
to increase enrolment
to increase enrolment
to increase enrolment
to increase enrolment
to increase enrolment
to increase enrolment
to increase enrolment
to increase enrolment
to increase enrolment
to increase enrolment
to increase enrolment
to increase enrolment
to increase enrolment
to increase enrolment
to increase enrolment
to increase enrolment
to increase enrolment
to increase enrolment
to increase enrolment
to increase enrolment
to increase enrolment
to increase enrolment
to increase enrolment
to increase enrolment
to increase enrolment
to increase enrolment
to increase enrolment
to increase enrolment
to increase enrolment
to increase enrolment
to increase enrolment
to increase enrolment
to increase enrolment
to increase enrolment
to increase enrolment
to increase enrolment
to increase enrolment
to increase enrolment
to increase enrolment
to increase enrolment
to increase enrolment
to increase enrolment
to increase enrolment
to increase enrolment
to increase enrolment
to increase enrolment
to increase enrolment
to increase enrolment
to increase enrolment
to increase enrolment
to increase enrolment
to increase enrolment
to increase enrolment
to increase enrolment
to increase enrolment
to increase enrolment
to increase enrolment
to increase enrolment
to increase enrolment
to increase enrolment
to increase enrolment
to increase enrolment
to increase enrolment
to increase enrolment
to increase enrolment
to increase enrolment
to increase enrolment
to increase enrolment
to increase enrolment
to increase enrolment
to increase enrolment
to increase enrolment
to increase enrolment
to increase enrolment
to increase enrolment
to increase enrolment
to increase enrolment
to increase enrolment
to increase enrolment
to increase enrolment
to increase enrolment
to increase enrolment
to increase enrolment
to increase enrolment
to increase enrolment

## Formula Sheet
GOK
Development Partner
GOK & Development Partner
Yes
No
Compete
Cancel
Defer
Completed
Ongoing
Stalled