## instructions1
INSTRUCTIONS ON COMPLETION OF PROJECT STOCK TAKE TEMPLATE
1. All fields are mandatory and should be populated.
2. DO NOT EDIT the CONFIGURATION worksheet.
3. ONLY populate rows applicable in your respective Counties &Ward Location(s) and Hide the rest of the rows (DO NOT DELETE the Rows).
4. The scope of this exercise is projects started between the year 2013 and 30th June, 2024
5.Remember to SAVE the document after populating the required details in the worksheet.

## Project Stocktaking Template
PROJECT DETAILS | [6 empty] | PROJECT LOCATION |  |  | IMPLEMENTATION DETAILS | [6 empty] | FINANCIAL INFORMATION |  |  |  |  | DISBURSMENT |  |  |  | EXPENDITURE |  |  | PROJECT STATUS |  |  | ACTIONS FOR STALLED |  |  |  | RISKS AND RECOMMENDATIONS |  |  | CLIMATE & DISASTER RISK SCREENING |  | ENVIRONMENTAL , SOCIAL AND OCCUPATIONAL HEALTH, SAFETY AND GENDER SCREENING |  | TECHNICAL, FINANCIAL, AND ECONOMIC VIABILITY SCREENING |  | ADDITIONAL REMARKS
S/No. | Project Name/Title | Project Description | Project Goal/Objective | Project Output | Project Code (Budget line) | Budget Item Name | Sub-County | Ward | Geographic Location (Latitude & Longitude) | Sector/ Vote Name | Department, Directorate, Units, Agencies | Implementing Department/Agency / Muncipalities | Date of Approval/Financial Approval | Project Start Date | Expected Project Completion Date | Actual Project Completion Date | Estimated Project Cost (Kshs.) | Approved Project Cost | Funds available in the specific year | Project Funding Source | If Development Partners, Please specify . | County Government component in the Project Cost (Kshs.) | Development Partner component in the Project Cost (Kshs.) | Total Disbursed Funds as at 30th June 2024 (Kshs.) | Percentage (%) Disbursed Amount = (Disbursed/ Approved) | Expenditure to date | Pending Bill/Outstanding commitment not paid but work done | Project Balance (Kshs.) i.e (Approved Project Cost - Disbursed Amount) | Project Status at the time of the Exercise (i.e Completed, Ongoing, Stalled) | % completion for ongoing/stalled projects | If Stalled, what is the percentage (%) completion at the time of stalling (Physical completion status) | If stalled give reasons; | Year the project stalled | Time required to complete the stalled project (in months) | Estimated cost required to complete the stalled project (in Kshs.) | Is the project still appering in the budget or is it still receiving funds in the annual budgets? (Yes/No) | Recommendation for the Stalled Project (Complete/ Cancel/ Defer) | Identify the Risks associated with the stalled/completed/ongoing project ie. (Contractual/legal/Financial/Environmental etc.) | Has this project been screened for Climate & Disaster Risks? Yes/No | If yes, what action has been taken to mitigate? IF Not, give reasons and the immediate plans for conducting the screening. | Has the project been screened for Environmental, Social, Occupational Health, Safety and gender risks | If yes, what action has been taken to mitigate? IF Not, give reasons and the immediate plans for conducting the screening. | Has the project been screened for Technical, Financial, and Economic Viability and a fesibility report been prepared? (yes/No) | If yes, what action has been taken to mitigate? IF Not, what is being used to measure viability of the project? Additionally, indicate immediate plans on when the screening and feasibility study will be undertaken | REMARKS
1 | Eluai Enkaroni Borehole | Drilling and equipping of borehole | Increase access to safe and affordable water | Borehole drilled and equipped |  | Eluai Enkaroni Borehole | Kajiado Central | Purko |  | Water, Irrigation, Environment and Natural Resources | Water & Irrigation | Water & Irrigation | 2013-06-30 | 2013-09-01 | 2014-06-30 |  | 5000000 | 5000000 | 5000000 | CGK | N/A | 5000000 | 0 | 788000 | 15.76% | 788000 | 4212000 | 4212000 | Stalled | 16% | 16% | Dry borehole | 2014 | 6 | 8000000 | No | Defer | Financial | No | Propose budget for screening | No | Propose budget for screening | Yes | Fesibility studies and design | Dry borehole
2 | Ilparua Borehole | Drilling and equipping of borehole | Increase access to safe and affordable water | Borehole drilled and equipped |  | Ilparua Borehole | Kajiado Central | Purko |  | Water, Irrigation, Environment and Natural Resources | Water & Irrigation | Water & Irrigation | 2013-06-30 | 2013-09-01 | 2014-06-30 |  | 5000000 | 5000000 | 5000000 | CGK | N/A | 5000000 | 0 | 0 | 0% | 0 | 5000000 | 5000000 | Stalled | 0% | 0% |  |  |  |  | No | Defer | Legal | No | Propose budget for screening | No | Propose budget for screening | Yes | Fesibility studies and design | Site dispute. Project has not taken off.
3 | Emukutan Borehole | Drilling and equipping of borehole | Increase access to safe and affordable water | Borehole drilled and equipped |  | Emukutan Borehole | Kajiado Central | Matapato North |  | Water, Irrigation, Environment and Natural Resources | Water & Irrigation | Water & Irrigation | 2013-06-30 | 2013-09-01 | 2014-06-30 |  | 6500000 | 6500000 | 6500000 | CGK | N/A | 6500000 | 0 | 6500000 | 100% | 6500000 | 0 | 0 | Completed | [6 empty] | No |  | Environmental | No | Propose budget for screening | No | Propose budget for screening | Yes | Fesibility studies and design | Construction of cattle trough to be done in FY 2016/17.
4 | Endoinyo Borehole | Drilling and equipping of borehole | Increase access to safe and affordable water | Borehole drilled and equipped |  | Endoinyo Borehole | Kajiado Central | Matapato North |  | Water, Irrigation, Environment and Natural Resources | Water & Irrigation | Water & Irrigation | 2013-06-30 | 2013-09-01 | 2014-06-30 |  | 7000000 | 7000000 | 7000000 | CGK | N/A | 7000000 | 0 | 7000000 | 100% | 7000000 | 0 | 0 | Completed | [6 empty] | No |  | Environmental | No | Propose budget for screening | No | Propose budget for screening | Yes | Fesibility studies and design | Construction of cattle trough to be done in FY 2016/17.
5 | Iltareto Borehole | Drilling and Equipping | Increase access to safe and affordable water | Borehole drilled and equipped |  | Iltareto Borehole | Kajiado Central | Dalalekutuk |  | Water, Irrigation, Environment and Natural Resources | Water & Irrigation | Water & Irrigation | 2013-06-30 | 2013-09-01 | 2014-06-30 |  | 5000000 | 5000000 | 5000000 | CGK | N/A | 5000000 | 0 | 1900000 | 38% | 1900000 | 3100000 | 3100000 | Stalled | 38% | 38% | Site dispute | 2014 | 6 | 4000000 | No | Defer | Legal | No | Propose budget for screening | No | Propose budget for screening | Yes | Fesibility studies and design | Site dispute. Awaiting resolution from County commissioner.
6 | Kimana-Tikondo Borehole | Drilling and equipping of borehole | Increase access to safe and affordable water | Borehole drilled and equipped |  | Kimana-Tikondo Borehole | Kajiado South | Kimana |  | Water, Irrigation, Environment and Natural Resources | Water & Irrigation | Water & Irrigation | 2013-06-30 | 2013-09-01 | 2014-06-30 |  | 6875660 | 6875660 | 6875660 | CGK | N/A | 6875660 | 0 | 6875660 | 100% | 6875660 | 0 | 0 | Completed | [6 empty] | No |  | Environmental | No | Propose budget for screening | No | Propose budget for screening | Yes | Fesibility studies and design | 3km pipeline extension and an elevated tank were proposed for the next FY
7 | Maisuyati Borehole | Drilling and equipping of borehole | Increase access to safe and affordable water | Borehole drilled and equipped |  | Maisuyati Borehole | Kajiado South | Kimana |  | Water, Irrigation, Environment and Natural Resources | Water & Irrigation | Water & Irrigation | 2013-06-30 | 2013-09-01 | 2014-06-30 |  | 6821400 | 6821400 | 6821400 | CGK | N/A | 6821400 | 0 | 6821400 | 100% | 6821400 | 0 | 0 | Completed | [6 empty] | No |  | Environmental | No | Propose budget for screening | No | Propose budget for screening | Yes | Fesibility studies and design | Complete and operational
8 | Enkariak Ronkena Borehole | Drilling and equipping of borehole | Increase access to safe and affordable water | Borehole drilled and equipped |  | Enkariak Ronkena Borehole | Kajiado South | Kimana |  | Water, Irrigation, Environment and Natural Resources | Water & Irrigation | Water & Irrigation | 2013-06-30 | 2013-09-01 | 2014-06-30 |  | 7700000 | 7700000 | 7700000 | CGK | N/A | 7700000 | 0 | 7700000 | 100% | 7700000 | 0 | 0 | Completed | [6 empty] | No |  | Environmental | No | Propose budget for screening | No | Propose budget for screening | Yes | Fesibility studies and design | Complete and operational. Requires a booster pump to serve the community residing on the upper belt
9 | Entonet Borehole | Drilling and equipping of borehole | Increase access to safe and affordable water | Borehole drilled and equipped |  | Entonet Borehole | Kajiado South | Entonet/ Lenkisim |  | Water, Irrigation, Environment and Natural Resources | Water & Irrigation | Water & Irrigation | 2013-06-30 | 2013-09-01 | 2014-06-30 |  | 5000000 | 5000000 | 5000000 | CGK | N/A | 5000000 | 0 | 1200115 | 24% | 1200115 | 3799885 | 3799885 | Completed | [6 empty] | No |  | Environmental | No | Propose budget for screening | No | Propose budget for screening | Yes | Fesibility studies and design | Complete and operational. Yield -24m3/hr.
10 | Emesasu Borehole | Drilling and equipping of borehole | Increase access to safe and affordable water | Borehole drilled and equipped |  | Emesasu Borehole | Kajiado South | Kuku |  | Water, Irrigation, Environment and Natural Resources | Water & Irrigation | Water & Irrigation | 2013-06-30 | 2013-09-01 | 2014-06-30 |  | 6031700 | 6031700 | 6031700 | CGK | N/A | 6031700 | 0 | 6031700 | 100% | 6031700 | 0 | 0 | Completed | [6 empty] | No |  | Environmental | No | Propose budget for screening | No | Propose budget for screening | Yes | Fesibility studies and design | Complete and operational
11 | Loitokitok Borehole | borehole drilling and equipping | Increase access to safe and affordable water | Borehole drilled and equipped |  | Loitokitok Borehole | Kajiado South | Kuku |  | Water, Irrigation, Environment and Natural Resources | Water & Irrigation | Water & Irrigation | 2013-06-30 | 2013-09-01 | 2014-06-30 |  | 6200000 | 6200000 | 6200000 | CGK | N/A | 6200000 | 0 | 6200000 | 100% | 6200000 | 0 | 0 | Completed | [6 empty] | No |  | Environmental | No | Propose budget for screening | No | Propose budget for screening | Yes | Fesibility studies and design | Complete and operational
12 | Kuku Borehole | Drilling and equipping of borehole | Increase access to safe and affordable water | Borehole drilled and equipped |  | Kuku Borehole | Kajiado South | Kuku |  | Water, Irrigation, Environment and Natural Resources | Water & Irrigation | Water & Irrigation | 2013-06-30 | 2013-09-01 | 2014-06-30 |  | 9886800 | 9886800 | 9886800 | CGK | N/A | 9886800 | 0 | 9886800 | 100% | 9886800 | 0 | 0 | Completed | [6 empty] | No |  | Environmental | No | Propose budget for screening | No | Propose budget for screening | Yes | Fesibility studies and design | Complete and operational
13 | Oloosirkon Borehole | Drilling and equipping of borehole | Increase access to safe and affordable water | Borehole drilled and equipped |  | Oloosirkon Borehole | Kajiado East | Oloosirkon/ Sholinke |  | Water, Irrigation, Environment and Natural Resources | Water & Irrigation | Water & Irrigation | 2013-06-30 | 2013-09-01 | 2014-06-30 |  | 5000000 | 5000000 | 5000000 | CGK | N/A | 5000000 | 0 | 1900000 | 38% | 1900000 | 3100000 | 3100000 | Stalled | 38% | 38% | Dry borehole | 2014 | 6 | 8000000 | No | Defer | Financial | No | Propose budget for screening | No | Propose budget for screening | Yes | Fesibility studies and design | Dry borehole
14 | Emarti borehole | Drilling & Equipping | Increase access to safe and affordable water | Borehole drilled and equipped |  | Emarti borehole | Kajiado East | Imaroro |  | Water, Irrigation, Environment and Natural Resources | Water & Irrigation | Water & Irrigation | 2013-06-30 | 2013-09-01 | 2014-06-30 |  | 5000000 | 5000000 | 5000000 | CGK | N/A | 5000000 | 0 | 1324000 | 26.48% | 1324000 | 3676000 | 3676000 | Stalled | 26% | 26% | Dry borehole | 2014 | 6 | 7000000 | No | Defer | Financial | No | Propose budget for screening | No | Propose budget for screening | Yes | Fesibility studies and design | Dry borehole
15 | Arroi borehole | Drilling and equipping of borehole | Increase access to safe and affordable water | Borehole drilled and equipped |  | Arroi borehole | Kajiado East | Imaroro |  | Water, Irrigation, Environment and Natural Resources | Water & Irrigation | Water & Irrigation | 2013-06-30 | 2013-09-01 | 2014-06-30 |  | 5000000 | 5000000 | 5000000 | CGK | N/A | 5000000 | 0 | 1924816 | 38.5% | 1924816 | 3075184 | 3075184 | Stalled | 38% | 38% | Low yield | 2014 | 6 | 7000000 | No | Defer | Financial | No | Propose budget for screening | No | Propose budget for screening | Yes | Fesibility studies and design | Yield = 1m3/hr
16 | Ilmao Borehole | Drilling and Equipping | Increase access to safe and affordable water | Borehole drilled and equipped |  | Ilmao Borehole | Kajiado East | Kenyewa |  | Water, Irrigation, Environment and Natural Resources | Water & Irrigation | Water & Irrigation | 2013-06-30 | 2013-09-01 | 2014-06-30 |  | 6500000 | 6500000 | 6500000 | CGK | N/A | 6500000 | 0 | 6500000 | 100% | 6500000 | 0 | 0 | Completed | [6 empty] | No |  | Environmental | No | Propose budget for screening | No | Propose budget for screening | Yes | Fesibility studies and design | Complete and operational
17 | Kitengela Bus Park Borehole | Drilling and equipping of a borehole | Increase access to safe and affordable water | Borehole drilled and equipped |  | Kitengela Bus Park Borehole | Kajiado East | Oloosirkon/ Sholinke |  | Water, Irrigation, Environment and Natural Resources | Water & Irrigation | Water & Irrigation | 2013-06-30 | 2013-09-01 | 2014-06-30 |  | 5000000 | 5000000 | 5000000 | CGK | N/A | 5000000 | 0 | 5000000 | 100% | 5000000 | 0 | 0 | Completed | [6 empty] | No |  | Environmental | No | Propose budget for screening | No | Propose budget for screening | Yes | Fesibility studies and design | Complete and operational
18 | Ndikirro borehole | Drilling and equipping a borehole | Increase access to safe and affordable water | Borehole drilled and equipped |  | Ndikirro borehole | Kajiado West | Ewaso Kedong |  | Water, Irrigation, Environment and Natural Resources | Water & Irrigation | Water & Irrigation | 2013-06-30 | 2013-09-01 | 2014-06-30 |  | 5000000 | 5000000 | 5000000 | CGK | N/A | 5000000 | 0 | 1900000 | 38% | 1900000 | 3100000 | 3100000 | Stalled | 38% | 38% | Low yield | 2014 | 6 | 8000000 | No | Defer | Financial | No | Propose budget for screening | No | Propose budget for screening | Yes | Fesibility studies and design | Yield of the borehole very low. Recommended for Solar equipping.
19 | Iyarat Borehole | Drilling and equipping of borehole | Increase access to safe and affordable water | Borehole drilled and equipped |  | Iyarat Borehole | Kajiado West | Loodokilani |  | Water, Irrigation, Environment and Natural Resources | Water & Irrigation | Water & Irrigation | 2013-06-30 | 2013-09-01 | 2014-06-30 |  | 5000000 | 5000000 | 5000000 | CGK | N/A | 5000000 | 0 | 987000 | 19.74% | 987000 | 4013000 | 4013000 | Stalled | 18% | 18% | Dry borehole | 2014 | 6 | 8000000 | No | Defer | Financial | No | Propose budget for screening | No | Propose budget for screening | Yes | Fesibility studies and design | Dry borehole
20 | Emurukea Borehole | Drilling and equipping of borehole | Increase access to safe and affordable water | Borehole drilled and equipped |  | Emurukea Borehole | Kajiado West | loodokilani |  | Water, Irrigation, Environment and Natural Resources | Water & Irrigation | Water & Irrigation | 2013-06-30 | 2013-09-01 | 2014-06-30 |  | 7000000 | 7000000 | 7000000 | CGK | N/A | 7000000 | 0 | 1522000 | 21.74% | 1522000 | 5478000 | 5478000 | Stalled | 21% | 21% | Dry borehole | 2014 | 6 | 8000000 | No | Defer | Environmental | No | Propose budget for screening | No | Propose budget for screening | Yes | Fesibility studies and design | Dry borehole
21 | Demo Farm Water Project | Drilling, equipping of Borehole and construction of 4.2Kms pipeline from Source to AIC Girls' Primary School | Increase access to safe and affordable water | 1. Borehole drilled and equipped 2. Pipeline constructed |  | Demo Farm Water Project | Kajiado Central | Ildamat |  | Water, Irrigation, Environment and Natural Resources | Water & Irrigation | Water & Irrigation | 2013-06-30 | 2013-09-01 | 2014-06-30 |  | 6804014 | 6804014 | 6804014 | CGK | N/A | 6804014 | 0 | 6804014 | 100% | 6804014 | 0 | 0 | Completed | [6 empty] | No |  | Environmental | No | Propose budget for screening | No | Propose budget for screening | Yes | Fesibility studies and design | Complete and operational
22 | Demo Farm Pan | Construction of pan | Increase access to safe and affordable water | Water pan constructed |  | Demo Farm Pan | Kajiado Central | Ildamat |  | Water, Irrigation, Environment and Natural Resources | Water & Irrigation | Water & Irrigation | 2013-06-30 | 2013-09-01 | 2014-06-30 |  | 5000000 | 5000000 | 5000000 | CGK | N/A | 5000000 | 0 | 5000000 | 100% | 5000000 | 0 | 0 | Completed | [6 empty] | No |  | Environmental | No | Propose budget for screening | No | Propose budget for screening | Yes | Fesibility studies and design | Complete and operational
23 | Piping of Headquarters’ Offices | Construction of a pipeline and connect to County Executive Residence, County Government Offices, County Assembly, | Increase access to safe and affordable water | Pipeline constructed |  | Piping of Headquarters’ Offices | Kajiado Central | Ildamat |  | Water, Irrigation, Environment and Natural Resources | Water & Irrigation | Water & Irrigation | 2013-06-30 | 2013-09-01 | 2014-06-30 |  | 7500000 | 7500000 | 7500000 | CGK | N/A | 7500000 | 0 | 7500000 | 100% | 7500000 | 0 | 0 | Completed | [6 empty] | No |  | Environmental | No | Propose budget for screening | No | Propose budget for screening | Yes | Fesibility studies and design | Complete and operational
24 | Maparasha Water Pan | Construction of water pan at Emarti | Increase access to safe and affordable water | Water pan constructed |  | Maparasha Water Pan | Kajiado Central | Matapato North |  | Water, Irrigation, Environment and Natural Resources | Water & Irrigation | Water & Irrigation | 2013-06-30 | 2013-09-01 | 2014-06-30 |  | 15000000 | 15000000 | 15000000 | CGK | N/A | 15000000 | 0 | 15000000 | 100% | 15000000 | 0 | 0 | Completed | [6 empty] | No |  | Environmental | No | Propose budget for screening | No | Propose budget for screening | Yes | Fesibility studies and design | Complete and operational
25 | Tikoko Springs | Construction of pipeline and spring intakes | Increase access to safe and affordable water | 1. Spring developed 2. Pipeline constructed |  | Tikoko Springs | Kajiado Central | Matapato south |  | Water, Irrigation, Environment and Natural Resources | Water & Irrigation | Water & Irrigation | 2013-06-30 | 2013-09-01 | 2014-06-30 |  | 7687400 | 7687400 | 7687400 | CGK | N/A | 7687400 | 0 | 7687400 | 100% | 7687400 | 0 | 0 | Completed | [6 empty] | No |  | Environmental | No | Propose budget for screening | No | Propose budget for screening | Yes | Fesibility studies and design | Complete and operational
26 | Esonorua water project | Construction of intake, installation of pumping equipment and construction of pipeline | Increase access to safe and affordable water | 1. Spring developed 2. Pipeline constructed |  | Esonorua water project | Kajiado West | Keekonyokie |  | Water, Irrigation, Environment and Natural Resources | Water & Irrigation | Water & Irrigation | 2013-06-30 | 2013-09-01 | 2014-06-30 |  | 5000000 | 5000000 | 5000000 | CGK | N/A | 5000000 | 0 | 5000000 | 100% | 5000000 | 0 | 0 | Completed | [6 empty] | No |  | Financial | No | Propose budget for screening | No | Propose budget for screening | Yes | Fesibility studies and design | Phase one complete; Phase II proposed for funding in FY 2014/15
27 | Ewuaso Nyiro Pipeline | Piping from Ewuaso nyiro intake to musenke | Increase access to safe and affordable water | 1. Spring developed 2. Pipeline constructed 3. Storage tank constructed |  | Ewuaso Nyiro Pipeline | Kajiado West | Musenke |  | Water, Irrigation, Environment and Natural Resources | Water & Irrigation | Water & Irrigation | 2013-06-30 | 2013-09-01 | 2014-06-30 |  | 15000000 | 15000000 | 15000000 | CGK | N/A | 15000000 | 0 | 15000000 | 100% | 15000000 | 0 | 0 | Completed | [6 empty] | No |  | Environmental | No | Propose budget for screening | No | Propose budget for screening | Yes | Fesibility studies and design | Complete and operational
28 | Enkii Water Pan | Construction of water Pan | Increase access to safe and affordable water | Water pan constructed |  | Enkii Water Pan | Kajiado South | Kuku |  | Water, Irrigation, Environment and Natural Resources | Water & Irrigation | Water & Irrigation | 2013-06-30 | 2013-09-01 | 2014-06-30 |  | 10000000 | 10000000 | 10000000 | CGK | N/A | 10000000 | 0 | 10000000 | 100% | 10000000 | 0 | 0 | Completed | [6 empty] | No |  | Environmental | No | Propose budget for screening | No | Propose budget for screening | Yes | Fesibility studies and design | Complete and operational
29 | Nolturesh – Olkaria WP Pipeline | Construction of pipeline. | Increase access to safe and affordable water | Pipeline constructed |  | Nolturesh – Olkaria WP Pipeline | Kajiado South | Kuku |  | Water, Irrigation, Environment and Natural Resources | Water & Irrigation | Water & Irrigation | 2013-06-30 | 2013-09-01 | 2014-06-30 |  | 5000000 | 5000000 | 5000000 | CGK | N/A | 5000000 | 0 | 5000000 | 100% | 5000000 | 0 | 0 | Completed | [6 empty] | No |  | Environmental | No | Propose budget for screening | No | Propose budget for screening | Yes | Fesibility studies and design | Complete and operational
30 | Iltipikuani Earth Dam | Construction of earth dam | Increase access to safe and affordable water | Earth dam constructed |  | Iltipikuani Earth Dam | Kajiado East | Imaroro |  | Water, Irrigation, Environment and Natural Resources | Water & Irrigation | Water & Irrigation | 2013-06-30 | 2013-09-01 | 2014-06-30 |  | 10000000 | 10000000 | 10000000 | CGK | N/A | 10000000 | 0 | 10000000 | 100% | 10000000 | 0 | 0 | Completed | [6 empty] | No |  | Environmental | No | Propose budget for screening | No | Propose budget for screening | Yes | Fesibility studies and design | Complete and operational
31 | Oloitokitok Borehole-Kikelelua-Kibaoni Pipeline | Piping from Oloitokitok borehole to Kikeleleu-Kimbaoni | Increase access to safe and affordable water | Pipeline constructed |  | Oloitokitok Borehole-Kikelelua-Kibaoni Pipeline | Kajiado South | Rombo |  | Water, Irrigation, Environment and Natural Resources | Water & Irrigation | Water & Irrigation | 2013-06-30 | 2013-09-01 | 2014-06-30 |  | 5000000 | 5000000 | 5000000 | CGK | N/A | 5000000 | 0 | 5000000 | 100% | 5000000 | 0 | 0 | Completed | [6 empty] | No |  |  | No | Propose budget for screening | No | Propose budget for screening | Yes | Fesibility studies and design | Complete and operational
32 | Esambu -Ilchalai pipeline | Piping of Esambu to Ilchalai (18 km) | Increase access to safe and affordable water | Pipeline constructed |  | Esambu -Ilchalai pipeline | Kajiado South | Imbirikani |  | Water, Irrigation, Environment and Natural Resources | Water & Irrigation | Water & Irrigation | 2013-06-30 | 2013-09-01 | 2014-06-30 |  | 9604157 | 9604157 | 9604157 | CGK | N/A | 9604157 | 0 | 9604157 | 100% | 9604157 | 0 | 0 | Completed | [6 empty] | No |  |  | No | Propose budget for screening | No | Propose budget for screening | Yes | Fesibility studies and design | Complete and operational
33 | Kajiado TownToilet Block | Construction of public toilet | Increase access to adequate and equitable sanitation and hygiene | Public toilet constructed |  | Kajiado TownToilet Block | Kajiado Central | Ildamat |  | Water, Irrigation, Environment and Natural Resources | Water & Irrigation | Water & Irrigation | 2013-06-30 | 2013-09-01 | 2014-06-30 |  | 6000000 | 6000000 | 6000000 | CGK | N/A | 6000000 | 0 | 6000000 | 100% | 6000000 | 0 | 0 | Completed | [6 empty] | No |  | Environmental | No | Propose budget for screening | No | Propose budget for screening | Yes | Fesibility studies and design | Complete and operational
34 | Namanga Town Toilet Block | Construction of public toilet | Increase access to adequate and equitable sanitation and hygiene | Public toilet constructed |  | Namanga Town Toilet Block | Kajiado Central | Matapato South |  | Water, Irrigation, Environment and Natural Resources | Water & Irrigation | Water & Irrigation | 2013-06-30 | 2013-09-01 | 2014-06-30 |  | 6000000 | 6000000 | 6000000 | CGK | N/A | 6000000 | 0 | 6000000 | 100% | 6000000 | 0 | 0 | Completed | [6 empty] | No |  | Environmental | No | Propose budget for screening | No | Propose budget for screening | Yes | Fesibility studies and design | Complete and operational
35 | Nkaimurunya Market Toilet Block | Construction of public Toilet | Increase access to adequate and equitable sanitation and hygiene | Public toilet constructed |  | Nkaimurunya Market Toilet Block | Kajiado North | Nkaimurunya |  | Water, Irrigation, Environment and Natural Resources | Water & Irrigation | Water & Irrigation | 2013-06-30 | 2013-09-01 | 2014-06-30 |  | 6000000 | 6000000 | 6000000 | CGK | N/A | 6000000 | 0 | 6000000 | 100% | 6000000 | 0 | 0 | Completed | [6 empty] | No |  | Environmental | No | Propose budget for screening | No | Propose budget for screening | Yes | Fesibility studies and design | Complete and operational
36 | Kitengela Market Toilet Block | Construction of public Toilet | Increase access to adequate and equitable sanitation and hygiene | Public toilet constructed |  | Kitengela Market Toilet Block | Kajiado East | Kitengela town |  | Water, Irrigation, Environment and Natural Resources | Water & Irrigation | Water & Irrigation | 2013-06-30 | 2013-09-01 | 2014-06-30 |  | 6000000 | 6000000 | 6000000 | CGK | N/A | 6000000 | 0 | 6000000 | 100% | 6000000 | 0 | 0 | Completed | [6 empty] | No |  | Environmental | No | Propose budget for screening | No | Propose budget for screening | Yes | Fesibility studies and design | Complete and operational
37 | Kitengela Town (Bus Park) Toilet Block | Construction of public Toilet | Increase access to adequate and equitable sanitation and hygiene | Public toilet constructed |  | Kitengela Town (Bus Park) Toilet Block | Kajiado East | Olosirikon/ Shorinke |  | Water, Irrigation, Environment and Natural Resources | Water & Irrigation | Water & Irrigation | 2013-06-30 | 2013-09-01 | 2014-06-30 |  | 6000000 | 6000000 | 6000000 | CGK | N/A | 6000000 | 0 | 6000000 | 100% | 6000000 | 0 | 0 | Completed | [6 empty] | No |  | Environmental | No | Propose budget for screening | No | Propose budget for screening | Yes | Fesibility studies and design | Complete and operational
38 | Kiserian Market Toilet Block | Construction of public Toilet | Increase access to adequate and equitable sanitation and hygiene | Public toilet constructed |  | Kiserian Market Toilet Block | Kajiado West | Kekonyokie |  | Water, Irrigation, Environment and Natural Resources | Water & Irrigation | Water & Irrigation | 2013-06-30 | 2013-09-01 | 2014-06-30 |  | 6000000 | 6000000 | 6000000 | CGK | N/A | 6000000 | 0 | 6000000 | 100% | 6000000 | 0 | 0 | Completed | [6 empty] | No |  | Environmental | No | Propose budget for screening | No | Propose budget for screening | Yes | Fesibility studies and design | Complete and operational
39 | Kimana Market Toilet Block | Construction of public Toilet | Increase access to adequate and equitable sanitation and hygiene | Public toilet constructed |  | Kimana Market Toilet Block | Kajiado South | Kimana |  | Water, Irrigation, Environment and Natural Resources | Water & Irrigation | Water & Irrigation | 2013-06-30 | 2013-09-01 | 2014-06-30 |  | 6000000 | 6000000 | 6000000 | CGK | N/A | 6000000 | 0 | 6000000 | 100% | 6000000 | 0 | 0 | Completed | [6 empty] | No |  | Environmental | No | Propose budget for screening | No | Propose budget for screening | Yes | Fesibility studies and design | Complete and operational
40 | Loitokitok town (Ololopon) Toilet Block | Construction of public Toilet | Increase access to adequate and equitable sanitation and hygiene | Public toilet constructed |  | Loitokitok town (Ololopon) Toilet Block | Kajiado South | Kuku |  | Water, Irrigation, Environment and Natural Resources | Water & Irrigation | Water & Irrigation | 2013-06-30 | 2013-09-01 | 2014-06-30 |  | 6000000 | 6000000 | 6000000 | CGK | N/A | 6000000 | 0 | 6000000 | 100% | 6000000 | 0 | 0 | Completed | [6 empty] | No |  | Environmental | No | Propose budget for screening | No | Propose budget for screening | Yes | Fesibility studies and design | Complete and operational
41 | Matepesi Canal. | Construction of canal. | Increase area under irrigation | Canal constructed |  | Matepesi Canal. | Kajiado South | Rombo |  | Water, Irrigation, Environment and Natural Resources | Water & Irrigation | Water & Irrigation | 2013-06-30 | 2013-09-01 | 2014-06-30 |  | 5000000 | 5000000 | 5000000 | CGK | N/A | 5000000 | 0 | 4160884 | 83.22% | 4160884 | 839116 | 839116 | Completed | [6 empty] | No |  | Environmental | No | Propose budget for screening | No | Propose budget for screening | Yes | Fesibility studies and design | Complete and operational
42 | Enkongu Furrow | Construction of Enkongu furrow | Increase area under irrigation | Furrow constructed |  | Enkongu Furrow | Kajiado South | Mbirikani/ Eselenkei |  | Water, Irrigation, Environment and Natural Resources | Water & Irrigation | Water & Irrigation | 2013-06-30 | 2013-09-01 | 2014-06-30 |  | 5000000 | 5000000 | 5000000 | CGK | N/A | 5000000 | 0 | 4315010 | 86.3% | 4315010 | 684990 | 684990 | Completed | [6 empty] | No |  | Environmental | No | Propose budget for screening | No | Propose budget for screening | Yes | Fesibility studies and design | Complete and operational
43 | Kimana Mathare Canal | Construction of Kimana Mathare canal | Increase area under irrigation | Canal constructed |  | Kimana Mathare Canal | Kajiado South | Kimana |  | Water, Irrigation, Environment and Natural Resources | Water & Irrigation | Water & Irrigation | 2013-06-30 | 2013-09-01 | 2014-06-30 |  | 5000000 | 5000000 | 5000000 | CGK | N/A | 5000000 | 0 | 1562184 | 31.24% | 1562184 | 3437816 | 3437816 | Completed | [6 empty] | No |  | Environmental | No | Propose budget for screening | No | Propose budget for screening | Yes | Fesibility studies and design | Complete and operational
44 | Olooltepesi Canal | Extension of Olooltepesi canal | Increase area under irrigation | Canal extended |  | Olooltepesi Canal | Kajiado South | Rombo |  | Water, Irrigation, Environment and Natural Resources | Water & Irrigation | Water & Irrigation | 2013-06-30 | 2013-09-01 | 2014-06-30 |  | 5000000 | 5000000 | 5000000 | CGK | N/A | 5000000 | 0 | 5000000 | 100% | 5000000 | 0 | 0 | Completed | [6 empty] | No |  | Environmental | No | Propose budget for screening | No | Propose budget for screening | Yes | Fesibility studies and design | Complete and operational
45 | Kisioki Spring Protection | Spring protection | Increase area under irrigation | Spring protected |  | Kisioki Spring Protection | Kajiado South | Rombo |  | Water, Irrigation, Environment and Natural Resources | Water & Irrigation | Water & Irrigation | 2013-06-30 | 2013-09-01 | 2014-06-30 |  | 5000000 | 5000000 | 5000000 | CGK | N/A | 5000000 | 0 | 5000000 | 100% | 5000000 | 0 | 0 | Completed | [6 empty] | No |  | Financial | No | Propose budget for screening | No | Propose budget for screening | Yes | Fesibility studies and design | Complete and operational
46 | Namelok Canal | Construction of Namelok canal | Increase area under irrigation | Canal constructed |  | Namelok Canal | Kajiado South | Entonet |  | Water, Irrigation, Environment and Natural Resources | Water & Irrigation | Water & Irrigation | 2013-06-30 | 2013-09-01 | 2014-06-30 |  | 5000000 | 5000000 | 5000000 | CGK | N/A | 5000000 | 0 | 5000000 | 100% | 5000000 | 0 | 0 | Completed | [6 empty] | No |  | Environmental | No | Propose budget for screening | No | Propose budget for screening | Yes | Fesibility studies and design | Complete and operational
47 | Construction of Pakase Canal | Construction of intake and canal | Increase area under irrigation | Canal constructed |  | Construction of Pakase Canal | Kajiado West | Magadi |  | Water, Irrigation, Environment and Natural Resources | Water & Irrigation | Water & Irrigation | 2013-06-30 | 2013-09-01 | 2014-06-30 |  | 5000000 | 5000000 | 5000000 | CGK | N/A | 5000000 | 0 | 1652030 | 33.04% | 1652030 | 3347970 | 3347970 | Stalled | 33% | 33% | Contractor abadonded the site | 2014 | 6 | 5000000 | No | Defer | Financial | No | Propose budget for screening | No | Propose budget for screening | Yes | Fesibility studies and design | Recommended for termination
48 | Nkama Rock Catchment | Rock catchment development. Construction of 100m3 masonry tank | Increase access to safe and affordable water | Rock catchment constructed |  | Nkama Rock Catchment | Kajiado West | Iloodokilani |  | Water, Irrigation, Environment and Natural Resources | Water & Irrigation | Water & Irrigation | 2014-06-30 | 2014-09-01 | 2015-06-30 |  | 2000000 | 2000000 | 2000000 | CGK | N/A | 2000000 | 0 | 1995046 | 99.75% | 1995046 | 4954 | 4954 | Completed | [6 empty] | No |  | Environmental | No | Propose budget for screening | No | Propose budget for screening | Yes | Fesibility studies and design | Complete and operational
49 | CFC Community Borehole | Borehole equipping | Increase access to safe and affordable water | Borehole equipped |  | CFC Community Borehole | Kajiado West | Iloodokilani |  | Water, Irrigation, Environment and Natural Resources | Water & Irrigation | Water & Irrigation | 2014-06-30 | 2014-09-01 | 2015-06-30 |  | 4000000 | 4000000 | 4000000 | CGK | N/A | 4000000 | 0 | 3968000 | 99.2% | 1900000 | 32000 | 32000 | Completed | [8 empty] | Financial | No | Propose budget for screening | No | Propose budget for screening | Yes | Fesibility studies and design | Complete and operational
50 | Oldepe Borehole | Drilling and equipping of borehole | Increase access to safe and affordable water | Borehole drilled and equipped |  | Oldepe Borehole | Kajiado West | Mosiro |  | Water, Irrigation, Environment and Natural Resources | Water & Irrigation | Water & Irrigation | 2014-06-30 | 2014-09-01 | 2015-06-30 |  | 5000000 | 5000000 | 5000000 | CGK | N/A | 5000000 | 0 | 2667000 | 53.34% | 2667000 | 2333000 | 2333000 | Stalled | 51% | 51% | Dry borehole | 2015 | 6 | 8000000 | No | Defer | Financial | No | Propose budget for screening | No | Propose budget for screening | Yes | Fesibility studies and design | Dry borehole
51 | Ilmariani Borehole | Drilling and equipping of borehole | Increase access to safe and affordable water | Borehole drilled and equipped |  | Ilmariani Borehole | Kajiado West | Mosiro |  | Water, Irrigation, Environment and Natural Resources | Water & Irrigation | Water & Irrigation | 2014-06-30 | 2014-09-01 | 2015-06-30 |  | 5000000 | 5000000 | 5000000 | CGK | N/A | 5000000 | 0 | 0 | 0% | 0 | 5000000 | 5000000 | Stalled | 56% | 56% | Dry borehole | 2015 | 6 | 8000000 | No | Defer | Financial | No | Propose budget for screening | No | Propose budget for screening | Yes | Fesibility studies and design | Dry borehole
52 | Eiti Borehole | Drilling and equipping of borehole | Increase access to safe and affordable water | Borehole drilled and equipped |  | Eiti Borehole | Kajiado West | Mosiro |  | Water, Irrigation, Environment and Natural Resources | Water & Irrigation | Water & Irrigation | 2014-06-30 | 2014-09-01 | 2015-06-30 |  | 5000000 | 5000000 | 5000000 | CGK | N/A | 5000000 | 0 | 2245000 | 44.9% | 2245000 | 2755000 | 2755000 | Stalled | 45% | 45% | Inadequate finances | 2015 | 6 | 4000000 | No | Defer | Financial | No | Propose budget for screening | No | Propose budget for screening | Yes | Fesibility studies and design | Phase one complete; Phase II proposed for funding in FY 2015/16; Tested yield 8m3/hr.
53 | Olosirua Borehole | Drilling and equipping of borehole | Increase access to safe and affordable water | Borehole drilled and equipped |  | Olosirua Borehole | Kajiado West | Lodokilani |  | Water, Irrigation, Environment and Natural Resources | Water & Irrigation | Water & Irrigation | 2014-06-30 | 2014-09-01 | 2015-06-30 |  | 5000000 | 5000000 | 5000000 | CGK | N/A | 5000000 | 0 | 2529000 | 50.58% | 2529000 | 2471000 | 2471000 | Stalled | 51% | 51% | Inadequate finances | 2015 | 6 | 4000000 | No | Defer | Financial | No | Propose budget for screening | No | Propose budget for screening | Yes | Fesibility studies and design | Equipping proposed for next FY. Tested yield = 26m3/hr.
54 | Oloolera Borehole | Drilling and equipping of borehole | Increase access to safe and affordable water | Borehole drilled and equipped |  | Oloolera Borehole | Kajiado West | Lodokilani |  | Water, Irrigation, Environment and Natural Resources | Water & Irrigation | Water & Irrigation | 2014-06-30 | 2014-09-01 | 2015-06-30 |  | 5000000 | 5000000 | 5000000 | CGK | N/A | 5000000 | 0 | 4997980 | 99.96% | 2315000 | 2020 | 2020 | Stalled | 46.32% | 46% | Inadequate finances | 2015 | 6 | 4000000 | No | Defer | Financial | No | Propose budget for screening | No | Propose budget for screening | Yes | Fesibility studies and design | Equipping proposed for next FY. Tested yield = 18.5m3/hr.
55 | Oldonyo Nyokie Pipeline | Pipeline and water tanks construction | Increase access to safe and affordable water | 1. Pipeline constructed 2. Water tanks constructed |  | Oldonyo Nyokie Pipeline | Kajiado West | Magadi |  | Water, Irrigation, Environment and Natural Resources | Water & Irrigation | Water & Irrigation | 2014-06-30 | 2014-09-01 | 2015-06-30 |  | 6500000 | 6500000 | 6500000 | CGK | N/A | 6500000 | 0 | 6280700 | 96.63% | 6280700 | 219300 | 219300 | Completed | [6 empty] | No |  | Environmental | No | Propose budget for screening | No | Propose budget for screening | Yes | Fesibility studies and design | Complete and operational
56 | Olgumi Galley / Contour | Construction of gabions | Restore degraded land and soil | Gabions constructed |  | Olgumi Galley / Contour | Kajiado West | Ewaso Kedong |  | Water, Irrigation, Environment and Natural Resources | Water & Irrigation | Water & Irrigation | 2014-06-30 | 2014-09-01 | 2015-06-30 |  | 2500000 | 2500000 | 2500000 | CGK | N/A | 2500000 | 0 | 0 | 0% | 0 | 2500000 | 2500000 | Stalled | 0% | 0% | Inadequate finances | 2015 | 6 | 7000000 | No | Defer | Financial | No | Propose budget for screening | No | Propose budget for screening | Yes | Fesibility studies and design | Not started due to inadequate funds
57 | Esonorua Water project phase 2 | Pipeline construction and installation of water storage tanks | Increase access to safe and affordable water | 1. Pipeline constructed 2. Water tanks constructed |  | Esonorua Water project phase 2 | Kajiado West | Keekonyokie |  | Water, Irrigation, Environment and Natural Resources | Water & Irrigation | Water & Irrigation | 2014-06-30 | 2014-09-01 | 2015-06-30 |  | 3000000 | 3000000 | 3000000 | CGK | N/A | 3000000 | 0 | 0 | 0% | 0 | 3000000 | 3000000 | Stalled | 0% | 0% | Inadequate finances | 2015 | 6 | 5000000 | No | Defer | Financial | No | Propose budget for screening | No | Propose budget for screening | Yes | Fesibility studies and design | Not started due to inadequate funds
58 | Bondeni Borehole & Tank | Drilling, equipping of borehole and tank construction | Increase access to safe and affordable water | 1. Borehole drilled and equipped 2. Storage tank constructed |  | Bondeni Borehole & Tank | Kajiado North | ngong |  | Water, Irrigation, Environment and Natural Resources | Water & Irrigation | Water & Irrigation | 2014-06-30 | 2014-09-01 | 2015-06-30 |  | 5000000 | 5000000 | 5000000 | CGK | N/A | 5000000 | 0 | 4967550 | 99.35% | 4967550 | 32450 | 32450 | Stalled | 99% | 99% | Inadequate finances | 2015 | 2 | 1000000 | No | Defer | Financial | No | Propose budget for screening | No | Propose budget for screening | Yes | Fesibility studies and design | Pending power connection
59 | Olepolos Borehole | Drilling and equipping of a borehole | Increase access to safe and affordable water | Borehole drilled and equipped |  | Olepolos Borehole | Kajiado North | Ololua |  | Water, Irrigation, Environment and Natural Resources | Water & Irrigation | Water & Irrigation | 2014-06-30 | 2014-09-01 | 2015-06-30 |  | 5000000 | 5000000 | 5000000 | CGK | N/A | 5000000 | 0 | 4970450 | 99.41% | 2582000 | 29550 | 29550 | Stalled | 52% | 52% | Land compensation and inadequate finances | 2015 | 6 | 8000000 | No | Defer | Financial | No | Propose budget for screening | No | Propose budget for screening | Yes | Fesibility studies and design | Land compensation and equipping recommended for next FY. Tested yields 36m3/hr.
60 | Bulbul Borehole | Drilling and equipping of a borehole | Increase access to safe and affordable water | Borehole drilled and equipped |  | Bulbul Borehole | Kajiado North | Ololua |  | Water, Irrigation, Environment and Natural Resources | Water & Irrigation | Water & Irrigation | 2014-06-30 | 2014-09-01 | 2015-06-30 |  | 5000000 | 5000000 | 5000000 | CGK | N/A | 5000000 | 0 | 4945660 | 98.91% | 2689004 | 54340 | 54340 | Stalled | 53.78% | 54% | Land compensation | 2015 | 6 | 4000000 | No | Defer | Legal | No | Propose budget for screening | No | Propose budget for screening | Yes | Fesibility studies and design | Drilling works complete; equipping not done
61 | Kerarapon Tank and pipeline | Tank installation and pipeline construction | Increase access to safe and affordable water | 1. Storage tank constructed 2. Pipeline constructed |  | Kerarapon Tank and pipeline | Kajiado North | Ololua |  | Water, Irrigation, Environment and Natural Resources | Water & Irrigation | Water & Irrigation | 2014-06-30 | 2014-09-01 | 2015-06-30 |  | 3000000 | 3000000 | 3000000 | CGK | N/A | 3000000 | 0 | 2987760 | 99.59% | 2987760 | 12240 | 12240 | Completed | [6 empty] | No |  | Environmental | No | Propose budget for screening | No | Propose budget for screening | Yes | Fesibility studies and design | Complete and operational
62 | Olngarua Borehole | Equipping of a borehole | Increase access to safe and affordable water | Borehole equipped |  | Olngarua Borehole | Kajiado East | Oloosirikon / Sholinke |  | Water, Irrigation, Environment and Natural Resources | Water & Irrigation | Water & Irrigation | 2014-06-30 | 2014-09-01 | 2015-06-30 |  | 2000000 | 2000000 | 2000000 | CGK | N/A | 2000000 | 0 | 1887000 | 94.35% | 1887000 | 113000 | 113000 | Stalled | 94% | 94% | Inadequate finances | 2015 | 6 | 4000000 | No | Defer | Financial | No | Propose budget for screening | No | Propose budget for screening | Yes | Fesibility studies and design | Equipping proposed for 2015/16 FY. Tested yield 48m3/hr.
63 | Erankau Borehole | Rehabilitation of a borehole | Increase access to safe and affordable water | Borehole rehabilitated |  | Erankau Borehole | Kajiado East | Olosirikon/Shorinke |  | Water, Irrigation, Environment and Natural Resources | Water & Irrigation | Water & Irrigation | 2014-06-30 | 2014-09-01 | 2015-06-30 |  | 2000000 | 2000000 | 2000000 | CGK | N/A | 2000000 | 0 | 1978456 | 98.92% | 0 | 21544 | 21544 | Stalled | 0% | 0% | Land compensation issues and inadequate finances | 2015 | 6 | 4000000 | No | Defer | Legal | No | Propose budget for screening | No | Propose budget for screening | Yes | Fesibility studies and design | Funds relocated to Olngarua for equipping which has yield of 48m3/hr.
64 | Olturoto Borehole | Drilling and equipping of a borehole | Increase access to safe and affordable water | Borehole drilled and equipped |  | Olturoto Borehole | Kajiado East | Kaputei North |  | Water, Irrigation, Environment and Natural Resources | Water & Irrigation | Water & Irrigation | 2014-06-30 | 2014-09-01 | 2015-06-30 |  | 5000000 | 5000000 | 5000000 | CGK | N/A | 5000000 | 0 | 2700000 | 54% | 2700000 | 2300000 | 2300000 | Stalled | 54% | 54% | Inadequate finances | 2015 | 6 | 4000000 | No | Defer | Financial | No | Propose budget for screening | No | Propose budget for screening | Yes | Fesibility studies and design | Equipping proposed for 2015/16 FY. Tested yield 3.5m3/hr.
65 | Enkilele Borehole | Drilling and equipping of a borehole | Increase access to safe and affordable water | Borehole drilled and equipped |  | Enkilele Borehole | Kajiado East | Kaputei North |  | Water, Irrigation, Environment and Natural Resources | Water & Irrigation | Water & Irrigation | 2014-06-30 | 2014-09-01 | 2015-06-30 |  | 5000000 | 5000000 | 5000000 | CGK | N/A | 5000000 | 0 | 2400000 | 48% | 2400000 | 2600000 | 2600000 | Stalled | 48% | 48% | Inadequate finances | 2015 | 6 | 4000000 | No | Defer | Financial | No | Propose budget for screening | No | Propose budget for screening | Yes | Fesibility studies and design | Equipping proposed for 2015/16 FY. Tested yield 2m3/hr.
66 | Olkinos Borehole Rehab | Rehabilitation of borehole | Increase access to safe and affordable water | Borehole rehabilitated |  | Olkinos Borehole Rehab | Kajiado East | Kaputei north |  | Water, Irrigation, Environment and Natural Resources | Water & Irrigation | Water & Irrigation | 2014-06-30 | 2014-09-01 | 2015-06-30 |  | 500000 | 500000 | 500000 | CGK | N/A | 500000 | 0 | 500000 | 100% | 500000 | 0 | 0 | Completed | [6 empty] | No |  | Environmental | No | Propose budget for screening | No | Propose budget for screening | Yes | Fesibility studies and design | Complete and operational
67 | Kisaju Borehole | Equipping of a borehole | Increase access to safe and affordable water | Borehole equipped |  | Kisaju Borehole | Kajiado East | Kaputei north |  | Water, Irrigation, Environment and Natural Resources | Water & Irrigation | Water & Irrigation | 2014-06-30 | 2014-09-01 | 2015-06-30 |  | 3000000 | 3000000 | 3000000 | CGK | N/A | 3000000 | 0 | 3000000 | 100% | 3000000 | 0 | 0 | Completed | [6 empty] | No |  | Environmental | No | Propose budget for screening | No | Propose budget for screening | Yes | Fesibility studies and design | Complete and operational
68 | Kisaju Public Toilet | Construction of public toilet | Increase access to adequate and equitable sanitation and hygiene | Public toilet constructed |  | Kisaju Public Toilet | Kajiado East | Kaputei north |  | Water, Irrigation, Environment and Natural Resources | Water & Irrigation | Water & Irrigation | 2014-06-30 | 2014-09-01 | 2015-06-30 |  | 1500000 | 1500000 | 1500000 | CGK | N/A | 1500000 | 0 | 1500000 | 100% | 1500000 | 0 | 0 | Completed | [6 empty] | No |  | Environmental | No | Propose budget for screening | No | Propose budget for screening | Yes | Fesibility studies and design | Complete and operational
69 | Edikirr Piping | Construction of pipeline | Increase access to safe and affordable water | Pipeline constructed |  | Edikirr Piping | Kajiado East | Kaputei north |  | Water, Irrigation, Environment and Natural Resources | Water & Irrigation | Water & Irrigation | 2014-06-30 | 2014-09-01 | 2015-06-30 |  | 2000000 | 2000000 | 2000000 | CGK | N/A | 2000000 | 0 | 1999999 | 100% | 1999999 | 1 | 1 | Completed | [6 empty] | No |  | Environmental | No | Propose budget for screening | No | Propose budget for screening | Yes | Fesibility studies and design | Complete and operational
70 | Nkama Oiti Borehole | Drilling and equipping of a borehole | Increase access to safe and affordable water | Borehole drilled and equipped |  | Nkama Oiti Borehole | Kajiado East | Kenyewa/Poka |  | Water, Irrigation, Environment and Natural Resources | Water & Irrigation | Water & Irrigation | 2014-06-30 | 2014-09-01 | 2015-06-30 |  | 5000000 | 5000000 | 5000000 | CGK | N/A | 5000000 | 0 | 2500000 | 50% | 2500000 | 2500000 | 2500000 | Stalled | 50% | 50% | Inadequate finances | 2015 | 6 | 4000000 | No | Defer | Financial | No | Propose budget for screening | No | Propose budget for screening | Yes | Fesibility studies and design | Balance from Imukutani/Naningo to equip the borehole. Tested yield 3.5m3/hr.
71 | Oiti Borehole | Rehabilitation of a borehole | Increase access to safe and affordable water | Borehole rehabilitated |  | Oiti Borehole | Kajiado East | Imaroro |  | Water, Irrigation, Environment and Natural Resources | Water & Irrigation | Water & Irrigation | 2014-06-30 | 2014-09-01 | 2015-06-30 |  | 5000000 | 5000000 | 5000000 | CGK | N/A | 5000000 | 0 | 0 | 0% | 0 | 5000000 | 5000000 | Stalled | 0% | 0% | Inadequate finances | 2015 | 6 | 5000000 | No | Defer | Financial | No | Propose budget for screening | No | Propose budget for screening | Yes | Fesibility studies and design | Rehabilitation recommended for 2015/16 FY. Tested yields 2m3/hr.
72 | Enkusero Arroi Borehole | Drilling and equipping of a borehole | Increase access to safe and affordable water | Borehole drilled and equipped |  | Enkusero Arroi Borehole | Kajiado East | imaroro |  | Water, Irrigation, Environment and Natural Resources | Water & Irrigation | Water & Irrigation | 2014-06-30 | 2014-09-01 | 2015-06-30 |  | 5000000 | 5000000 | 5000000 | CGK & Partner | ENSDA | 5000000 | 1858000 | 3142000 | 62.84% | 3142000 | 1858000 | 1858000 | Completed | [6 empty] | No |  | Financial | No | Propose budget for screening | No | Propose budget for screening | Yes | Fesibility studies and design | Complete and operational; Tested yields 48m3/hr.
73 | Enkasiti Pipeline | Pipeline construction | Increase access to safe and affordable water | Pipeline constructed |  | Enkasiti Pipeline | Kajiado East | kitengela |  | Water, Irrigation, Environment and Natural Resources | Water & Irrigation | Water & Irrigation | 2014-06-30 | 2014-09-01 | 2015-06-30 |  | 2000000 | 2000000 | 2000000 | CGK | N/A | 2000000 | 0 | 1042840 | 52.14% | 1042840 | 957160 | 957160 | Stalled | 52% | 52% | Borehole (source) collapsed | 2015 | 6 | 8000000 | No | Defer | Environmental | No | Propose budget for screening | No | Propose budget for screening | Yes | Fesibility studies and design | Require drilling of a new borehole for source of water to be piped since existing borehole collapsed
74 | Lemongo Borehole Drilling | Drilling and equipping of a borehole | Increase access to safe and affordable water | Borehole drilled and equipped |  | Lemongo Borehole Drilling | Kajiado South | Rombo |  | Water, Irrigation, Environment and Natural Resources | Water & Irrigation | Water & Irrigation | 2014-06-30 | 2014-09-01 | 2015-06-30 |  | 7000000 | 7000000 | 7000000 | CGK | N/A | 7000000 | 0 | 7000000 | 100% | 7000000 | 0 | 0 | Completed | [6 empty] | No | Defer | Environmental | No | Propose budget for screening | No | Propose budget for screening | Yes | Fesibility studies and design | Complete and operational; Tested yields 3.5m3/hr.
75 | Lemasus Borehole | Drilling and equipping of a borehole | Increase access to safe and affordable water | Borehole drilled and equipped |  | Lemasus Borehole | Kajiado South | Mbirikani – Eselenkei |  | Water, Irrigation, Environment and Natural Resources | Water & Irrigation | Water & Irrigation | 2014-06-30 | 2014-09-01 | 2015-06-30 |  | 5000000 | 5000000 | 5000000 | CGK | N/A | 5000000 | 0 | 3380000 | 67.6% | 3380000 | 1620000 | 1620000 | Completed | [6 empty] | No |  | Environmental | No | Propose budget for screening | No | Propose budget for screening | Yes | Fesibility studies and design
76 | Lorkiu Borehole | Drilling and equipping of a borehole | Increase access to safe and affordable water | Borehole drilled and equipped |  | Lorkiu Borehole | Kajiado South | Mbirikani – Eselenkei |  | Water, Irrigation, Environment and Natural Resources | Water & Irrigation | Water & Irrigation | 2014-06-30 | 2014-09-01 | 2015-06-30 |  | 5000000 | 5000000 | 5000000 | CGK | N/A | 5000000 | 0 | 2567000 | 51.34% | 2567000 | 2433000 | 2433000 | Completed | [6 empty] | No |  | Environmental | No | Propose budget for screening | No | Propose budget for screening | Yes | Fesibility studies and design
77 | Iltilal Borehole | Drilling and equipping of a borehole | Increase access to safe and affordable water | Borehole drilled and equipped |  | Iltilal Borehole | Kajiado South | Kuku |  | Water, Irrigation, Environment and Natural Resources | Water & Irrigation | Water & Irrigation | 2014-06-30 | 2014-09-01 | 2015-06-30 |  | 5000000 | 5000000 | 5000000 | CGK | N/A | 5000000 | 0 | 5000000 | 100% | 5000000 | 0 | 0 | Completed | [6 empty] | No |  | Environmental | No | Propose budget for screening | No | Propose budget for screening | Yes | Fesibility studies and design
78 | Silalei Borehole | Drilling and equipping of a borehole | Increase access to safe and affordable water | Borehole drilled and equipped |  | Silalei Borehole | Kajiado Central | Dalalekutuk |  | Water, Irrigation, Environment and Natural Resources | Water & Irrigation | Water & Irrigation | 2014-06-30 | 2014-09-01 | 2015-06-30 |  | 5000000 | 5000000 | 5000000 | CGK | N/A | 5000000 | 0 |  | 0% |  | 5000000 | 5000000 | Completed | [6 empty] | No |  | Environmental | No | Propose budget for screening | No | Propose budget for screening |  | Fesibility studies and design
79 | Ngosuani Borehole | Drilling and equipping of a borehole | Increase access to safe and affordable water | Borehole drilled and equipped |  | Ngosuani Borehole | Kajiado Central | Purko |  | Water, Irrigation, Environment and Natural Resources | Water & Irrigation | Water & Irrigation | 2014-06-30 | 2014-09-01 | 2015-06-30 |  | 5000000 | 5000000 | 5000000 | CGK | N/A | 5000000 | 0 | 2519000 | 50.38% | 2519000 | 2481000 | 2481000 | Completed | [6 empty] | No |  | Environmental | No | Propose budget for screening | No | Propose budget for screening |  | Fesibility studies and design
80 | Kiloriti Dam renovation | Fencing of a water dam and construction of gabions | Improve water quality by reducing pollution | 1. Water dam fenced 2. Gabions constructed |  | Kiloriti Dam renovation | Kajiado Central | Ildamat |  | Water, Irrigation, Environment and Natural Resources | Water & Irrigation | Water & Irrigation | 2014-06-30 | 2014-09-01 | 2015-06-30 |  | 1500000 | 1500000 | 1500000 | CGK | N/A | 1500000 | 0 | 1200000 | 80% | 1200000 | 300000 | 300000 | Completed | [6 empty] | No |  | Environmental | No | Propose budget for screening | No | Propose budget for screening |  | Fesibility studies and design
81 | Iparua Dam | Dam constructed c/w watering facilities | Increase access to safe and affordable water | Dam constructed c/w watering facilities |  | Iparua Dam | Kajiado Central | Purko |  | Water, Irrigation, Environment and Natural Resources | Water & Irrigation | Water & Irrigation | 2014-06-30 | 2014-09-01 | 2015-06-30 |  | 10000000 | 10000000 | 10000000 | CGK | N/A | 10000000 | 0 | 9892000 | 98.92% | 9892000 | 108000 | 108000 | Completed | [6 empty] | No |  | Environmental | No | Propose budget for screening | No | Propose budget for screening | Yes | Fesibility studies and design
82 | Olkishunki water point | Tank construction | Increase access to safe and affordable water | Storage tank constructed |  | Olkishunki water point | Kajiado Central | Matapato North |  | Water, Irrigation, Environment and Natural Resources | Water & Irrigation | Water & Irrigation | 2014-06-30 | 2014-09-01 | 2015-06-30 |  | 1000000 | 1000000 | 1000000 | CGK | N/A | 1000000 | 0 | 0 | 0% | 0 | 1000000 | 1000000 | Completed | [6 empty] | No |  | Environmental | No | Propose budget for screening | No | Propose budget for screening | Yes | Fesibility studies and design
83 | Inkeresuna Water point | Tank rehabilitation | Increase access to safe and affordable water | Tank rehabilitated |  | Inkeresuna Water point | Kajiado Central | Matapato North |  | Water, Irrigation, Environment and Natural Resources | Water & Irrigation | Water & Irrigation | 2014-06-30 | 2014-09-01 | 2015-06-30 |  | 1000000 | 1000000 | 1000000 | CGK | N/A | 1000000 | 0 | 1009800 | 101% | 1009800 | -9800 | -9800 | Completed | [6 empty] | No |  | Environmental | No | Propose budget for screening | No | Propose budget for screening | Yes | Fesibility studies and design
84 | Olchoro- Onyokie Water project | Rehabilitation of a 6km pipeline | Increase access to safe and affordable water | Pipeline rehabilitated |  | Olchoro- Onyokie Water project | Kajiado central | Matapato south |  | Water, Irrigation, Environment and Natural Resources | Water & Irrigation | Water & Irrigation | 2015-06-30 | 2015-09-01 | 2016-06-30 |  | 6000000 | 6000000 | 6000000 | CGK | N/A | 6000000 | 0 | 6000000 | 100% | 6000000 | 0 | 0 | Completed | [6 empty] | No |  | Environmental | No | Propose budget for screening | No | Propose budget for screening | Yes | Fesibility studies and design
85 | Olootimeloi Borehole | Drilling and equipping of a borehole | Increase access to safe and affordable water | Borehole drilled and equipped |  | Olootimeloi Borehole | Kajiado central | Matapato South |  | Water, Irrigation, Environment and Natural Resources | Water & Irrigation | Water & Irrigation | 2015-06-30 | 2015-09-01 | 2016-06-30 |  | 7000000 | 7000000 | 7000000 | CGK | N/A | 7000000 | 0 | 0 | 0% | 0 | 7000000 | 7000000 | Completed | [6 empty] | No |  | Environmental | No | Propose budget for screening | No | Propose budget for screening | Yes | Fesibility studies and design
86 | Eldonyewuas borehole | Drilling of a borehole | Increase access to safe and affordable water | Borehole drilled |  | Eldonyewuas borehole | Kajiado central | Matapato North |  | Water, Irrigation, Environment and Natural Resources | Water & Irrigation | Water & Irrigation | 2015-06-30 | 2015-09-01 | 2016-06-30 |  | 7000000 | 7000000 | 7000000 | CGK | N/A | 7000000 | 0 | 0 | 0% | 0 | 7000000 | 7000000 | Completed | [6 empty] | No |  | Environmental | No | Propose budget for screening | No | Propose budget for screening | Yes | Fesibility studies and design
87 | Leisai borehole | Drilling of a borehole | Increase access to safe and affordable water | Borehole drilled |  | Leisai borehole | Kajiado central | Matapato North |  | Water, Irrigation, Environment and Natural Resources | Water & Irrigation | Water & Irrigation | 2015-06-30 | 2015-09-01 | 2016-06-30 |  | 6000000 | 6000000 | 6000000 | CGK | N/A | 6000000 | 0 | 0 | 0% | 0 | 6000000 | 6000000 | Completed | [6 empty] | No |  | Environmental | No | Propose budget for screening | No | Propose budget for screening | Yes | Fesibility studies and design
88 | Kikurro Borehole | Drilling of a borehole | Increase access to safe and affordable water | Borehole drilled |  | Kikurro Borehole | Kajiado central | Dalalekutuk |  | Water, Irrigation, Environment and Natural Resources | Water & Irrigation | Water & Irrigation | 2015-06-30 | 2015-09-01 | 2016-06-30 |  | 7000000 | 7000000 | 7000000 | CGK | N/A | 7000000 | 0 | 7000000 | 100% | 7000000 | 0 | 0 | Completed | [6 empty] | No |  | Environmental | No | Propose budget for screening | No | Propose budget for screening | Yes | Fesibility studies and design
89 | Orinie Water Project | Drilling of a borehole | Increase access to safe and affordable water | Borehole drilled |  | Orinie Water Project | Kajiado central | Dalalekutuk |  | Water, Irrigation, Environment and Natural Resources | Water & Irrigation | Water & Irrigation | 2015-06-30 | 2015-09-01 | 2016-06-30 |  | 8000000 | 8000000 | 8000000 | CGK | N/A | 8000000 | 0 | 8000000 | 100% | 8000000 | 0 | 0 | Completed | [6 empty] | No |  | Environmental | No | Propose budget for screening | No | Propose budget for screening | Yes | Fesibility studies and design
90 | Chokaa Borehole | Drilling and equipping of a borehole | Increase access to safe and affordable water | Borehole drilled and equipped |  | Chokaa Borehole | Kajiado central | Ildamat |  | Water, Irrigation, Environment and Natural Resources | Water & Irrigation | Water & Irrigation | 2015-06-30 | 2015-09-01 | 2016-06-30 |  | 7000000 | 7000000 | 7000000 | CGK | N/A | 7000000 | 0 | 0 | 0% | 0 | 7000000 | 7000000 | Completed | [6 empty] | No |  | Environmental | No | Propose budget for screening | No | Propose budget for screening | Yes | Fesibility studies and design
91 | Oloolsheta – Duka moja Borehole | Drilling and equipping of a borehole | Increase access to safe and affordable water | Borehole drilled and equipped |  | Oloolsheta – Duka moja Borehole | Kajiado central | Ildamat |  | Water, Irrigation, Environment and Natural Resources | Water & Irrigation | Water & Irrigation | 2015-06-30 | 2015-09-01 | 2016-06-30 |  | 7700000 | 7700000 | 7700000 | CGK | N/A | 7700000 | 0 | 7700000 | 100% | 7700000 | 0 | 0 | Completed | [6 empty] | No |  | Environmental | No | Propose budget for screening | No | Propose budget for screening | Yes | Fesibility studies and design
92 | Bulati borehole | Drilling and equipping of a borehole | Increase access to safe and affordable water | Borehole drilled and equipped |  | Bulati borehole | Kajiado central | Purko |  | Water, Irrigation, Environment and Natural Resources | Water & Irrigation | Water & Irrigation | 2015-06-30 | 2015-09-01 | 2016-06-30 |  | 7000000 | 7000000 | 7000000 | CGK | N/A | 7000000 | 0 | 2600000 | 37.14% | 2600000 | 4400000 | 4400000 | Completed | [6 empty] | No |  | Environmental | No | Propose budget for screening | No | Propose budget for screening | Yes | Fesibility studies and design
93 | Lorkidongoi/ Endonyo Ekampi Water Project | Drilling and equipping of a borehole | Increase access to safe and affordable water | Borehole drilled and equipped |  | Lorkidongoi/ Endonyo Ekampi Water Project | Kajiado central | Purko |  | Water, Irrigation, Environment and Natural Resources | Water & Irrigation | Water & Irrigation | 2015-06-30 | 2015-09-01 | 2016-06-30 |  | 5000000 | 5000000 | 5000000 | CGK | N/A | 5000000 | 0 | 5000000 | 100% | 5000000 | 0 | 0 | Completed | [6 empty] | No |  | Environmental | No | Propose budget for screening | No | Propose budget for screening | Yes | Fesibility studies and design
94 | Noolera/Esiati Borehole | Drilling and equipping of a borehole | Increase access to safe and affordable water | Borehole drilled and equipped |  | Noolera/Esiati Borehole | Kajiado central | Purko |  | Water, Irrigation, Environment and Natural Resources | Water & Irrigation | Water & Irrigation | 2015-06-30 | 2015-09-01 | 2016-06-30 |  | 7000000 | 7000000 | 7000000 | CGK | N/A | 7000000 | 0 | 0 | 0% | 0 | 7000000 | 7000000 | Completed | [6 empty] | No |  | Environmental | No | Propose budget for screening | No | Propose budget for screening | Yes | Fesibility studies and design
95 | Nkoile Primary School Sanitation Project | Construction of sanitation facility (4 toilets and 4 bathrooms) | Increase access to adequate and equitable sanitation and hygiene | Sanitation facility constructed |  | Nkoile Primary School Sanitation Project | Kajiado Central | Purko |  | Water, Irrigation, Environment and Natural Resources | Water & Irrigation | Water & Irrigation | 2015-06-30 | 2015-09-01 | 2016-06-30 |  | 1400000 | 1400000 | 1400000 | CGK | N/A | 1400000 | 0 | 1400000 | 100% | 1400000 | 0 | 0 | Completed | [6 empty] | No |  | Environmental | No | Propose budget for screening | No | Propose budget for screening | Yes | Fesibility studies and design
96 | Imukutani Borehole | Drilling and equipping of a borehole | Increase access to safe and affordable water | Borehole drilled and equipped |  | Imukutani Borehole | Kajiado East | Kenyewa poka |  | Water, Irrigation, Environment and Natural Resources | Water & Irrigation | Water & Irrigation | 2015-06-30 | 2015-09-01 | 2016-06-30 |  | 7000000 | 7000000 | 7000000 | CGK | N/A | 7000000 | 0 | 0 | 0% | 0 | 7000000 | 7000000 | Completed | [6 empty] | No |  | Environmental | No | Propose budget for screening | No | Propose budget for screening | Yes | Fesibility studies and design
97 | Emakoko borehole | Drilling and equipping of a borehole | Increase access to safe and affordable water | Borehole drilled and equipped |  | Emakoko borehole | Kajiado East | oloosirko/sholinke |  | Water, Irrigation, Environment and Natural Resources | Water & Irrigation | Water & Irrigation | 2015-06-30 | 2015-09-01 | 2016-06-30 |  | 1500000 | 1500000 | 1500000 | CGK | N/A | 1500000 | 0 | 1500000 | 100% | 1500000 | 0 | 0 | Completed | [6 empty] | No |  | Environmental | No | Propose budget for screening | No | Propose budget for screening | Yes | Fesibility studies and design
98 | Imejooli Borehole | Drilling and equipping of a borehole | Increase access to safe and affordable water | Borehole drilled and equipped |  | Imejooli Borehole | Kajiado East | Ilmaroro |  | Water, Irrigation, Environment and Natural Resources | Water & Irrigation | Water & Irrigation | 2015-06-30 | 2015-09-01 | 2016-06-30 |  | 7000000 | 7000000 | 7000000 | CGK | N/A | 7000000 | 0 | 0 | 0% | 0 | 7000000 | 7000000 | Completed | [6 empty] | No |  | Environmental | No | Propose budget for screening | No | Propose budget for screening | Yes | Fesibility studies and design
99 | Olmanie Borehole | Drilling and equipping of a borehole | Increase access to safe and affordable water | Borehole drilled and equipped |  | Olmanie Borehole | Kajiado East | Ilmaroro |  | Water, Irrigation, Environment and Natural Resources | Water & Irrigation | Water & Irrigation | 2015-06-30 | 2015-09-01 | 2016-06-30 |  | 2000000 | 2000000 | 2000000 | CGK | N/A | 2000000 | 0 | 1995800 | 99.79% | 1995800 | 4200 | 4200 | Completed | [6 empty] | No |  | Environmental | No | Propose budget for screening | No | Propose budget for screening | Yes | Fesibility studies and design
100 | Olkeriai Borehole | Pipeline construction | Increase access to safe and affordable water | Pipeline constructed |  | Olkeriai Borehole | Kajiado East | Ilmaroro |  | Water, Irrigation, Environment and Natural Resources | Water & Irrigation | Water & Irrigation | 2015-06-30 | 2015-09-01 | 2016-06-30 |  | 2000000 | 2000000 | 2000000 | CGK | N/A | 2000000 | 0 | 0 | 0% | 0 | 2000000 | 2000000 | Completed | [6 empty] | No |  | Environmental | No | Propose budget for screening | No | Propose budget for screening | Yes | Fesibility studies and design
101 | P.J Dave Borehole | Drilling and equipping of a borehole | Increase access to safe and affordable water | Borehole drilled and equipped |  | P.J Dave Borehole | Kajiado East | Kaputei North |  | Water, Irrigation, Environment and Natural Resources | Water & Irrigation | Water & Irrigation | 2015-06-30 | 2015-09-01 | 2016-06-30 |  | 4000000 | 4000000 | 4000000 | CGK | N/A | 4000000 | 0 | 0 | 0% | 0 | 4000000 | 4000000 | Completed | [6 empty] | No |  | Environmental | No | Propose budget for screening | No | Propose budget for screening | Yes | Fesibility studies and design
102 | Ole Nkoitila Borehole | Drilling and equipping of a borehole | Increase access to safe and affordable water | Borehole drilled and equipped |  | Ole Nkoitila Borehole | Kajiado East | Kaputei North |  | Water, Irrigation, Environment and Natural Resources | Water & Irrigation | Water & Irrigation | 2015-06-30 | 2015-09-01 | 2016-06-30 |  | 7500000 | 7500000 | 7500000 | CGK | N/A | 7500000 | 0 | 0 | 0% | 0 | 7500000 | 7500000 | Completed | [6 empty] | No |  | Environmental | No | Propose budget for screening | No | Propose budget for screening | Yes | Fesibility studies and design
103 | Nairode Water Project | Drilling and equipping of a borehole | Increase access to safe and affordable water | Borehole drilled and equipped |  | Nairode Water Project | Kajiado West | Ewaso Kidong |  | Water, Irrigation, Environment and Natural Resources | Water & Irrigation | Water & Irrigation | 2015-06-30 | 2015-09-01 | 2016-06-30 |  | 5000000 | 5000000 | 5000000 | CGK | N/A | 5000000 | 0 | 0 | 0% | 0 | 5000000 | 5000000 | Completed | [6 empty] | No |  | Environmental | No | Propose budget for screening | No | Propose budget for screening | Yes | Fesibility studies and design
104 | Kibiko water project | Construction of pipelines and storage tank | Increase access to safe and affordable water | Pipeline and storage Storage tank constructed |  | Kibiko water project | Kajiado West | Ewaso Kidong |  | Water, Irrigation, Environment and Natural Resources | Water & Irrigation | Water & Irrigation | 2015-06-30 | 2015-09-01 | 2016-06-30 |  | 5500000 | 5500000 | 5500000 | CGK | N/A | 5500000 | 0 | 5500000 | 100% | 5500000 | 0 | 0 | Completed | [6 empty] | No |  | Environmental | No | Propose budget for screening | No | Propose budget for screening | Yes | Fesibility studies and design
105 | Olmaroroi Borehole | Borehole rehabilitation | Increase access to safe and affordable water | Borehole rehabilitated |  | Olmaroroi Borehole | Kajiado West | Ewaso Kidong |  | Water, Irrigation, Environment and Natural Resources | Water & Irrigation | Water & Irrigation | 2015-06-30 | 2015-09-01 | 2016-06-30 |  | 6000000 | 6000000 | 6000000 | CGK | N/A | 6000000 | 0 | 6000000 | 100% | 6000000 | 0 | 0 | Completed | [6 empty] | No |  | Environmental | No | Propose budget for screening | No | Propose budget for screening | Yes | Fesibility studies and design
106 | Ewuaso G.Sch. Water Project | Construction of water tank | Increase access to safe and affordable water | Water Storage tank constructed |  | Ewuaso G.Sch. Water Project | Kajiado West | Ewaso Kidong |  | Water, Irrigation, Environment and Natural Resources | Water & Irrigation | Water & Irrigation | 2015-06-30 | 2015-09-01 | 2016-06-30 |  | 2000000 | 2000000 | 2000000 | CGK | N/A | 2000000 | 0 | 0 | 0% | 0 | 2000000 | 2000000 | Completed | [6 empty] | No |  | Environmental | No | Propose budget for screening | No | Propose budget for screening | Yes | Fesibility studies and design
107 | Enaborr sungu Borehole | Drilling and equipping of a borehole | Increase access to safe and affordable water | Borehole drilled and equipped |  | Enaborr sungu Borehole | Kajiado West | Mosiro |  | Water, Irrigation, Environment and Natural Resources | Water & Irrigation | Water & Irrigation | 2015-06-30 | 2015-09-01 | 2016-06-30 |  | 6000000 | 6000000 | 6000000 | CGK | N/A | 6000000 | 0 | 0 | 0% | 0 | 6000000 | 6000000 | Stalled | 0% | 0% | Inadequate finances | 2016 | 6 | 6000000 | No | Defer | Financial | No | Propose budget for screening | No | Propose budget for screening | Yes | Fesibility studies and design
108 | Oleserian-Komiti pipeline | Pipeline construction | Increase access to safe and affordable water | Pipeline constructed |  | Oleserian-Komiti pipeline | Kajiado West | Magadi |  | Water, Irrigation, Environment and Natural Resources | Water & Irrigation | Water & Irrigation | 2015-06-30 | 2015-09-01 | 2016-06-30 |  | 4570000 | 4570000 | 4570000 | CGK | N/A | 4570000 | 0 | 0 | 0% | 0 | 4570000 | 4570000 | Completed | [6 empty] | No |  | Environmental | No | Propose budget for screening | No | Propose budget for screening | Yes | Fesibility studies and design
109 | Kamukuru borehole | Rehabilitation of borehole and pipeline | Increase access to safe and affordable water | Borehole and pipeline rehabilitated |  | Kamukuru borehole | Kajiado West | Magadi |  | Water, Irrigation, Environment and Natural Resources | Water & Irrigation | Water & Irrigation | 2015-06-30 | 2015-09-01 | 2016-06-30 |  | 4570000 | 4570000 | 4570000 | CGK | N/A | 4570000 | 0 | 0 | 0% | 0 | 4570000 | 4570000 | Completed | [6 empty] | No |  | Environmental | No | Propose budget for screening | No | Propose budget for screening | Yes | Fesibility studies and design
110 | Inyonyori Community tank | Construction of 100m3 masonry tank | Increase access to safe and affordable water | 100m3 masonry Storage tank constructed |  | Inyonyori Community tank | Kajiado West | Keekonyokie |  | Water, Irrigation, Environment and Natural Resources | Water & Irrigation | Water & Irrigation | 2015-06-30 | 2015-09-01 | 2016-06-30 |  | 2000000 | 2000000 | 2000000 | CGK | N/A | 2000000 | 0 | 0 | 0% | 0 | 2000000 | 2000000 | Completed | [6 empty] | No |  | Environmental | No | Propose budget for screening | No | Propose budget for screening | Yes | Fesibility studies and design
111 | Enkusero-Inyonyori | Construction of 100m3 masonry tank | Increase access to safe and affordable water | 100m3 masonry Storage tank constructed |  | Enkusero-Inyonyori | Kajiado West | Keekonyokie |  | Water, Irrigation, Environment and Natural Resources | Water & Irrigation | Water & Irrigation | 2015-06-30 | 2015-09-01 | 2016-06-30 |  | 2000000 | 2000000 | 2000000 | CGK | N/A | 2000000 | 0 | 1993700 | 99.69% | 1993700 | 6300 | 6300 | Completed | [6 empty] | No |  | Environmental | No | Propose budget for screening | No | Propose budget for screening | Yes | Fesibility studies and design
112 | Indupa Borehole Phase II | Pipeline construction & Water tank Completion | Increase access to safe and affordable water | Pipeline constructed & water tank completed |  | Indupa Borehole Phase II | Kajiado West | Ilodokilani |  | Water, Irrigation, Environment and Natural Resources | Water & Irrigation | Water & Irrigation | 2015-06-30 | 2015-09-01 | 2016-06-30 |  | 5000000 | 5000000 | 5000000 | CGK | N/A | 5000000 | 0 | 0 | 0% | 0 | 5000000 | 5000000 | Completed | [6 empty] | No |  | Environmental | No | Propose budget for screening | No | Propose budget for screening | Yes | Fesibility studies and design
113 | Iloshon Storage Tank | Constuction of water storage tank, pipeline extension and upgrading of submersible pump and electric generator | Increase access to safe and affordable water | 1. Water Storage tank constructed 2. Pipeline extended 3. Borehole upgraded |  | Iloshon Storage Tank | Kajiado West | Ilodokilani |  | Water, Irrigation, Environment and Natural Resources | Water & Irrigation | Water & Irrigation | 2015-06-30 | 2015-09-01 | 2016-06-30 |  | 2000000 | 2000000 | 2000000 | CGK | N/A | 2000000 | 0 | 0 | 0% | 0 | 2000000 | 2000000 | Completed | [6 empty] | No |  | Environmental | No | Propose budget for screening | No | Propose budget for screening | Yes | Fesibility studies and design
114 | Ngong Township Pry. School Borehole | Drilling and equipping of a borehole | Increase access to safe and affordable water | Borehole drilled and equipped |  | Ngong Township Pry. School Borehole | Kajiado North | Ngong |  | Water, Irrigation, Environment and Natural Resources | Water & Irrigation | Water & Irrigation | 2015-06-30 | 2015-09-01 | 2016-06-30 |  | 7500000 | 7500000 | 7500000 | CGK | N/A | 7500000 | 0 | 0 | 0% | 0 | 7500000 | 7500000 | Completed | [6 empty] | No |  | Environmental | No | Propose budget for screening | No | Propose budget for screening | Yes | Fesibility studies and design
115 | Loitokitok Town Toilet | Construction of public toilet | Increase access to safe and affordable water | Public toilet constructed |  | Loitokitok Town Toilet | Kajiado North | Ongata Rongai |  | Water, Irrigation, Environment and Natural Resources | Water & Irrigation | Water & Irrigation | 2015-06-30 | 2015-09-01 | 2016-06-30 |  | 2000000 | 2000000 | 2000000 | CGK | N/A | 2000000 | 0 | 2000000 | 100% | 2000000 | 0 | 0 | Completed | [6 empty] | No |  | Environmental | No | Propose budget for screening | No | Propose budget for screening | Yes | Fesibility studies and design
116 | Loitokitok Town Storage tank | Construction of a water tank | Increase access to safe and affordable water | Water Storage tank constructed |  | Loitokitok Town Storage tank | Kajiado South | Kuku |  | Water, Irrigation, Environment and Natural Resources | Water & Irrigation | Water & Irrigation | 2015-06-30 | 2015-09-01 | 2016-06-30 |  | 3000000 | 3000000 | 3000000 | CGK | N/A | 3000000 | 0 | 0 | 0% | 0 | 3000000 | 3000000 | Completed | [6 empty] | No |  | Environmental | No | Propose budget for screening | No | Propose budget for screening | Yes | Fesibility studies and design
117 | Olkaria Water Project | Construction of a water tank | Increase access to safe and affordable water | Water Storage tank constructed |  | Olkaria Water Project | Kajiado South | Kuku |  | Water, Irrigation, Environment and Natural Resources | Water & Irrigation | Water & Irrigation | 2015-06-30 | 2015-09-01 | 2016-06-30 |  | 4000000 | 4000000 | 4000000 | CGK | N/A | 4000000 | 0 | 0 | 0% | 0 | 4000000 | 4000000 | Completed | [6 empty] | No |  | Environmental | No | Propose budget for screening | No | Propose budget for screening | Yes | Fesibility studies and design
118 | Oyarata Water Project | Drilling and equipping of a shallow well | Increase access to safe and affordable water | Shallow well drilled and equipped |  | Oyarata Water Project | Kajiado South | Kuku |  | Water, Irrigation, Environment and Natural Resources | Water & Irrigation | Water & Irrigation | 2015-06-30 | 2015-09-01 | 2016-06-30 |  | 2000000 | 2000000 | 2000000 | CGK | N/A | 2000000 | 0 | 2000000 | 100% | 2000000 | 0 | 0 | Completed | [6 empty] | No |  | Environmental | No | Propose budget for screening | No | Propose budget for screening | Yes | Fesibility studies and design
119 | Neiti Water Project | Drilling and equipping of a shallow well | Increase access to safe and affordable water | Shallow well drilled and equipped |  | Neiti Water Project | Kajiado South | Kuku |  | Water, Irrigation, Environment and Natural Resources | Water & Irrigation | Water & Irrigation | 2015-06-30 | 2015-09-01 | 2016-06-30 |  | 2000000 | 2000000 | 2000000 | CGK | N/A | 2000000 | 0 | 0 | 0% | 0 | 2000000 | 2000000 | Stalled | 40% | 40% | Dry borehole | 2016 | 6 | 2000000 | No | Defer | Financial | No | Propose budget for screening | No | Propose budget for screening | Yes | Fesibility studies and design
120 | Imisigiyo Water Project | Drilling and equipping of a borehole | Increase access to safe and affordable water | Borehole drilled and equipped |  | Imisigiyo Water Project | Kajiado south | Entonet/Lenkism |  | Water, Irrigation, Environment and Natural Resources | Water & Irrigation | Water & Irrigation | 2015-06-30 | 2015-09-01 | 2016-06-30 |  | 7000000 | 7000000 | 7000000 | CGK | N/A | 7000000 | 0 | 0 | 0% | 0 | 7000000 | 7000000 | Completed | [6 empty] | No |  | Environmental | No | Propose budget for screening | No | Propose budget for screening | Yes | Fesibility studies and design
121 | Kijito Water Project | Construction of watering facilities | Increase access to safe and affordable water | Water facilities constructed |  | Kijito Water Project | Kajiado South | Entonet/Lenkism |  | Water, Irrigation, Environment and Natural Resources | Water & Irrigation | Water & Irrigation | 2015-06-30 | 2015-09-01 | 2016-06-30 |  | 2000000 | 2000000 | 2000000 | CGK | N/A | 2000000 | 0 | 0 | 0% | 0 | 2000000 | 2000000 | Completed | [6 empty] | No |  | Environmental | No | Propose budget for screening | No | Propose budget for screening | Yes | Fesibility studies and design
122 | Olkirinyi Water Project | Construction of a 50m3 ground masonry tank and 3km pipeline | Increase access to safe and affordable water | 50m3 ground masonry tank and 3km pipeline constructed |  | Olkirinyi Water Project | Kajiado South | Entonet/Lenkism |  | Water, Irrigation, Environment and Natural Resources | Water & Irrigation | Water & Irrigation | 2015-06-30 | 2015-09-01 | 2016-06-30 |  | 3500000 | 3500000 | 3500000 | CGK | N/A | 3500000 | 0 | 3500000 | 100% | 3500000 | 0 | 0 | Completed | [6 empty] | No |  | Environmental | No | Propose budget for screening | No | Propose budget for screening | Yes | Fesibility studies and design
123 | Natumose Water Project | Tank and pipeline construction | Increase access to safe and affordable water | Tank and pipeline constructed |  | Natumose Water Project | Kajiado South | Entonet/Lenkism |  | Water, Irrigation, Environment and Natural Resources | Water & Irrigation | Water & Irrigation | 2015-06-30 | 2015-09-01 | 2016-06-30 |  | 3000000 | 3000000 | 3000000 | CGK | N/A | 3000000 | 0 | 0 | 0% | 0 | 3000000 | 3000000 | Completed | [6 empty] | No |  | Environmental | No | Propose budget for screening | No | Propose budget for screening | Yes | Fesibility studies and design
124 | Karesirwa Water Project |  | Increase access to safe and affordable water |  |  | Karesirwa Water Project | Kajiado South | Imbirikani/ Isinet |  | Water, Irrigation, Environment and Natural Resources | Water & Irrigation | Water & Irrigation | 2015-06-30 | 2015-09-01 | 2016-06-30 |  | 2000000 | 2000000 | 2000000 | CGK | N/A | 2000000 | 0 | 0 | 0% | 0 | 2000000 | 2000000 | work in progress | [6 empty] | No |  | Environmental | No |  | No | Propose budget for screening | Yes
125 | Nado Nkajijik borehole | Drilling and equipping of a borehole | Increase access to safe and affordable water | Borehole drilled and equipped |  | Nado Nkajijik borehole | Kajiado south | Mbirikani/ Eselenkei |  | Water, Irrigation, Environment and Natural Resources | Water & Irrigation | Water & Irrigation | 2015-06-30 | 2015-09-01 | 2016-06-30 |  | 7000000 | 7000000 | 7000000 | CGK | N/A | 7000000 | 0 | 0 | 0% | 0 | 7000000 | 7000000 | Completed | [6 empty] | No |  | Environmental | No | Propose budget for screening | No | Propose budget for screening | Yes | Fesibility studies and design
126 | Engaji Nabor Furrow | Construction of irrigation furrow | Increase area under irrigation | Irrigation furrow constructed |  | Engaji Nabor Furrow | Kajiado south | Imbirikani/ Eselenkei |  | Water, Irrigation, Environment and Natural Resources | Water & Irrigation | Water & Irrigation | 2015-06-30 | 2015-09-01 | 2016-06-30 |  | 5000000 | 5000000 | 5000000 | CGK | N/A | 5000000 | 0 | 0 | 0% | 0 | 5000000 | 5000000 | Completed | [6 empty] | No |  | Environmental | No | Propose budget for screening | No | Propose budget for screening | Yes | Fesibility studies and design
127 | Gabriel water springs | Spring protection | Protect and restore water-related ecosystems | Spring protected |  | Gabriel water springs | Kajiado south | Rombo |  | Water, Irrigation, Environment and Natural Resources | Water & Irrigation | Water & Irrigation | 2015-06-30 | 2015-09-01 | 2016-06-30 |  | 7000000 | 7000000 | 7000000 | CGK | N/A | 7000000 | 0 | 0 | 0% | 0 | 7000000 | 7000000 | Completed | [6 empty] | No |  | Environmental | No | Propose budget for screening | No | Propose budget for screening | Yes | Fesibility studies and design
128 | Oloile Water Project | Drilling and equipping of a borehole | Increase access to safe and affordable water | Borehole drilled and equipped |  | Oloile Water Project | Kajiado south | Kimana |  | Water, Irrigation, Environment and Natural Resources | Water & Irrigation | Water & Irrigation | 2015-06-30 | 2015-09-01 | 2016-06-30 |  | 7000000 | 7000000 | 7000000 | CGK | N/A | 7000000 | 0 | 0 | 0% | 0 | 7000000 | 7000000 | Completed |  |  | Inadequate funds |  |  |  | No |  | Environmental | No | Propose budget for screening | No | Propose budget for screening | Yes | Fesibility studies and design
129 | Mosiro Irrigation | Solar pumping equipment installation, Construction of pipeline, water storage tank and irrigation canal | Increase area under irrigation | Intake, pipeline, storage tank and canal constructed |  | Mosiro Irrigation | Kajiado West | Mosiro |  | Water, Irrigation, Environment and Natural Resources | Water & Irrigation | Water & Irrigation | 2015-06-30 | 2015-09-01 | 2016-06-30 |  | 10000000 | 10000000 | 10000000 | CGK | N/A | 10000000 | 0 | 0 | 0% | 0 | 10000000 | 10000000 | Stalled | 40% | 40% |  |  |  |  | No |  | Environmental | No |  | No | Propose budget for screening | Yes | Fesibility studies and design
130 | Impiro canal repair | Lining of a canal | Increase area under irrigation | Canal lined |  | Impiro canal repair | Kajiado South | kimana |  | Water, Irrigation, Environment and Natural Resources | Water & Irrigation | Water & Irrigation | 2015-06-30 | 2015-09-01 | 2016-06-30 |  | 5000000 | 5000000 | 5000000 | CGK | N/A | 5000000 | 0 | 0 | 0% | 0 | 5000000 | 5000000 | Completed | [6 empty] | No |  | Environmental | No | Propose budget for screening | No | Propose budget for screening | Yes | Fesibility studies and design
131 | Ilemai borehole | Water piping from Ilemei borehole to Inkorienito tank | Increase access to safe and affordable water | Pipeline constructed |  | Ilemai borehole | Kajiado South | Entonet/ Lenkism |  | Water, Irrigation, Environment and Natural Resources | Water & Irrigation | Water & Irrigation | 2016-06-30 | 2016-07-01 | 2017-06-30 |  | 1500000 | 1500000 | 1500000 | CGK | N/A | 1500000 | 0 | 1495800 | 99.72% | 1495800 | 4200 | 4200 | Completed | [6 empty] | No |  | Environmental | No | Propose budget for screening | No | Propose budget for screening | Yes | Fesibility studies and design
132 | Inkiito water tank | Water tank construction | Increase access to safe and affordable water | Storage tank constructed |  | Inkiito water tank | Kajiado South | Entonet/ Lenkism |  | Water, Irrigation, Environment and Natural Resources | Water & Irrigation | Water & Irrigation | 2016-06-30 | 2016-07-01 | 2017-06-30 |  | 1500000 | 1500000 | 1500000 | CGK | N/A | 1500000 | 0 | 1495800 | 99.72% | 1495800 | 4200 | 4200 | Completed | [6 empty] | No |  | Environmental | No | Propose budget for screening | No | Propose budget for screening | Yes | Fesibility studies and design
133 | Emparinkoi community water tank | Water tank construction | Increase access to safe and affordable water | Storage tank constructed |  | Emparinkoi community water tank | Kajiado South | Entonet/ Lenkism |  | Water, Irrigation, Environment and Natural Resources | Water & Irrigation | Water & Irrigation | 2016-06-30 | 2016-07-01 | 2017-06-30 |  | 1900000 | 1900000 | 1900000 | CGK | N/A | 1900000 | 0 | 1895000 | 99.74% | 1895000 | 5000 | 5000 | Completed | [6 empty] | No |  | Environmental | No | Propose budget for screening | No | Propose budget for screening | Yes | Fesibility studies and design
134 | Naiperra borehole | Construction of a water tank & cattle trough | Increase access to safe and affordable water | Storage tank constructed |  | Naiperra borehole | Kajiado South | Entonet/ Lenkism |  | Water, Irrigation, Environment and Natural Resources | Water & Irrigation | Water & Irrigation | 2016-06-30 | 2016-07-01 | 2017-06-30 |  | 2000000 | 2000000 | 2000000 | CGK | N/A | 2000000 | 0 | 1983960 | 99.2% | 1983960 | 16040 | 16040 | Completed | [6 empty] | No |  | Environmental | No | Propose budget for screening | No | Propose budget for screening | Yes | Fesibility studies and design
135 | Nado Nkajijik borehole | Borehole equipping and watering facilities construction | Increase access to safe and affordable water | Borehole drilled and equipped |  | Nado Nkajijik borehole | Kajiado South | Entonet/ Lenkism |  | Water, Irrigation, Environment and Natural Resources | Water & Irrigation | Water & Irrigation | 2016-06-30 | 2016-07-01 | 2017-06-30 |  | 4000000 | 4000000 | 4000000 | CGK | N/A | 4000000 | 0 |  | 0% |  | 4000000 | 4000000 | Completed | [6 empty] | No |  | Environmental | No | Propose budget for screening | No | Propose budget for screening | Yes | Fesibility studies and design
136 | Nkoroshoni borehole | Borehole drilling and equipping | Increase access to safe and affordable water | Borehole drilled and equipped |  | Nkoroshoni borehole | Kajiado South | Entonet/ Lenkism |  | Water, Irrigation, Environment and Natural Resources | Water & Irrigation | Water & Irrigation | 2016-06-30 | 2016-07-01 | 2017-06-30 |  | 7000000 | 7000000 | 7000000 | CGK | N/A | 7000000 | 0 | 3985520 | 56.94% | 3985520 | 3014480 | 3014480 | Completed | [6 empty] | No |  | Environmental | No | Propose budget for screening | No | Propose budget for screening | Yes | Fesibility studies and design
137 | Oloile borehole | 4km water pipeline extension | Increase access to safe and affordable water | Pipeline constructed |  | Oloile borehole | Kajiado South | Kimana |  | Water, Irrigation, Environment and Natural Resources | Water & Irrigation | Water & Irrigation | 2016-06-30 | 2016-07-01 | 2017-06-30 |  | 7500000 | 7500000 | 7500000 | CGK | N/A | 7500000 | 0 | 7485750 | 99.81% | 7485750 | 14250 | 14250 | Completed | [6 empty] | No |  | Environmental | No | Propose budget for screening | No | Propose budget for screening | Yes | Fesibility studies and design
138 | Namelock/Olenjabi | Construction of a 50m3 masonry tank | Increase access to safe and affordable water | Storage tank constructed |  | Namelock/Olenjabi | Kajiado South | Kimana |  | Water, Irrigation, Environment and Natural Resources | Water & Irrigation | Water & Irrigation | 2016-06-30 | 2016-07-01 | 2017-06-30 |  | 4000000 | 4000000 | 4000000 | CGK | N/A | 4000000 | 0 | 3999000 | 99.98% | 3999000 | 1000 | 1000 | Completed | [6 empty] | No |  | Environmental | No | Propose budget for screening | No | Propose budget for screening | Yes | Fesibility studies and design
139 | Maisuyat Water Project | 3km water pipeline extension | Increase access to safe and affordable water | Pipeline constructed |  | Maisuyat Water Project | Kajiado South | Kimana |  | Water, Irrigation, Environment and Natural Resources | Water & Irrigation | Water & Irrigation | 2016-06-30 | 2016-07-01 | 2017-06-30 |  | 3000000 | 3000000 | 3000000 | CGK | N/A | 3000000 | 0 | 2983500 | 99.45% | 2983500 | 16500 | 16500 | Completed | [6 empty] | No |  | Environmental | No | Propose budget for screening | No | Propose budget for screening | Yes | Fesibility studies and design
140 | Kimana Tikondo borehole | 3km water pipeline extension | Increase access to safe and affordable water | Pipeline constructed |  | Kimana Tikondo borehole | Kajiado South | Kimana |  | Water, Irrigation, Environment and Natural Resources | Water & Irrigation | Water & Irrigation | 2016-06-30 | 2016-07-01 | 2017-06-30 |  | 5000000 | 5000000 | 5000000 | CGK | N/A | 5000000 | 0 | 4985000 | 99.7% | 4985000 | 15000 | 15000 | Completed | [6 empty] | No |  | Environmental | No | Propose budget for screening | No | Propose budget for screening | Yes | Fesibility studies and design
141 | Kimoingan Dam | Construction of a dam and cattle trough | Increase access to safe and affordable water | Dam constructed c/w watering facilities |  | Kimoingan Dam | Kajiado South | Kimana |  | Water, Irrigation, Environment and Natural Resources | Water & Irrigation | Water & Irrigation | 2016-06-30 | 2016-07-01 | 2017-06-30 |  | 2000000 | 2000000 | 2000000 | CGK | N/A | 2000000 | 0 | 1993250 | 99.66% | 1993250 | 6750 | 6750 | Completed | [6 empty] | No |  | Environmental | No | Propose budget for screening | No | Propose budget for screening | Yes | Fesibility studies and design
142 | Ololmara Borehole | Water pipeline extension | Increase access to safe and affordable water | Pipeline constructed |  | Ololmara Borehole | Kajiado South | Kuku |  | Water, Irrigation, Environment and Natural Resources | Water & Irrigation | Water & Irrigation | 2016-06-30 | 2016-07-01 | 2017-06-30 |  | 6000000 | 6000000 | 6000000 | CGK | N/A | 6000000 | 0 | 3115760 | 51.93% | 3115760 | 2884240 | 2884240 | Completed | [6 empty] | No |  | Environmental | No | Propose budget for screening | No | Propose budget for screening | Yes | Fesibility studies and design
143 | Nasore borehole | Drilling and equipping of a borehole | Increase access to safe and affordable water | Borehole drilled and equipped |  | Nasore borehole | Kajiado South | Kuku |  | Water, Irrigation, Environment and Natural Resources | Water & Irrigation | Water & Irrigation | 2016-06-30 | 2016-07-01 | 2017-06-30 |  | 6000000 | 6000000 | 6000000 | CGK | N/A | 6000000 | 0 |  | 0% |  | 6000000 | 6000000 | Completed | [6 empty] | No |  | Environmental | No | Propose budget for screening | No | Propose budget for screening | Yes | Fesibility studies and design
144 | Olmatasia borehole | Drilling and equipping of a borehole | Increase access to safe and affordable water | Borehole drilled and equipped |  | Olmatasia borehole | Kajiado South | Kuku |  | Water, Irrigation, Environment and Natural Resources | Water & Irrigation | Water & Irrigation | 2016-06-30 | 2016-07-01 | 2017-06-30 |  | 4000000 | 4000000 | 4000000 | CGK | N/A | 4000000 | 0 | 3985500 | 99.64% | 3985500 | 14500 | 14500 | Completed | [6 empty] | No |  | Environmental | No | Propose budget for screening | No | Propose budget for screening | Yes | Fesibility studies and design
145 | Kibaoni borehole | Borehole equipping & construction of watering facilites | Increase access to safe and affordable water | Borehole drilled and equipped |  | Kibaoni borehole | Kajiado South | Rombo |  | Water, Irrigation, Environment and Natural Resources | Water & Irrigation | Water & Irrigation | 2016-06-30 | 2016-07-01 | 2017-06-30 |  | 4000000 | 4000000 | 4000000 | CGK | N/A | 4000000 | 0 |  | 0% |  | 4000000 | 4000000 | Completed | [6 empty] | No |  | Environmental | No | Propose budget for screening | No | Propose budget for screening | Yes | Fesibility studies and design
146 | Njukini borehole | Borehole drilling and equipping | Increase access to safe and affordable water | Borehole drilled and equipped |  | Njukini borehole | Kajiado South | Rombo |  | Water, Irrigation, Environment and Natural Resources | Water & Irrigation | Water & Irrigation | 2016-06-30 | 2016-07-01 | 2017-06-30 |  | 4000000 | 4000000 | 4000000 | CGK | N/A | 4000000 | 0 | 3990125 | 99.75% | 3990125 | 9875 | 9875 | Completed | [6 empty] | No |  | Environmental | No | Propose budget for screening | No | Propose budget for screening | Yes | Fesibility studies and design
147 | Oloshonyokie borehole | Borehole equipping | Increase access to safe and affordable water | Borehole equipped |  | Oloshonyokie borehole | Kajiado South | Rombo |  | Water, Irrigation, Environment and Natural Resources | Water & Irrigation | Water & Irrigation | 2016-06-30 | 2016-07-01 | 2017-06-30 |  | 500000 | 500000 | 500000 | CGK | N/A | 500000 | 0 |  | 0% |  | 500000 | 500000 | Completed | [6 empty] | No |  | Environmental | No | Propose budget for screening | No | Propose budget for screening | Yes | Fesibility studies and design
148 | Mukuna pipeline | Water pipeline extension | Increase access to safe and affordable water | Pipeline constructed |  | Mukuna pipeline | Kajiado South | Rombo |  | Water, Irrigation, Environment and Natural Resources | Water & Irrigation | Water & Irrigation | 2016-06-30 | 2016-07-01 | 2017-06-30 |  | 500000 | 500000 | 500000 | CGK | N/A | 500000 | 0 |  | 0% |  | 500000 | 500000 | Completed | [6 empty] | No |  | Environmental | No | Propose budget for screening | No | Propose budget for screening | Yes | Fesibility studies and design
149 | Intake- canal - Musangiro Olepolos | Canal construction | Increase area under irrigation | Canal constructed |  | Intake- canal - Musangiro Olepolos | Kajiado South | Rombo |  | Water, Irrigation, Environment and Natural Resources | Water & Irrigation | Water & Irrigation | 2016-06-30 | 2016-07-01 | 2017-06-30 |  | 1200000 | 1200000 | 1200000 | CGK | N/A | 1200000 | 0 |  | 0% |  | 1200000 | 1200000 | Completed | [6 empty] | No |  | Environmental | No | Propose budget for screening | No | Propose budget for screening | Yes | Fesibility studies and design
150 | Murantawua borehole | Rehabilitation of machine | Increase access to safe and affordable water | Genset rehabilitated |  | Murantawua borehole | Kajiado Central | Ildamat |  | Water, Irrigation, Environment and Natural Resources | Water & Irrigation | Water & Irrigation | 2016-06-30 | 2016-07-01 | 2017-06-30 |  | 1200000 | 1200000 | 1200000 | CGK | N/A | 1200000 | 0 | 989255 | 82.44% | 989255 | 210745 | 210745 | Completed | [6 empty] | No |  | Environmental | No | Propose budget for screening | No | Propose budget for screening | Yes | Fesibility studies and design
151 | Intinyika borehole | Piping water to Oloilalei | Increase access to safe and affordable water | Pipeline constructed |  | Intinyika borehole | Kajiado Central | Ildamat |  | Water, Irrigation, Environment and Natural Resources | Water & Irrigation | Water & Irrigation | 2016-06-30 | 2016-07-01 | 2017-06-30 |  | 4100000 | 4100000 | 4100000 | CGK | N/A | 4100000 | 0 | 3975000 | 96.95% | 3975000 | 125000 | 125000 | Completed | [6 empty] | No |  | Environmental | No | Propose budget for screening | No | Propose budget for screening | Yes | Fesibility studies and design
152 | Nalepo borehole | Rehabilitation of Nalepo borehole | Increase access to safe and affordable water | Borehole rehabilitated |  | Nalepo borehole | Kajiado Central | Ildamat |  | Water, Irrigation, Environment and Natural Resources | Water & Irrigation | Water & Irrigation | 2016-06-30 | 2016-07-01 | 2017-06-30 |  | 1500000 | 1500000 | 1500000 | CGK | N/A | 1500000 | 0 | 1498340 | 99.89% | 1498340 | 1660 | 1660 | Completed | [6 empty] | No |  | Environmental | No | Propose budget for screening | No | Propose budget for screening | Yes | Fesibility studies and design
153 | Esukuta borehole | Drilling and equipping of a borehole | Increase access to safe and affordable water | Borehole drilled and equipped |  | Esukuta borehole | Kajiado Central | Ildamat |  | Water, Irrigation, Environment and Natural Resources | Water & Irrigation | Water & Irrigation | 2016-06-30 | 2016-07-01 | 2017-06-30 |  | 7000000 | 7000000 | 7000000 | CGK | N/A | 7000000 | 0 | 3028760 | 43.27% | 3028760 | 3971240 | 3971240 | Completed | [6 empty] | No |  | Environmental | No | Propose budget for screening | No | Propose budget for screening | Yes | Fesibility studies and design
154 | Olmitong borehole | Pipeline extension | Increase access to safe and affordable water | Pipeline constructed |  | Olmitong borehole | Kajiado Central | Ildamat |  | Water, Irrigation, Environment and Natural Resources | Water & Irrigation | Water & Irrigation | 2016-06-30 | 2016-07-01 | 2017-06-30 |  | 2000000 | 2000000 | 2000000 | CGK | N/A | 2000000 | 0 |  | 0% |  | 2000000 | 2000000 | Completed | [6 empty] | No |  | Environmental | No | Propose budget for screening | No | Propose budget for screening | Yes | Fesibility studies and design
155 | Isilale borehole | Construction of Isilale Primary School pipeline | Increase access to safe and affordable water | Pipeline constructed |  | Isilale borehole | Kajiado Central | Dalalaekutuk |  | Water, Irrigation, Environment and Natural Resources | Water & Irrigation | Water & Irrigation | 2016-06-30 | 2016-07-01 | 2017-06-30 |  | 7000000 | 7000000 | 7000000 | CGK | N/A | 7000000 | 0 | 1970000 | 28.14% | 1970000 | 5030000 | 5030000 | Completed | [6 empty] | No |  | Environmental | No | Propose budget for screening | No | Propose budget for screening | Yes | Fesibility studies and design
156 | Olobelibel community borehole | Drilling and development of Olobelibeli borehole | Increase access to safe and affordable water | Borehole drilled and equipped |  | Olobelibel community borehole | Kajiado Central | Dalalaekutuk |  | Water, Irrigation, Environment and Natural Resources | Water & Irrigation | Water & Irrigation | 2016-06-30 | 2016-07-01 | 2017-06-30 |  | 7000000 | 7000000 | 7000000 | CGK | N/A | 7000000 | 0 | 2930000 | 41.86% | 2930000 | 4070000 | 4070000 | Completed | [6 empty] | No |  | Environmental | No | Propose budget for screening | No | Propose budget for screening | Yes | Fesibility studies and design
157 | Piping from Oldonyo to Olchorro Oibor | Water piping | Increase access to safe and affordable water | Pipeline constructed |  | Piping from Oldonyo to Olchorro Oibor | Kajiado Central | Matapato North |  | Water, Irrigation, Environment and Natural Resources | Water & Irrigation | Water & Irrigation | 2016-06-30 | 2016-07-01 | 2017-06-30 |  | 5000000 | 5000000 | 5000000 | CGK | N/A | 5000000 | 0 | 4984000 | 99.68% | 4984000 | 16000 | 16000 | Completed | [6 empty] | No |  | Environmental | No | Propose budget for screening | No | Propose budget for screening | Yes | Fesibility studies and design
158 | Emukutan borehole | Construction of watering facilities | Increase access to safe and affordable water | Watering facilities constructed |  | Emukutan borehole | Kajiado Central | Matapato North |  | Water, Irrigation, Environment and Natural Resources | Water & Irrigation | Water & Irrigation | 2016-06-30 | 2016-07-01 | 2017-06-30 |  | 1450000 | 1450000 | 1450000 | CGK | N/A | 1450000 | 0 |  | 0% |  | 1450000 | 1450000 | Completed | [6 empty] | No |  | Environmental | No | Propose budget for screening | No | Propose budget for screening | Yes | Fesibility studies and design
159 | Endonyio borehole | Construction of watering facilities | Increase access to safe and affordable water | Watering facilities constructed |  | Endonyio borehole | Kajiado Central | Matapato North |  | Water, Irrigation, Environment and Natural Resources | Water & Irrigation | Water & Irrigation | 2016-06-30 | 2016-07-01 | 2017-06-30 |  | 1450000 | 1450000 | 1450000 | CGK | N/A | 1450000 | 0 |  | 0% |  | 1450000 | 1450000 | Completed | [6 empty] | No |  | Environmental | No | Propose budget for screening | No | Propose budget for screening | Yes | Fesibility studies and design
160 | Eluanata dispensary borehole | Rehabilitation of Eluanata Community Dispensary pipeline | Increase access to safe and affordable water | Pipeline rehabilitated |  | Eluanata dispensary borehole | Kajiado Central | Matapato North |  | Water, Irrigation, Environment and Natural Resources | Water & Irrigation | Water & Irrigation | 2016-06-30 | 2016-07-01 | 2017-06-30 |  | 1500000 | 1500000 | 1500000 | CGK | N/A | 1500000 | 0 | 1499800 | 99.99% | 1499800 | 200 | 200 | Completed | [6 empty] | No |  | Environmental | No | Propose budget for screening | No | Propose budget for screening | Yes | Fesibility studies and design
161 | Oloorisheta borehole | Equipping and repair of Olooresheta community borehole | Increase access to safe and affordable water | Borehole equipped |  | Oloorisheta borehole | Kajiado Central | Purko |  | Water, Irrigation, Environment and Natural Resources | Water & Irrigation | Water & Irrigation | 2016-06-30 | 2016-07-01 | 2017-06-30 |  | 2000000 | 2000000 | 2000000 | CGK | N/A | 2000000 | 0 | 1991000 | 99.55% | 1991000 | 9000 | 9000 | Completed | [6 empty] | No |  | Environmental | No | Propose budget for screening | No | Propose budget for screening | Yes | Fesibility studies and design
162 | Ilng'osuani borehole | Equipping of Ngosuani borehole | Increase access to safe and affordable water | Borehole equipped |  | Ilng'osuani borehole | Kajiado Central | Purko |  | Water, Irrigation, Environment and Natural Resources | Water & Irrigation | Water & Irrigation | 2016-06-30 | 2016-07-01 | 2017-06-30 |  | 4000000 | 4000000 | 4000000 | CGK | N/A | 4000000 | 0 | 3991900 | 99.8% | 3991900 | 8100 | 8100 | Completed | [6 empty] | No |  | Environmental | No | Propose budget for screening | No | Propose budget for screening | Yes | Fesibility studies and design
163 | Noltepesi dam | Construction of Noltepesi Pan fence | Improve water quality by reducing pollution | Fence constructed |  | Noltepesi dam | Kajiado Central | Purko |  | Water, Irrigation, Environment and Natural Resources | Water & Irrigation | Water & Irrigation | 2016-06-30 | 2016-07-01 | 2017-06-30 |  | 600000 | 600000 | 600000 | CGK | N/A | 600000 | 0 | 599500 | 99.92% | 599500 | 500 | 500 | Completed | [6 empty] | No |  | Environmental | No | Propose budget for screening | No | Propose budget for screening | Yes | Fesibility studies and design
164 | Olekilil borehole | Drilling and equipping of a borehole | Increase access to safe and affordable water | Borehole drilled and equipped |  | Olekilil borehole | Kajiado West | Mosiro |  | Water, Irrigation, Environment and Natural Resources | Water & Irrigation | Water & Irrigation | 2016-06-30 | 2016-07-01 | 2017-06-30 |  | 7000000 | 7000000 | 7000000 | CGK | N/A | 7000000 | 0 |  | 0% |  | 7000000 | 7000000 | Completed | [6 empty] | No |  | Environmental | No | Propose budget for screening | No | Propose budget for screening | Yes | Fesibility studies and design
165 | Olorkunono borehole | Drilling and equipping of a borehole | Increase access to safe and affordable water | Borehole drilled and equipped |  | Olorkunono borehole | Kajiado West | Mosiro |  | Water, Irrigation, Environment and Natural Resources | Water & Irrigation | Water & Irrigation | 2016-06-30 | 2016-07-01 | 2017-06-30 |  | 7000000 | 7000000 | 7000000 | CGK | N/A | 7000000 | 0 |  | 0% |  | 7000000 | 7000000 | Completed | [6 empty] | No |  | Environmental | No | Propose budget for screening | No | Propose budget for screening | Yes | Fesibility studies and design
166 | Oldepe borehole | Drilling and equipping of a borehole | Increase access to safe and affordable water | Borehole drilled and equipped |  | Oldepe borehole | Kajiado West | Mosiro |  | Water, Irrigation, Environment and Natural Resources | Water & Irrigation | Water & Irrigation | 2016-06-30 | 2016-07-01 | 2017-06-30 |  | 3000000 | 3000000 | 3000000 | CGK | N/A | 3000000 | 0 | 2999760 | 99.99% | 2999760 | 240 | 240 | Completed | [6 empty] | No |  | Environmental | No | Propose budget for screening | No | Propose budget for screening | Yes | Fesibility studies and design
167 | Embarbal school | Construction of Embarbal School pipeline from | Increase access to safe and affordable water | Pipeline constructed |  | Embarbal school | Kajiado West | Mosiro |  | Water, Irrigation, Environment and Natural Resources | Water & Irrigation | Water & Irrigation | 2016-06-30 | 2016-07-01 | 2017-06-30 |  | 2000000 | 2000000 | 2000000 | CGK | N/A | 2000000 | 0 | 1998000 | 99.9% | 1998000 | 2000 | 2000 | Completed | [6 empty] | No |  | Environmental | No | Propose budget for screening | No | Propose budget for screening | Yes | Fesibility studies and design
168 | Purchase of Kibiko Water Tank | Supply, installation of tanks and pipeline at Kibiko | Increase access to safe and affordable water | Tanks supplied |  | Purchase of Kibiko Water Tank | Kajiado West | Ewuaso |  | Water, Irrigation, Environment and Natural Resources | Water & Irrigation | Water & Irrigation | 2016-06-30 | 2016-07-01 | 2017-06-30 |  | 1000000 | 1000000 | 1000000 | CGK | N/A | 1000000 | 0 | 1000000 | 100% | 1000000 | 0 | 0 | Completed | [6 empty] | No |  | Environmental | No | Propose budget for screening | No | Propose budget for screening | Yes | Fesibility studies and design
169 | Olepasikirie water tank | Extension of pipeline, rehabilitation of tank and CWP | Increase access to safe and affordable water | Pipeline constructed |  | Olepasikirie water tank | Kajiado West | Ewuaso |  | Water, Irrigation, Environment and Natural Resources | Water & Irrigation | Water & Irrigation | 2016-06-30 | 2016-07-01 | 2017-06-30 |  | 5000000 | 5000000 | 5000000 | CGK | N/A | 5000000 | 0 |  | 0% |  | 5000000 | 5000000 | Completed | [6 empty] | No |  | Environmental | No | Propose budget for screening | No | Propose budget for screening | Yes | Fesibility studies and design
170 | Isek borehole | Drilling and equipping of a borehole | Increase access to safe and affordable water | Borehole drilled and equipped |  | Isek borehole | Kajiado West | Ewuaso |  | Water, Irrigation, Environment and Natural Resources | Water & Irrigation | Water & Irrigation | 2016-06-30 | 2016-07-01 | 2017-06-30 |  | 1000000 | 1000000 | 1000000 | CGK | N/A | 1000000 | 0 | 998100 | 99.81% | 998100 | 1900 | 1900 | Completed | [6 empty] | No |  | Environmental | No | Propose budget for screening | No | Propose budget for screening | Yes | Fesibility studies and design
171 | Komiya Water Project | Construction of 50m3 masonry storage tank | Increase access to safe and affordable water | Storage tank constructed |  | Komiya Water Project | Kajiado West | Magadi |  | Water, Irrigation, Environment and Natural Resources | Water & Irrigation | Water & Irrigation | 2016-06-30 | 2016-07-01 | 2017-06-30 |  | 1500000 | 1500000 | 1500000 | CGK | N/A | 1500000 | 0 |  | 0% |  | 1500000 | 1500000 | Completed | [6 empty] | No |  | Environmental | No | Propose budget for screening | No | Propose budget for screening | Yes | Fesibility studies and design
172 | Ooshaki along the high way | Construction of underground tank | Increase access to safe and affordable water | Storage tank constructed |  | Ooshaki along the high way | Kajiado West | Magadi |  | Water, Irrigation, Environment and Natural Resources | Water & Irrigation | Water & Irrigation | 2016-06-30 | 2016-07-01 | 2017-06-30 |  | 2000000 | 2000000 | 2000000 | CGK | N/A | 2000000 | 0 |  | 0% |  | 2000000 | 2000000 | Completed | [6 empty] | No |  | Environmental | No | Propose budget for screening | No | Propose budget for screening | Yes | Fesibility studies and design
173 | Construction of Kisamis Pipeline | Water piping from Kisamis- water point and tank rehabilitation | Increase access to safe and affordable water | Pipeline constructed |  | Construction of Kisamis Pipeline | Kajiado West | Ikeekonyokie |  | Water, Irrigation, Environment and Natural Resources | Water & Irrigation | Water & Irrigation | 2016-06-30 | 2016-07-01 | 2017-06-30 |  | 3500000 | 3500000 | 3500000 | CGK | N/A | 3500000 | 0 | 2990000 | 85.43% |  | 510000 | 510000 | Completed | [6 empty] | No |  | Environmental | No | Propose budget for screening | No | Propose budget for screening | Yes | Fesibility studies and design
174 | Kudu- Oltepesi Water Project | Extension of water pipeline from Kudu to Oltepesi | Increase access to safe and affordable water | Pipeline constructed |  | Kudu- Oltepesi Water Project | Kajiado West | Loodokilani |  | Water, Irrigation, Environment and Natural Resources | Water & Irrigation | Water & Irrigation | 2016-06-30 | 2016-07-01 | 2017-06-30 |  | 3500000 | 3500000 | 3500000 | CGK | N/A | 3500000 | 0 | 3493100 | 99.8% |  | 6900 | 6900 | Completed | [6 empty] | No |  | Environmental | No | Propose budget for screening | No | Propose budget for screening | Yes | Fesibility studies and design
175 | Olosirwua borehole | Purchase of 26kva genset | Increase access to safe and affordable water | Genset purchased |  | Olosirwua borehole | Kajiado West | Loodokilani |  | Water, Irrigation, Environment and Natural Resources | Water & Irrigation | Water & Irrigation | 2016-06-30 | 2016-07-01 | 2017-06-30 |  | 1000000 | 1000000 | 1000000 | CGK | N/A | 1000000 | 0 | 985200 | 98.52% |  | 14800 | 14800 | Completed | [6 empty] | No |  | Environmental | No | Propose budget for screening | No | Propose budget for screening | Yes | Fesibility studies and design
176 | Bondeni borehole Completion | Construction of elevated tank and tower | Increase access to safe and affordable water | Storage tank constructed |  | Bondeni borehole Completion | Kajiado North | Ngong |  | Water, Irrigation, Environment and Natural Resources | Water & Irrigation | Water & Irrigation | 2016-06-30 | 2016-07-01 | 2017-06-30 |  | 1000000 | 1000000 | 1000000 | CGK | N/A | 1000000 | 0 |  | 0% |  | 1000000 | 1000000 | Completed | [6 empty] | No |  | Environmental | No | Propose budget for screening | No | Propose budget for screening | Yes | Fesibility studies and design
177 | Ngong Township Primary School | Construction of a special unit toilet | Increase access to adequate and equitable sanitation and hygiene | Toilet constructed |  | Ngong Township Primary School | Kajiado North | Ngong |  | Water, Irrigation, Environment and Natural Resources | Water & Irrigation | Water & Irrigation | 2016-06-30 | 2016-07-01 | 2017-06-30 |  | 500000 | 500000 | 500000 | CGK | N/A | 500000 | 0 |  | 0% |  | 500000 | 500000 | Completed | [6 empty] | No |  | Environmental | No | Propose budget for screening | No | Propose budget for screening | Yes | Fesibility studies and design
178 | Ngong township borehole | Drilling, equipping and construction of water facilities | Increase access to safe and affordable water | Borehole drilled and equipped |  | Ngong township borehole | Kajiado North | Ngong |  | Water, Irrigation, Environment and Natural Resources | Water & Irrigation | Water & Irrigation | 2016-06-30 | 2016-07-01 | 2017-06-30 |  | 5000000 | 5000000 | 5000000 | CGK | N/A | 5000000 | 0 |  | 0% |  | 5000000 | 5000000 | Completed | [6 empty] | No |  | Environmental | No | Propose budget for screening | No | Propose budget for screening | Yes | Fesibility studies and design
179 | Oloolua polytechnic | Construction of storm water drainage at Oloolua | Restore degraded land and soil | Storm water drainage constructed |  | Oloolua polytechnic | Kajiado North | Oloolua |  | Water, Irrigation, Environment and Natural Resources | Water & Irrigation | Water & Irrigation | 2016-06-30 | 2016-07-01 | 2017-06-30 |  | 2500000 | 2500000 | 2500000 | CGK | N/A | 2500000 | 0 | 2478045 | 99.12% | 2478045 | 21955 | 21955 | Completed | [6 empty] | No |  | Environmental | No | Propose budget for screening | No | Propose budget for screening | Yes | Fesibility studies and design
180 | Olepolos borehole | Construction of elevated tank and tower and construction of watering facilities | Increase access to safe and affordable water | Storage tank constructed |  | Olepolos borehole | Kajiado North | Oloolua |  | Water, Irrigation, Environment and Natural Resources | Water & Irrigation | Water & Irrigation | 2016-06-30 | 2016-07-01 | 2017-06-30 |  | 4000000 | 4000000 | 4000000 | CGK | N/A | 4000000 | 0 | 3995000 | 99.88% | 3995000 | 5000 | 5000 | Completed | [6 empty] | No |  | Environmental | No | Propose budget for screening | No | Propose budget for screening | Yes | Fesibility studies and design
181 | Embulbul borehole | Construction of elevated tank and tower | Increase access to safe and affordable water | Storage tank constructed |  | Embulbul borehole | Kajiado North | Oloolua |  | Water, Irrigation, Environment and Natural Resources | Water & Irrigation | Water & Irrigation | 2016-06-30 | 2016-07-01 | 2017-06-30 |  | 9000000 | 9000000 | 9000000 | CGK | N/A | 9000000 | 0 | 3988000 | 44.31% | 3988000 | 5012000 | 5012000 | Completed | [6 empty] | No |  | Environmental | No | Propose budget for screening | No | Propose budget for screening | Yes | Fesibility studies and design
182 | Oloitiko Iloshon borehole | Construction of Oloitiko- Iloshon borehole | Increase access to safe and affordable water | Borehole drilled and equipped |  | Oloitiko Iloshon borehole | Kajiado East | Imaroro |  | Water, Irrigation, Environment and Natural Resources | Water & Irrigation | Water & Irrigation | 2016-06-30 | 2016-07-01 | 2017-06-30 |  | 9000000 | 9000000 | 9000000 | CGK | N/A | 9000000 | 0 | 8988300 | 99.87% | 8988300 | 11700 | 11700 | Completed | [6 empty] | No |  | Environmental | No | Propose budget for screening | No | Propose budget for screening | Yes | Fesibility studies and design
183 | Noongaboio borehole | Drilling and equipping of a borehole | Increase access to safe and affordable water | Borehole drilled and equipped |  | Noongaboio borehole | Kajiado East | Kenyewa poka |  | Water, Irrigation, Environment and Natural Resources | Water & Irrigation | Water & Irrigation | 2016-06-30 | 2016-07-01 | 2017-06-30 |  | 5000000 | 5000000 | 5000000 | CGK | N/A | 5000000 | 0 |  | 0% |  | 5000000 | 5000000 | Completed | [6 empty] | No |  | Environmental | No | Propose budget for screening | No | Propose budget for screening | Yes | Fesibility studies and design
184 | Noosidan borehole | Drilling and development of Noosidan borehole | Increase access to safe and affordable water | Borehole drilled and equipped |  | Noosidan borehole | Kajiado East | Kenyewa poka |  | Water, Irrigation, Environment and Natural Resources | Water & Irrigation | Water & Irrigation | 2016-06-30 | 2016-07-01 | 2017-06-30 |  | 5800000 | 5800000 | 5800000 | CGK | N/A | 5800000 | 0 | 2930000 | 50.52% | 2930000 | 2870000 | 2870000 | Completed | [6 empty] | No |  | Environmental | No | Propose budget for screening | No | Propose budget for screening | Yes | Fesibility studies and design
185 | Olmerrui borehole | Drilling and equipping of a borehole | Increase access to safe and affordable water | Borehole drilled and equipped |  | Olmerrui borehole | Kajiado East | Keputei North |  | Water, Irrigation, Environment and Natural Resources | Water & Irrigation | Water & Irrigation | 2016-06-30 | 2016-07-01 | 2017-06-30 |  | 7500000 | 7500000 | 7500000 | CGK | N/A | 7500000 | 0 | 7450000 | 99.33% | 7450000 | 50000 | 50000 | Completed | [6 empty] | No |  | Environmental | No | Propose budget for screening | No | Propose budget for screening | Yes | Fesibility studies and design
186 | Isinya borehole | Equipping of isinya borehole | Increase access to safe and affordable water | Borehole equipped |  | Isinya borehole | Kajiado East | Keputei North |  | Water, Irrigation, Environment and Natural Resources | Water & Irrigation | Water & Irrigation | 2016-06-30 | 2016-07-01 | 2017-06-30 |  | 4000000 | 4000000 | 4000000 | CGK | N/A | 4000000 | 0 |  | 0% |  | 4000000 | 4000000 | Completed | [6 empty] | No |  | Environmental | No | Propose budget for screening | No | Propose budget for screening | Yes | Fesibility studies and design
187 | Enkilele borehole | Borehole equipping | Increase access to safe and affordable water | Borehole equipped |  | Enkilele borehole | Kajiado East | Keputei North |  | Water, Irrigation, Environment and Natural Resources | Water & Irrigation | Water & Irrigation | 2016-06-30 | 2016-07-01 | 2017-06-30 |  | 1000000 | 1000000 | 1000000 | CGK | N/A | 1000000 | 0 |  | 0% |  | 1000000 | 1000000 | Completed | [6 empty] | No |  | Environmental | No | Propose budget for screening | No | Propose budget for screening | Yes | Fesibility studies and design
188 | Olkinois borehole | Rehabilitation of borehole and watering facilities | Increase access to safe and affordable water | Borehole rehabilitated |  | Olkinois borehole | Kajiado East | Keputei North |  | Water, Irrigation, Environment and Natural Resources | Water & Irrigation | Water & Irrigation | 2016-06-30 | 2016-07-01 | 2017-06-30 |  | 4000000 | 4000000 | 4000000 | CGK | N/A | 4000000 | 0 |  | 0% |  | 4000000 | 4000000 | Completed | [6 empty] | No |  | Environmental | No | Propose budget for screening | No | Propose budget for screening | Yes | Fesibility studies and design
189 | Olturoto borehole | Borehole equipping | Increase access to safe and affordable water | Borehole equipped |  | Olturoto borehole | Kajiado East | Keputei North |  | Water, Irrigation, Environment and Natural Resources | Water & Irrigation | Water & Irrigation | 2016-06-30 | 2016-07-01 | 2017-06-30 |  | 3000000 | 3000000 | 3000000 | CGK | N/A | 3000000 | 0 | 2698000 | 89.93% | 2698000 | 302000 | 302000 | Completed | [6 empty] | No |  | Environmental | No | Propose budget for screening | No | Propose budget for screening | Yes | Fesibility studies and design
190 | PJ dave borehole | Borehole equipping | Increase access to safe and affordable water | Borehole equipped |  | PJ dave borehole | Kajiado East | Keputei North |  | Water, Irrigation, Environment and Natural Resources | Water & Irrigation | Water & Irrigation | 2016-06-30 | 2016-07-01 | 2017-06-30 |  | 2500000 | 2500000 | 2500000 | CGK | N/A | 2500000 | 0 | 2494000 | 99.76% | 2494000 | 6000 | 6000 | Completed | [6 empty] | No |  | Environmental | No | Propose budget for screening | No | Propose budget for screening | Yes | Fesibility studies and design
191 | Sholinke borehole | Borehole equipping | Increase access to safe and affordable water | Borehole equipped |  | Sholinke borehole | Kajiado East | Oloosrikon |  | Water, Irrigation, Environment and Natural Resources | Water & Irrigation | Water & Irrigation | 2016-06-30 | 2016-07-01 | 2017-06-30 |  | 1000000 | 1000000 | 1000000 | CGK | N/A | 1000000 | 0 | 989941 | 98.99% | 989941 | 10059 | 10059 | Completed | [6 empty] | No |  | Environmental | No | Propose budget for screening | No | Propose budget for screening | Yes | Fesibility studies and design
192 | Olngarua borehole | Equipping of borehole and construction of 3.5km pipeline | Increase access to safe and affordable water | Borehole equipped |  | Olngarua borehole | Kajiado East | Oloosrikon |  | Water, Irrigation, Environment and Natural Resources | Water & Irrigation | Water & Irrigation | 2016-06-30 | 2016-07-01 | 2017-06-30 |  | 3000000 | 3000000 | 3000000 | CGK | N/A | 3000000 | 0 | 2990000 | 99.67% | 2990000 | 10000 | 10000 | Completed | [6 empty] | No |  | Environmental | No | Propose budget for screening | No | Propose budget for screening | Yes | Fesibility studies and design
193 | Matali, Kitengela and Sholinke Public Toilets | Construction of toilets | Increase access to adequate and equitable sanitation and hygiene | Toilet constructed |  | Matali, Kitengela and Sholinke Public Toilets | Kajiado East | Oloosrikon |  | Water, Irrigation, Environment and Natural Resources | Water & Irrigation | Water & Irrigation | 2016-06-30 | 2016-07-01 | 2017-06-30 |  | 2500000 | 2500000 | 2500000 | CGK | N/A | 2500000 | 0 | 2494000 | 99.76% | 2494000 | 6000 | 6000 | Completed | [6 empty] | No |  | Environmental | No | Propose budget for screening | No | Propose budget for screening | Yes | Fesibility studies and design
194 | Ilkuruki borehole | Borehole equipping and construction of watering facilities | Increase access to safe and affordable water | Borehole drilled and equipped |  | Ilkuruki borehole | Kajiado North | Ngong |  | Water, Irrigation, Environment and Natural Resources | Water & Irrigation | Water & Irrigation | 2016-06-30 | 2016-07-01 | 2017-06-30 |  | 3000000 | 3000000 | 3000000 | CGK | N/A | 3000000 | 0 | 2988700 | 99.62% | 2988700 | 11300 | 11300 | Stalled | 0% | 0% | Inadequate finances | 2017 | 6 | 11300 | No | Defer | Financial | No | Propose budget for screening | No | Propose budget for screening | Yes | Fesibility studies and design
195 | Kirkuria borehole | Rehabilitation of kirkuria borehole | Increase access to safe and affordable water | Borehole rehabilitated |  | Kirkuria borehole | Kajiado East | keekonyokie |  | Water, Irrigation, Environment and Natural Resources | Water & Irrigation | Water & Irrigation | 2016-06-30 | 2016-07-01 | 2017-06-30 |  | 2500000 | 2500000 | 2500000 | CGK | N/A | 2500000 | 0 |  | 0% |  | 2500000 | 2500000 | Completed | [6 empty] | No |  | Environmental | No | Propose budget for screening | No | Propose budget for screening | Yes | Fesibility studies and design
196 | Nairode borehole | Equipping of Nairode borehole | Increase access to safe and affordable water | Borehole equipped |  | Nairode borehole | Kajiado West | Ewasokedong |  | Water, Irrigation, Environment and Natural Resources | Water & Irrigation | Water & Irrigation | 2016-06-30 | 2016-07-01 | 2017-06-30 |  | 3000000 | 3000000 | 3000000 | CGK | N/A | 3000000 | 0 |  | 0% |  | 3000000 | 3000000 | Completed | [6 empty] | No |  | Environmental | No | Propose budget for screening | No | Propose budget for screening | Yes | Fesibility studies and design
197 | Musenke water project | Extension of Musenke pipeline project | Increase access to safe and affordable water | Pipeline constructed |  | Musenke water project | Kajiado West | Magadi |  | Water, Irrigation, Environment and Natural Resources | Water & Irrigation | Water & Irrigation | 2016-06-30 | 2016-07-01 | 2017-06-30 |  | 1000000 | 1000000 | 1000000 | CGK | N/A | 1000000 | 0 |  | 0% |  | 1000000 | 1000000 | Completed | [6 empty] | No |  | Environmental | No | Propose budget for screening | No | Propose budget for screening | Yes | Fesibility studies and design
198 | Naika borehole | Borehole equipping and construction of watering facilities | Increase access to safe and affordable water | Borehole equipped |  | Naika borehole | Kajiado East | Kenyewa |  | Water, Irrigation, Environment and Natural Resources | Water & Irrigation | Water & Irrigation | 2016-06-30 | 2016-07-01 | 2017-06-30 |  | 3000000 | 3000000 | 3000000 | CGK | N/A | 3000000 | 0 | 2990200 | 99.67% | 2990200 | 9800 | 9800 | Completed | [6 empty] | No |  | Environmental | No | Propose budget for screening | No | Propose budget for screening | Yes | Fesibility studies and design
199 | Enkutoto Naretoi borehole | Borehole equipping and construction of watering facilities | Increase access to safe and affordable water | Borehole equipped |  | Enkutoto Naretoi borehole | Kajiado East | Olosirnko |  | Water, Irrigation, Environment and Natural Resources | Water & Irrigation | Water & Irrigation | 2016-06-30 | 2016-07-01 | 2017-06-30 |  | 2500000 | 2500000 | 2500000 | CGK | N/A | 2500000 | 0 | 2485000 | 99.4% | 2485000 | 15000 | 15000 | Completed | [6 empty] | No |  | Environmental | No | Propose budget for screening | No | Propose budget for screening | Yes | Fesibility studies and design
200 | Lenchani borehole | Equipping and construction of a storage tank | Increase access to safe and affordable water | Borehole equipped |  | Lenchani borehole | Kajiado Central | Matapato North |  | Water, Irrigation, Environment and Natural Resources | Water & Irrigation | Water & Irrigation | 2016-06-30 | 2016-07-01 | 2017-06-30 |  | 2000000 | 2000000 | 2000000 | CGK | N/A | 2000000 | 0 | 1990000 | 99.5% | 1990000 | 10000 | 10000 | Completed | [6 empty] | No |  | Environmental | No | Propose budget for screening | No | Propose budget for screening | Yes | Fesibility studies and design
201 | Olotimeloi borehole | Borehole equipping and construction of watering facilities | Increase access to safe and affordable water | Borehole equipped |  | Olotimeloi borehole | Kajiado Central | Matapato North |  | Water, Irrigation, Environment and Natural Resources | Water & Irrigation | Water & Irrigation | 2016-06-30 | 2016-07-01 | 2017-06-30 |  | 2500000 | 2500000 | 2500000 | CGK | N/A | 2500000 | 0 |  | 0% |  | 2500000 | 2500000 | Completed | [6 empty] | No |  | Environmental | No | Propose budget for screening | No | Propose budget for screening | Yes | Fesibility studies and design
202 | Osiligimaa borehole | Borehole equipping and construction of watering facilities | Increase access to safe and affordable water | Borehole equipped |  | Osiligimaa borehole | Kajiado South | Lenkisim |  | Water, Irrigation, Environment and Natural Resources | Water & Irrigation | Water & Irrigation | 2016-06-30 | 2016-07-01 | 2017-06-30 |  | 3000000 | 3000000 | 3000000 | CGK | N/A | 3000000 | 0 | 2995000 | 99.83% | 2995000 | 5000 | 5000 | Completed | [6 empty] | No |  | Environmental | No | Propose budget for screening | No | Propose budget for screening | Yes | Fesibility studies and design
203 | Kajiado town water pipeline | Improvement of reticulation network in Kajiado | Increase access to safe and affordable water | Water reticulation done |  | Kajiado town water pipeline | Kajiado Central | Ildamat |  | Water, Irrigation, Environment and Natural Resources | Water & Irrigation | Water & Irrigation | 2016-06-30 | 2016-07-01 | 2017-06-30 |  | 5000000 | 5000000 | 5000000 | CGK | N/A | 5000000 | 0 | 4999990 | 100% | 4999990 | 10 | 10 | Completed | [6 empty] | No |  | Environmental | No | Propose budget for screening | No | Propose budget for screening | Yes | Fesibility studies and design
204 | Ewuaso water piping | Construction of Ewuaso Enkidong water supply | Increase access to safe and affordable water | Pipeline constructed |  | Ewuaso water piping | Kajiado West | Ewasokedong |  | Water, Irrigation, Environment and Natural Resources | Water & Irrigation | Water & Irrigation | 2016-06-30 | 2016-07-01 | 2017-06-30 |  | 6000000 | 6000000 | 6000000 | CGK | N/A | 6000000 | 0 | 5987050 | 99.78% | 5987050 | 12950 | 12950 | Completed | [6 empty] | No |  | Environmental | No | Propose budget for screening | No | Propose budget for screening | Yes | Fesibility studies and design
205 | Mosiro irrigation | Intake construction, pipeline and storage tank | Increase area under irrigation | Irrigation scheme constructed |  | Mosiro irrigation | Kajiado West | Mosiro |  | Water, Irrigation, Environment and Natural Resources | Water & Irrigation | Water & Irrigation | 2016-06-30 | 2016-07-01 | 2017-06-30 |  | 17934330 | 17934330 | 17934330 | CGK | N/A | 17934330 | 0 | 17845963 | 99.51% | 17845963 | 88367 | 88367 | Stalled | 40% | 40% | Inadequate finances | 2017 | 6 | 88367 | No | Defer | Financial | No | Propose budget for screening | No | Propose budget for screening | Yes | Fesibility studies and design
206 | Construction of Uswa water project | Borehole solarization, pipeline and watering facilities construction | Increase access to safe and affordable water | Pipeline constructed |  | Construction of Uswa water project | Kajiado West | Iloodokilani |  | Water, Irrigation, Environment and Natural Resources | Water & Irrigation | Water & Irrigation | 2016-06-30 | 2016-07-01 | 2017-06-30 |  | 20000000 | 20000000 | 20000000 | CGK | N/A | 20000000 | 0 | 19514448 | 97.57% | 19514448 | 485552 | 485552 | Completed | [6 empty] | No |  | Environmental | No | Propose budget for screening | No | Propose budget for screening | Yes | Fesibility studies and design
207 | Gitwe springs development project for Gitwe water providers association | Extension of water pipeline to Jerusalem | Increase access to safe and affordable water | Pipeline constructed |  | Gitwe springs development project for Gitwe water providers association | Kajiado North | OLOOLUA |  | Water, Irrigation, Environment and Natural Resources | Water & Irrigation | Water & Irrigation | 2017-06-30 | 2017-07-01 | 2018-06-01 |  | 1500000 | 1500000 | 1500000 | CGK | N/A | 1500000 | 0 | 0 | 0% |  | 1500000 | 1500000 | Completed | [6 empty] | No |  | Environmental | No | Propose budget for screening | No | Propose budget for screening | Yes | Fesibility studies and design
208 | Oloisho-Ololete borehole | Supply and piping of water | Increase access to safe and affordable water | Pipeline constructed |  | Oloisho-Ololete borehole | Kajiado North | NGONG |  | Water, Irrigation, Environment and Natural Resources | Water & Irrigation | Water & Irrigation | 2017-06-30 | 2017-07-01 | 2018-06-01 |  | 6000000 | 6000000 | 6000000 | CGK | N/A | 6000000 | 0 | 0 | 0% |  | 6000000 | 6000000 | Stalled | 40% | 40% | Inadequate finances | 2018 | 6 | 6000000 | No | Defer | Financial | No | Propose budget for screening | No | Propose budget for screening | Yes | Fesibility studies and design
209 | Piping of water from Florida and Township borehole to homesteads | Piping of water from Florida and Township borehole to homesteads | Increase access to safe and affordable water | Pipeline constructed |  | Piping of water from Florida and Township borehole to homesteads | Kajiado North | NGONG |  | Water, Irrigation, Environment and Natural Resources | Water & Irrigation | Water & Irrigation | 2017-06-30 | 2017-07-01 | 2018-06-01 |  | 6000000 | 6000000 | 6000000 | CGK | N/A | 6000000 | 0 | 0 | 0% |  | 6000000 | 6000000 | Completed | [6 empty] | No |  | Environmental | No | Propose budget for screening | No | Propose budget for screening | Yes | Fesibility studies and design
210 | Singiraine Belgium dam | Desilting | Increase access to safe and affordable water | Dam desiltated |  | Singiraine Belgium dam | Kajiado West | LOODOKILANI |  | Water, Irrigation, Environment and Natural Resources | Water & Irrigation | Water & Irrigation | 2017-06-30 | 2017-07-01 | 2018-06-01 |  | 2000000 | 2000000 | 2000000 | CGK | N/A | 2000000 | 0 | 0 | 0% |  | 2000000 | 2000000 | Completed | [6 empty] | No |  | Environmental | No | Propose budget for screening | No | Propose budget for screening | Yes | Fesibility studies and design
211 | Tikoishi borehole | Equipping | Increase access to safe and affordable water | Borehole equipped |  | Tikoishi borehole | Kajiado West | LOODOKILANI |  | Water, Irrigation, Environment and Natural Resources | Water & Irrigation | Water & Irrigation | 2017-06-30 | 2017-07-01 | 2018-06-01 |  | 5000000 | 5000000 | 5000000 | CGK | N/A | 5000000 | 0 | 0 | 0% |  | 5000000 | 5000000 | Completed | [6 empty] | No |  | Environmental | No | Propose budget for screening | No | Propose budget for screening | Yes | Fesibility studies and design
212 | Enchorro Esenteu borehole | Pipeline construction | Increase access to safe and affordable water | Pipeline constructed |  | Enchorro Esenteu borehole | Kajiado West | LOODOKILANI |  | Water, Irrigation, Environment and Natural Resources | Water & Irrigation | Water & Irrigation | 2017-06-30 | 2017-07-01 | 2018-06-01 |  | 7000000 | 7000000 | 7000000 | CGK | N/A | 7000000 | 0 | 0 | 0% |  | 7000000 | 7000000 | Completed | [6 empty] | No |  | Environmental | No | Propose budget for screening | No | Propose budget for screening | Yes | Fesibility studies and design
213 | Naningoi Girls borehole | Rehabilitation | Increase access to safe and affordable water | Borehole rehabilitated |  | Naningoi Girls borehole | Kajiado West | MOSIRO |  | Water, Irrigation, Environment and Natural Resources | Water & Irrigation | Water & Irrigation | 2017-06-30 | 2017-07-01 | 2018-06-01 |  | 2000000 | 2000000 | 2000000 | CGK | N/A | 2000000 | 0 | 0 | 0% |  | 2000000 | 2000000 | Completed | [6 empty] | No |  | Environmental | No | Propose budget for screening | No | Propose budget for screening | Yes | Fesibility studies and design
214 | Imariani borehole | Drilling and Equipping | Increase access to safe and affordable water | Borehole drilled and equipped |  | Imariani borehole | Kajiado West | MOSIRO |  | Water, Irrigation, Environment and Natural Resources | Water & Irrigation | Water & Irrigation | 2017-06-30 | 2017-07-01 | 2018-06-01 |  | 7000000 | 7000000 | 7000000 | CGK | N/A | 7000000 | 0 | 0 | 0% |  | 7000000 | 7000000 | Completed | [6 empty] | No |  | Environmental | No | Propose budget for screening | No | Propose budget for screening | Yes | Fesibility studies and design
215 | Kiruk borehole | Drilling and Equipping | Increase access to safe and affordable water | Borehole drilled and equipped |  | Kiruk borehole | Kajiado West | MOSIRO |  | Water, Irrigation, Environment and Natural Resources | Water & Irrigation | Water & Irrigation | 2017-06-30 | 2017-07-01 | 2018-06-01 |  | 7000000 | 7000000 | 7000000 | CGK | N/A | 7000000 | 0 | 0 | 0% |  | 7000000 | 7000000 | Completed | [6 empty] | No |  | Environmental | No | Propose budget for screening | No | Propose budget for screening | Yes | Fesibility studies and design
216 | Eiti Kisamis Pry Sch Borehole | Drilling and Equipping | Increase access to safe and affordable water | Borehole drilled and equipped |  | Eiti Kisamis Pry Sch Borehole | Kajiado West | KEEKONYOKIE |  | Water, Irrigation, Environment and Natural Resources | Water & Irrigation | Water & Irrigation | 2017-06-30 | 2017-07-01 | 2018-06-01 |  | 7000000 | 7000000 | 7000000 | CGK | N/A | 7000000 | 0 | 0 | 0% |  | 7000000 | 7000000 | Stalled | 40% | 40% | Dry borehole | 2018 | 6 | 7000000 | No | Defer | Financial | No | Propose budget for screening | No | Propose budget for screening | Yes | Fesibility studies and design
217 | Oreteti borehole - Kona baridi | Equipping | Increase access to safe and affordable water | Borehole drilled and equipped |  | Oreteti borehole - Kona baridi | Kajiado West | KEEKONYOKIE |  | Water, Irrigation, Environment and Natural Resources | Water & Irrigation | Water & Irrigation | 2017-06-30 | 2017-07-01 | 2018-06-01 |  | 2800000 | 2800000 | 2800000 | CGK | N/A | 2800000 | 0 | 0 | 0% |  | 2800000 | 2800000 | Completed | [6 empty] | No |  | Environmental | No | Propose budget for screening | No | Propose budget for screening | Yes | Fesibility studies and design
218 | Pakase modern water storage tank | Construction | Increase access to safe and affordable water | Storage tank constructed |  | Pakase modern water storage tank | Kajiado West | MAGADI |  | Water, Irrigation, Environment and Natural Resources | Water & Irrigation | Water & Irrigation | 2017-06-30 | 2017-07-01 | 2018-06-01 |  | 3000000 | 3000000 | 3000000 | CGK | N/A | 3000000 | 0 | 0 | 0% |  | 3000000 | 3000000 | Completed | [6 empty] | No |  | Environmental | No | Propose budget for screening | No | Propose budget for screening | Yes | Fesibility studies and design
219 | Lechoni Dam | Construction | Increase access to safe and affordable water | Dam constructed |  | Lechoni Dam | Kajiado West | MAGADI |  | Water, Irrigation, Environment and Natural Resources | Water & Irrigation | Water & Irrigation | 2017-06-30 | 2017-07-01 | 2018-06-01 |  | 8000000 | 8000000 | 8000000 | CGK | N/A | 8000000 | 0 | 0 | 0% |  | 8000000 | 8000000 | Completed | [6 empty] | No |  | Environmental | No | Propose budget for screening | No | Propose budget for screening | Yes | Fesibility studies and design
220 | Lorngosua - Nashipai Dominion Church water Pipeline | Completion | Increase access to safe and affordable water | Pipeline constructed |  | Lorngosua - Nashipai Dominion Church water Pipeline | Kajiado West | MAGADI |  | Water, Irrigation, Environment and Natural Resources | Water & Irrigation | Water & Irrigation | 2017-06-30 | 2017-07-01 | 2018-06-01 |  | 2000000 | 2000000 | 2000000 | CGK | N/A | 2000000 | 0 | 0 | 0% |  | 2000000 | 2000000 | Completed | [6 empty] | No |  | Environmental | No | Propose budget for screening | No | Propose budget for screening | Yes | Fesibility studies and design
221 | Kiwanja Borehole | Drilling and Equipping of a borehole | Increase access to safe and affordable water | Borehole drilled and equipped |  | Kiwanja Borehole | Kajiado South | KUKU |  | Water, Irrigation, Environment and Natural Resources | Water & Irrigation | Water & Irrigation | 2017-06-30 | 2017-07-01 | 2018-06-01 |  | 7000000 | 7000000 | 7000000 | CGK | N/A | 7000000 | 0 | 0 | 0% |  | 7000000 | 7000000 | Completed | [6 empty] | No |  | Environmental | No | Propose budget for screening | No | Propose budget for screening | Yes | Fesibility studies and design
222 | Njukini Borehole | Equipping of the borehole | Increase access to safe and affordable water | Borehole equipped |  | Njukini Borehole | Kajiado South | ROMBO |  | Water, Irrigation, Environment and Natural Resources | Water & Irrigation | Water & Irrigation | 2017-06-30 | 2017-07-01 | 2018-06-01 |  | 4000000 | 4000000 | 4000000 | CGK | N/A | 4000000 | 0 | 0 | 0% |  | 4000000 | 4000000 | Completed | [6 empty] | No |  | Environmental | No | Propose budget for screening | No | Propose budget for screening | Yes | Fesibility studies and design
223 | Olmapina Nasipa Miguira | Piping & 100cubic metres tank construction | Increase access to safe and affordable water | Pipeline constructed |  | Olmapina Nasipa Miguira | Kajiado South | ROMBO |  | Water, Irrigation, Environment and Natural Resources | Water & Irrigation | Water & Irrigation | 2017-06-30 | 2017-07-01 | 2018-06-01 |  | 1500000 | 1500000 | 1500000 | CGK | N/A | 1500000 | 0 | 0 | 0% |  | 1500000 | 1500000 | Completed | [6 empty] | No |  | Environmental | No | Propose budget for screening | No | Propose budget for screening | Yes | Fesibility studies and design
224 | Enduet Tank | Construction of a tank | Increase access to safe and affordable water | Storage tank constructed |  | Enduet Tank | Kajiado South | ROMBO |  | Water, Irrigation, Environment and Natural Resources | Water & Irrigation | Water & Irrigation | 2017-06-30 | 2017-07-01 | 2018-06-01 |  | 2000000 | 2000000 | 2000000 | CGK | N/A | 2000000 | 0 | 0 | 0% |  | 2000000 | 2000000 | Completed | [6 empty] | No |  | Environmental | No | Propose budget for screening | No | Propose budget for screening | Yes | Fesibility studies and design
225 | Loolakir/Eliti borehole | Equipping and watering facilities | Increase access to safe and affordable water | Borehole equipped |  | Loolakir/Eliti borehole | Kajiado South | ENTONET/ LENKISM |  | Water, Irrigation, Environment and Natural Resources | Water & Irrigation | Water & Irrigation | 2017-06-30 | 2017-07-01 | 2018-06-01 |  | 4000000 | 4000000 | 4000000 | CGK | N/A | 4000000 | 0 | 0 | 0% |  | 4000000 | 4000000 | Completed | [6 empty] | No |  | Environmental | No | Propose budget for screening | No | Propose budget for screening | Yes | Fesibility studies and design
226 | Olepolos/Murutot Water Project | 3Km pipeline extension and a water tank | Increase access to safe and affordable water | Pipeline constructed |  | Olepolos/Murutot Water Project | Kajiado South | ENTONET/ LENKISM |  | Water, Irrigation, Environment and Natural Resources | Water & Irrigation | Water & Irrigation | 2017-06-30 | 2017-07-01 | 2018-06-01 |  | 4500000 | 4500000 | 4500000 | CGK | N/A | 4500000 | 0 | 0 | 0% |  | 4500000 | 4500000 | Completed | [6 empty] | No |  | Environmental | No | Propose budget for screening | No | Propose budget for screening | Yes | Fesibility studies and design
227 | Olepolos Borehole | Equipping and construction of watering facilities | Increase access to safe and affordable water | Borehole equipped |  | Olepolos Borehole | Kajiado South | ENTONET/ LENKISM |  | Water, Irrigation, Environment and Natural Resources | Water & Irrigation | Water & Irrigation | 2017-06-30 | 2017-07-01 | 2018-06-01 |  | 2000000 | 2000000 | 2000000 | CGK | N/A | 2000000 | 0 | 0 | 0% |  | 2000000 | 2000000 | Completed | [6 empty] | No |  | Environmental | No | Propose budget for screening | No | Propose budget for screening | Yes | Fesibility studies and design
228 | Osiram Cultural boma water | 1.5Km pipeline extension | Increase access to safe and affordable water | Pipeline constructed |  | Osiram Cultural boma water | Kajiado South | IMBIRIKANI/ ESELENKEI |  | Water, Irrigation, Environment and Natural Resources | Water & Irrigation | Water & Irrigation | 2017-06-30 | 2017-07-01 | 2018-06-01 |  | 1500000 | 1500000 | 1500000 | CGK | N/A | 1500000 | 0 | 0 | 0% |  | 1500000 | 1500000 | Completed | [6 empty] | No |  | Environmental | No | Propose budget for screening | No | Propose budget for screening | Yes | Fesibility studies and design
229 | Enkaji Naibor farrow | 3km Canal extension works | Increase access to safe and affordable water | Canal constructed |  | Enkaji Naibor farrow | Kajiado South | IMBIRIKANI/ ESELENKEI |  | Water, Irrigation, Environment and Natural Resources | Water & Irrigation | Water & Irrigation | 2017-06-30 | 2017-07-01 | 2018-06-01 |  | 3000000 | 3000000 | 3000000 | CGK | N/A | 3000000 | 0 | 0 | 0% |  | 3000000 | 3000000 | Completed | [6 empty] | No |  | Environmental | No | Propose budget for screening | No | Propose budget for screening | Yes | Fesibility studies and design
230 | Kisilet farrow | Canal lining | Increase area under irrigation | Canal lined |  | Kisilet farrow | Kajiado South | KIMANA |  | Water, Irrigation, Environment and Natural Resources | Water & Irrigation | Water & Irrigation | 2017-06-30 | 2017-07-01 | 2018-06-01 |  | 4000000 | 4000000 | 4000000 | CGK | N/A | 4000000 | 0 | 0 | 0% |  | 4000000 | 4000000 | Completed | [6 empty] | No |  | Environmental | No | Propose budget for screening | No | Propose budget for screening | Yes | Fesibility studies and design
231 | Ilnchalai borehole | Installation of a gen set | Increase access to safe and affordable water | Genset installed |  | Ilnchalai borehole | Kajiado South | IMBIRIKANI/ ESELENKEI |  | Water, Irrigation, Environment and Natural Resources | Water & Irrigation | Water & Irrigation | 2017-06-30 | 2017-07-01 | 2018-06-01 |  | 1500000 | 1500000 | 1500000 | CGK | N/A | 1500000 | 0 | 0 | 0% |  | 1500000 | 1500000 | Completed | [6 empty] | No |  | Environmental | No | Propose budget for screening | No | Propose budget for screening | Yes | Fesibility studies and design
232 | Mashamba Mapya community borehole | 6Km pipeline extension | Increase access to safe and affordable water | Pipeline constructed |  | Mashamba Mapya community borehole | Kajiado South | KIMANA |  | Water, Irrigation, Environment and Natural Resources | Water & Irrigation | Water & Irrigation | 2017-06-30 | 2017-07-01 | 2018-06-01 |  | 6000000 | 6000000 | 6000000 | CGK | N/A | 6000000 | 0 | 0 | 0% |  | 6000000 | 6000000 | Completed | [6 empty] | No |  | Environmental | No | Propose budget for screening | No | Propose budget for screening | Yes | Fesibility studies and design
233 | Kimana community water tank | Construction of a water tank | Increase access to safe and affordable water | Water Storage tank constructed |  | Kimana community water tank | Kajiado South | KIMANA |  | Water, Irrigation, Environment and Natural Resources | Water & Irrigation | Water & Irrigation | 2017-06-30 | 2017-07-01 | 2018-06-01 |  | 3000000 | 3000000 | 3000000 | CGK | N/A | 3000000 | 0 | 0 | 0% |  | 3000000 | 3000000 | Completed | [6 empty] | No |  | Environmental | No | Propose budget for screening | No | Propose budget for screening | Yes | Fesibility studies and design
234 | Mansonry tank | Construction, piping, plumbing (3km) | Increase access to safe and affordable water | Pipeline constructed |  | Mansonry tank | Kajiado East | OLOOSIRKON/ SHOLINKE |  | Water, Irrigation, Environment and Natural Resources | Water & Irrigation | Water & Irrigation | 2017-06-30 | 2017-07-01 | 2018-06-01 |  | 6000000 | 6000000 | 6000000 | CGK | N/A | 6000000 | 0 | 0 | 0% |  | 6000000 | 6000000 | Completed | [6 empty] | No |  | Environmental | No | Propose budget for screening | No | Propose budget for screening | Yes | Fesibility studies and design
235 | Kunchu Borehole | Drlling and Equiping | Increase access to safe and affordable water | Borehole drilled and equipped |  | Kunchu Borehole | Kajiado East | KENYAWA POKA |  | Water, Irrigation, Environment and Natural Resources | Water & Irrigation | Water & Irrigation | 2017-06-30 | 2017-07-01 | 2018-06-01 |  | 7000000 | 7000000 | 7000000 | CGK | N/A | 7000000 | 0 | 0 | 0% |  | 7000000 | 7000000 | Completed | [6 empty] | No |  | Environmental | No | Propose budget for screening | No | Propose budget for screening | Yes | Fesibility studies and design
236 | Napukudet Community Borehole | Drilling and Equiping | Increase access to safe and affordable water | Borehole drilled and equipped |  | Napukudet Community Borehole | Kajiado East | IMARORO |  | Water, Irrigation, Environment and Natural Resources | Water & Irrigation | Water & Irrigation | 2017-06-30 | 2017-07-01 | 2018-06-01 |  | 4000000 | 4000000 | 4000000 | CGK | N/A | 4000000 | 0 | 0 | 0% |  | 4000000 | 4000000 | Completed | [6 empty] | No |  | Environmental | No | Propose budget for screening | No | Propose budget for screening | Yes | Fesibility studies and design
237 | Enkonerei Community Water Project | Drilling and Equiping | Increase access to safe and affordable water | Borehole drilled and equipped |  | Enkonerei Community Water Project | Kajiado East | IMARORO |  | Water, Irrigation, Environment and Natural Resources | Water & Irrigation | Water & Irrigation | 2017-06-30 | 2017-07-01 | 2018-06-01 |  | 5000000 | 5000000 | 5000000 | CGK | N/A | 5000000 | 0 | 0 | 0% |  | 5000000 | 5000000 | Completed | [6 empty] | No |  | Environmental | No | Propose budget for screening | No | Propose budget for screening | Yes | Fesibility studies and design
238 | Inchil-Inkojonga Water Project | Piping | Increase access to safe and affordable water | Pipeline constructed |  | Inchil-Inkojonga Water Project | Kajiado East | IMARORO |  | Water, Irrigation, Environment and Natural Resources | Water & Irrigation | Water & Irrigation | 2017-06-30 | 2017-07-01 | 2018-06-01 |  | 2000000 | 2000000 | 2000000 | CGK | N/A | 2000000 | 0 | 0 | 0% |  | 2000000 | 2000000 | Completed | [6 empty] | No |  | Environmental | No | Propose budget for screening | No | Propose budget for screening | Yes | Fesibility studies and design
239 | Esilalei Borehole | Drillling | Increase access to safe and affordable water | Borehole drilled |  | Esilalei Borehole | Kajiado East | IMARORO |  | Water, Irrigation, Environment and Natural Resources | Water & Irrigation | Water & Irrigation | 2017-06-30 | 2017-07-01 | 2018-06-01 |  | 4000000 | 4000000 | 4000000 | CGK | N/A | 4000000 | 0 | 0 | 0% |  | 4000000 | 4000000 | Completed | [6 empty] | No |  | Environmental | No | Propose budget for screening | No | Propose budget for screening | Yes | Fesibility studies and design
240 | Oltepesi Borehole | Piping to Inkuseron tank & tank renovation | Increase access to safe and affordable water | Pipeline constructed |  | Oltepesi Borehole | Kajiado East | IMARORO |  | Water, Irrigation, Environment and Natural Resources | Water & Irrigation | Water & Irrigation | 2017-06-30 | 2017-07-01 | 2018-06-01 |  | 2000000 | 2000000 | 2000000 | CGK | N/A | 2000000 | 0 | 0 | 0% |  | 2000000 | 2000000 | Completed | [6 empty] | No |  | Environmental | No | Propose budget for screening | No | Propose budget for screening | Yes | Fesibility studies and design
241 | Engeju-Oolowarak Borehole | Drilling and Equiping & installing an elevated tank | Increase access to safe and affordable water | Borehole drilled and equipped |  | Engeju-Oolowarak Borehole | Kajiado East | KITENGELA |  | Water, Irrigation, Environment and Natural Resources | Water & Irrigation | Water & Irrigation | 2017-06-30 | 2017-07-01 | 2018-06-01 |  | 7000000 | 7000000 | 7000000 | CGK | N/A | 7000000 | 0 | 0 | 0% |  | 7000000 | 7000000 | Completed | [6 empty] | No |  | Environmental | No | Propose budget for screening | No | Propose budget for screening | Yes | Fesibility studies and design
242 | Inkukuon Water Piping | Piping | Increase access to safe and affordable water | Pipeline constructed |  | Inkukuon Water Piping | Kajiado East | KITENGELA |  | Water, Irrigation, Environment and Natural Resources | Water & Irrigation | Water & Irrigation | 2017-06-30 | 2017-07-01 | 2018-06-01 |  | 2000000 | 2000000 | 2000000 | CGK | N/A | 2000000 | 0 | 0 | 0% |  | 2000000 | 2000000 | Completed | [6 empty] | No |  | Environmental | No | Propose budget for screening | No | Propose budget for screening | Yes | Fesibility studies and design
243 | Oloshaiki Borehole | Rehabilitation | Increase access to safe and affordable water | Borehole rehabilitated |  | Oloshaiki Borehole | Kajiado East | KAPUTIEI NORTH |  | Water, Irrigation, Environment and Natural Resources | Water & Irrigation | Water & Irrigation | 2017-06-30 | 2017-07-01 | 2018-06-01 |  | 2000000 | 2000000 | 2000000 | CGK | N/A | 2000000 | 0 | 0 | 0% |  | 2000000 | 2000000 | Stalled | 0% | 0% | Borehole collapsed | 2018 | 6 | 2000000 | No | Defer | Financial | No | Propose budget for screening | No | Propose budget for screening | Yes | Fesibility studies and design
244 | Namunyak Borehole | Drilling and Equiping | Increase access to safe and affordable water | Borehole drilled and equipped |  | Namunyak Borehole | Kajiado East | KAPUTIEI NORTH |  | Water, Irrigation, Environment and Natural Resources | Water & Irrigation | Water & Irrigation | 2017-06-30 | 2017-07-01 | 2018-06-01 |  | 7000000 | 7000000 | 7000000 | CGK | N/A | 7000000 | 0 | 0 | 0% |  | 7000000 | 7000000 | Completed | [6 empty] | No |  | Environmental | No | Propose budget for screening | No | Propose budget for screening | Yes | Fesibility studies and design
245 | Oloibor Soit borehole | Repair of Gen set | Increase access to safe and affordable water | Borehole rehabilitated |  | Oloibor Soit borehole | Kajiado Central | MATAPATO NORTH |  | Water, Irrigation, Environment and Natural Resources | Water & Irrigation | Water & Irrigation | 2017-06-30 | 2017-07-01 | 2018-06-01 |  | 500000 | 500000 | 500000 | CGK | N/A | 500000 | 0 | 0 | 0% |  | 500000 | 500000 | Completed | [6 empty] | No |  | Environmental | No | Propose budget for screening | No | Propose budget for screening | Yes | Fesibility studies and design
246 | Olchoro Oibor borehole | Drilling & Equipping | Increase access to safe and affordable water | Borehole drilled & equipped |  | Olchoro Oibor borehole | Kajiado Central | MATAPATO NORTH |  | Water, Irrigation, Environment and Natural Resources | Water & Irrigation | Water & Irrigation | 2017-06-30 | 2017-07-01 | 2018-06-01 |  | 7000000 | 7000000 | 7000000 | CGK | N/A | 7000000 | 0 | 0 | 0% |  | 7000000 | 7000000 | Completed | [6 empty] | No |  | Environmental | No | Propose budget for screening | No | Propose budget for screening | Yes | Fesibility studies and design
247 | Elerai borehole | Drilling and equipping | Increase access to safe and affordable water | Borehole drilled & equipped |  | Elerai borehole | Kajiado Central | DALALEKUTUK |  | Water, Irrigation, Environment and Natural Resources | Water & Irrigation | Water & Irrigation | 2017-06-30 | 2017-07-01 | 2018-06-01 |  | 7000000 | 7000000 | 7000000 | CGK | N/A | 7000000 | 0 | 0 | 0% |  | 7000000 | 7000000 | Completed | [6 empty] | No |  | Environmental | No | Propose budget for screening | No | Propose budget for screening | Yes | Fesibility studies and design
248 | Olgos shallow well | Upgrading shallow well to borehole and piping water to Nkoile primary school | Increase access to safe and affordable water | Shallow well drilled and equipped |  | Olgos shallow well | Kajiado Central | PURKO |  | Water, Irrigation, Environment and Natural Resources | Water & Irrigation | Water & Irrigation | 2017-06-30 | 2017-07-01 | 2018-06-01 |  | 7000000 | 7000000 | 7000000 | CGK | N/A | 7000000 | 0 | 0 | 0% |  | 7000000 | 7000000 | Completed | [6 empty] | No |  | Environmental | No | Propose budget for screening | No | Propose budget for screening | Yes | Fesibility studies and design
249 | Oloorela/Ensiati borehole | Borehole equiping | Increase access to safe and affordable water | Borehole equipped |  | Oloorela/Ensiati borehole | Kajiado Central | PURKO |  | Water, Irrigation, Environment and Natural Resources | Water & Irrigation | Water & Irrigation | 2017-06-30 | 2017-07-01 | 2018-06-01 |  | 2000000 | 2000000 | 2000000 | CGK | N/A | 2000000 | 0 | 0 | 0% |  | 2000000 | 2000000 | Completed | [6 empty] | No |  | Environmental | No | Propose budget for screening | No | Propose budget for screening | Yes | Fesibility studies and design
250 | Tikoishi borehole | Drilling and equipping | Increase access to safe and affordable water | Borehole drilled & equipped |  | Tikoishi borehole | Kajiado Central | ILDAMAT |  | Water, Irrigation, Environment and Natural Resources | Water & Irrigation | Water & Irrigation | 2017-06-30 | 2017-07-01 | 2018-06-01 |  | 7000000 | 7000000 | 7000000 | CGK | N/A | 7000000 | 0 | 0 | 0% |  | 7000000 | 7000000 | Completed | [6 empty] | No |  | Environmental | No | Propose budget for screening | No | Propose budget for screening | Yes | Fesibility studies and design
251 | Olasit water pan | Desilting | Increase access to safe and affordable water | Pan desilted |  | Olasit water pan | Kajiado Central | MATAPATO SOUTH |  | Water, Irrigation, Environment and Natural Resources | Water & Irrigation | Water & Irrigation | 2017-06-30 | 2017-07-01 | 2018-06-01 |  | 2000000 | 2000000 | 2000000 | CGK | N/A | 2000000 | 0 | 0 | 0% |  | 2000000 | 2000000 | Completed | [6 empty] | No |  | Environmental | No | Propose budget for screening | No | Propose budget for screening | Yes | Fesibility studies and design
252 | Empukani water pan | Desilting | Increase access to safe and affordable water | Pan desilted |  | Empukani water pan | Kajiado Central | MATAPATO SOUTH |  | Water, Irrigation, Environment and Natural Resources | Water & Irrigation | Water & Irrigation | 2017-06-30 | 2017-07-01 | 2018-06-01 |  | 1500000 | 1500000 | 1500000 | CGK | N/A | 1500000 | 0 | 0 | 0% |  | 1500000 | 1500000 | Completed | [6 empty] | No |  | Environmental | No | Propose budget for screening | No | Propose budget for screening | Yes | Fesibility studies and design
253 | Muntarakwa borehole | Drilling and equipping | Increase access to safe and affordable water | Borehole drilled & equipped |  | Muntarakwa borehole | Kajiado Central | MATAPATO SOUTH |  | Water, Irrigation, Environment and Natural Resources | Water & Irrigation | Water & Irrigation | 2017-06-30 | 2017-07-01 | 2018-06-01 |  | 7000000 | 7000000 | 7000000 | CGK | N/A | 7000000 | 0 | 0 | 0% |  | 7000000 | 7000000 | Completed | [6 empty] | No |  | Environmental | No | Propose budget for screening | No | Propose budget for screening | Yes | Fesibility studies and design
254 | Oloorela Water Pan | Desilting | Increase access to safe and affordable water | Pan desilted |  | Oloorela Water Pan | Kajiado Central | MATAPATO SOUTH |  | Water, Irrigation, Environment and Natural Resources | Water & Irrigation | Water & Irrigation | 2017-06-30 | 2017-07-01 | 2018-06-01 |  | 1500000 | 1500000 | 1500000 | CGK | N/A | 1500000 | 0 | 0 | 0% |  | 1500000 | 1500000 | Completed | [6 empty] | No |  | Environmental | No | Propose budget for screening | No | Propose budget for screening | Yes | Fesibility studies and design
255 | Water Reticulation in Isinet | Water reticulation | Increase access to safe and affordable water | Water reticulation done |  | Water Reticulation in Isinet |  |  |  | Water, Irrigation, Environment and Natural Resources | Water & Irrigation | Water & Irrigation | 2017-06-30 | 2017-07-01 | 2018-06-01 |  | 10000000 | 10000000 | 10000000 | CGK | N/A | 10000000 | 0 | 0 | 0% |  | 10000000 | 10000000 | Completed | [6 empty] | No |  | Environmental | No | Propose budget for screening | No | Propose budget for screening | Yes | Fesibility studies and design
256 | Impiro canal | Repair of canal | Increase area under irrigation | Canal repaired |  | Impiro canal |  |  |  | Water, Irrigation, Environment and Natural Resources | Water & Irrigation | Water & Irrigation | 2017-06-30 | 2017-07-01 | 2018-06-01 |  | 0 | 0 | 0 | CGK | N/A | 0 | 0 | 0 | #DIV/0! |  | 0 | 0 | Completed | [6 empty] | No |  | Environmental | No | Propose budget for screening | No | Propose budget for screening | Yes | Fesibility studies and design
257 | Uswa-Emorkea Water Project | Water Piping from Uswa Borehole to Emorkea Pri sch | Increase access to safe and affordable water | Pipeline constructed |  | Uswa-Emorkea Water Project | Kajiado West | Ildookilani |  | Water, Irrigation, Environment and Natural Resources | Water & Irrigation | Water & Irrigation | 2017-06-30 | 2017-07-01 | 2018-06-01 |  | 10000000 | 10000000 | 10000000 | CGK | N/A | 10000000 | 0 | 0 | 0% |  | 10000000 | 10000000 | Completed | [6 empty] | No |  | Environmental | No | Propose budget for screening | No | Propose budget for screening | Yes | Fesibility studies and design
258 | Kiserian-Oloosurutia -Nkoroi water project | Drilling and equipping of a borehole | Increase access to safe and affordable water | Borehole drilled and equipped |  | Kiserian-Oloosurutia -Nkoroi water project | Kajiado North | Olkeri |  | Water, Irrigation, Environment and Natural Resources | Water & Irrigation | Water & Irrigation | 2017-06-30 | 2017-07-01 | 2018-06-01 |  | 10000000 | 10000000 | 10000000 | CGK | N/A | 10000000 | 0 | 0 | 0% |  | 10000000 | 10000000 | Completed | [6 empty] | No |  | Environmental | No | Propose budget for screening | No | Propose budget for screening | Yes | Fesibility studies and design
259 | Merisho Oloika Water Project | Installation of solar panels; Water treatment kits; Purchase of three (3) inch pipes; and Installation of 50,000Litres storage tank. | Increase access to safe and affordable water | Borehole solarized and pipeline constructed |  | Merisho Oloika Water Project |  | OLKERI |  | Water, Irrigation, Environment and Natural Resources | Water & Irrigation | Water & Irrigation | 2018-06-30 | 2018-07-01 | 2019-06-01 |  | 8000000 | 8000000 | 8000000 | CGK | N/A | 8000000 | 0 | 0 | 0% |  | 8000000 | 8000000 | Completed | [6 empty] | No |  | Environmental | No | Propose budget for screening | No | Propose budget for screening | Yes | Fesibility studies and design
260 | Big dust bin at ngong town | Purchase of dust bins (big) | Improve management and conservation of the environment | Dust bins purchased |  | Big dust bin at ngong town |  | NGONG |  | Water, Irrigation, Environment and Natural Resources | Environment, Natural Resources and Climate Change | Environment, Natural Resources and Climate Change | 2018-06-30 | 2018-07-01 | 2019-06-01 |  | 1500000 | 1500000 | 1500000 | CGK | N/A | 1500000 | 0 | 0 | 0% |  | 1500000 | 1500000 | Completed | [6 empty] | No |  | Environmental | No | Propose budget for screening | No | Propose budget for screening | Yes | Fesibility studies and design
261 | Small dust bin at ngong town | Purchase of dust bins (small) | Improve management and conservation of the environment | Dust bins purchased |  | Small dust bin at ngong town |  | NGONG |  | Water, Irrigation, Environment and Natural Resources | Environment, Natural Resources and Climate Change | Environment, Natural Resources and Climate Change | 2018-06-30 | 2018-07-01 | 2019-06-01 |  | 500000 | 500000 | 500000 | CGK | N/A | 500000 | 0 | 0 | 0% |  | 500000 | 500000 | Completed | [6 empty] | No |  | Environmental | No | Propose budget for screening | No | Propose budget for screening | Yes | Fesibility studies and design
262 | Olkiramatin - Oldorko water pipeline | Construction of water pipeline | Increase access to safe and affordable water | Pipeline constructed |  | Olkiramatin - Oldorko water pipeline |  | MAGADI |  | Water, Irrigation, Environment and Natural Resources | Water & Irrigation | Water & Irrigation | 2018-06-30 | 2018-07-01 | 2019-06-01 |  | 4000000 | 4000000 | 4000000 | CGK | N/A | 4000000 | 0 | 0 | 0% |  | 4000000 | 4000000 | Completed | [6 empty] | No |  | Environmental | No | Propose budget for screening | No | Propose budget for screening | Yes | Fesibility studies and design
263 | Pakase water pipeline | Construction of water pipeline | Increase access to safe and affordable water | Pipeline constructed |  | Pakase water pipeline |  | MAGADI |  | Water, Irrigation, Environment and Natural Resources | Water & Irrigation | Water & Irrigation | 2018-06-30 | 2018-07-01 | 2019-06-01 |  | 4000000 | 4000000 | 4000000 | CGK | N/A | 4000000 | 0 | 0 | 0% |  | 4000000 | 4000000 | Completed | [6 empty] | No |  | Environmental | No | Propose budget for screening | No | Propose budget for screening | Yes | Fesibility studies and design
264 | Oldonyo onyokie sec school underground water tank | Construction of underground water tank | Increase access to safe and affordable water | Water Storage tank constructed |  | Oldonyo onyokie sec school underground water tank |  | MAGADI |  | Water, Irrigation, Environment and Natural Resources | Water & Irrigation | Water & Irrigation | 2018-06-30 | 2018-07-01 | 2019-06-01 |  | 2000000 | 2000000 | 2000000 | CGK | N/A | 2000000 | 0 | 0 | 0% |  | 2000000 | 2000000 | Completed | [6 empty] | No |  | Environmental | No | Propose budget for screening | No | Propose budget for screening | Yes | Fesibility studies and design
265 | Oloolairukokroik catchment | Rock catchment | Increase access to safe and affordable water | Rock catchment constructed |  | Oloolairukokroik catchment |  | MAGADI |  | Water, Irrigation, Environment and Natural Resources | Water & Irrigation | Water & Irrigation | 2018-06-30 | 2018-07-01 | 2019-06-01 |  | 2000000 | 2000000 | 2000000 | CGK | N/A | 2000000 | 0 | 0 | 0% |  | 2000000 | 2000000 | Completed | [6 empty] | No |  | Environmental | No | Propose budget for screening | No | Propose budget for screening | Yes | Fesibility studies and design
266 | Inyonyori water piping | Water piping | Increase access to safe and affordable water | Pipeline constructed |  | Inyonyori water piping |  | KEEKONYOKIE |  | Water, Irrigation, Environment and Natural Resources | Water & Irrigation | Water & Irrigation | 2018-06-30 | 2018-07-01 | 2019-06-01 |  | 2000000 | 2000000 | 2000000 | CGK | N/A | 2000000 | 0 | 0 | 0% |  | 2000000 | 2000000 | Completed | [6 empty] | No |  | Environmental | No | Propose budget for screening | No | Propose budget for screening | Yes | Fesibility studies and design
267 | Singiraine borehole | Drlling and equiping of a borehole at Singiraine | Increase access to safe and affordable water | Borehole drilled and equipped |  | Singiraine borehole |  | ILOODOKILANI |  | Water, Irrigation, Environment and Natural Resources | Water & Irrigation | Water & Irrigation | 2018-06-30 | 2018-07-01 | 2019-06-01 |  | 7000000 | 7000000 | 7000000 | CGK | N/A | 7000000 | 0 | 0 | 0% |  | 7000000 | 7000000 | Completed | [6 empty] | No |  | Environmental | No | Propose budget for screening | No | Propose budget for screening | Yes | Fesibility studies and design
268 | Lebitira Borehole | Drilling and Equipping of Lebitira borehole | Increase access to safe and affordable water | Borehole drilled and equipped |  | Lebitira Borehole |  | MOSIRO |  | Water, Irrigation, Environment and Natural Resources | Water & Irrigation | Water & Irrigation | 2018-06-30 | 2018-07-01 | 2019-06-01 |  | 7000000 | 7000000 | 7000000 | CGK | N/A | 7000000 | 0 | 0 | 0% |  | 7000000 | 7000000 | Completed | [6 empty] | No |  | Environmental | No | Propose budget for screening | No | Propose budget for screening | Yes | Fesibility studies and design
269 | Olasiti bore hole | Drilling and equipping | Increase access to safe and affordable water | Borehole drilled and equipped |  | Olasiti bore hole |  | EWUASO KEDONG |  | Water, Irrigation, Environment and Natural Resources | Water & Irrigation | Water & Irrigation | 2018-06-30 | 2018-07-01 | 2019-06-01 |  | 7000000 | 7000000 | 7000000 | CGK | N/A | 7000000 | 0 | 0 | 0% |  | 7000000 | 7000000 | Completed | [6 empty] | No |  | Environmental | No | Propose budget for screening | No | Propose budget for screening | Yes | Fesibility studies and design
270 | Enkeresuna Olmootiok water project | Pumping of water from Enkereruna to Ilmootiok primary/dispensary | Increase access to safe and affordable water | Pipeline constructed |  | Enkeresuna Olmootiok water project |  | MATAPATO NORTH |  | Water, Irrigation, Environment and Natural Resources | Water & Irrigation | Water & Irrigation | 2018-06-30 | 2018-07-01 | 2019-06-01 |  | 10000000 | 10000000 | 10000000 | CGK | N/A | 10000000 | 0 | 0 | 0% |  | 10000000 | 10000000 | Completed | [6 empty] | No |  | Environmental | No | Propose budget for screening | No | Propose budget for screening | Yes | Fesibility studies and design
271 | Bissil Water Project | Construction of 2 No. 50,000 litres tanks and pumping water from the borehole | Increase access to safe and affordable water | Water Storage tank constructed |  | Bissil Water Project |  | MATAPATO NORTH |  | Water, Irrigation, Environment and Natural Resources | Water & Irrigation | Water & Irrigation | 2018-06-30 | 2018-07-01 | 2019-06-01 |  | 5000000 | 5000000 | 5000000 | CGK | N/A | 5000000 | 0 | 0 | 0% |  | 5000000 | 5000000 | Completed | [6 empty] | No |  | Environmental | No | Propose budget for screening | No | Propose budget for screening | Yes | Fesibility studies and design
272 | Orgos Borehole | Equipping machine and piping | Increase access to safe and affordable water | Borehole equipped |  | Orgos Borehole |  | DALALEKUTUK |  | Water, Irrigation, Environment and Natural Resources | Water & Irrigation | Water & Irrigation | 2018-06-30 | 2018-07-01 | 2019-06-01 |  | 3000000 | 3000000 | 3000000 | CGK | N/A | 3000000 | 0 | 0 | 0% |  | 3000000 | 3000000 | Completed | [6 empty] | No |  | Environmental | No | Propose budget for screening | No | Propose budget for screening | Yes | Fesibility studies and design
273 | Impiro Borehole | Equiping and Repair of machine | Increase access to safe and affordable water | Borehole equipped |  | Impiro Borehole |  | DALALEKUTUK |  | Water, Irrigation, Environment and Natural Resources | Water & Irrigation | Water & Irrigation | 2018-06-30 | 2018-07-01 | 2019-06-01 |  | 2000000 | 2000000 | 2000000 | CGK | N/A | 2000000 | 0 | 0 | 0% |  | 2000000 | 2000000 | Completed | [6 empty] | No |  | Environmental | No | Propose budget for screening | No | Propose budget for screening | Yes | Fesibility studies and design
274 | Olmoti Borehole | Purchase of water machine (genset ) | Increase access to safe and affordable water | Genset installed |  | Olmoti Borehole |  | ENTONET/LENKISM |  | Water, Irrigation, Environment and Natural Resources | Water & Irrigation | Water & Irrigation | 2018-06-30 | 2018-07-01 | 2019-06-01 |  | 2000000 | 2000000 | 2000000 | CGK | N/A | 2000000 | 0 | 0 | 0% |  | 2000000 | 2000000 | Completed | [6 empty] | No |  | Environmental | No | Propose budget for screening | No | Propose budget for screening | Yes | Fesibility studies and design
275 | Olchorro springs- perimeter wall and Tank. | Construction of perimeter wall and Tank at Olchorro springs | Increase access to safe and affordable water | Perimeter wall and Storage tank constructed |  | Olchorro springs- perimeter wall and Tank. |  | ENTONET/LENKISM |  | Water, Irrigation, Environment and Natural Resources | Water & Irrigation | Water & Irrigation | 2018-06-30 | 2018-07-01 | 2019-06-01 |  | 5000000 | 5000000 | 5000000 | CGK | N/A | 5000000 | 0 | 0 | 0% |  | 5000000 | 5000000 | Completed | [6 empty] | No |  | Environmental | No | Propose budget for screening | No | Propose budget for screening | Yes | Fesibility studies and design
276 | Isinet - Kalesirua canal. | Rehabilitation 9km canal | Increase area under irrigation | Canal rehabilitated |  | Isinet - Kalesirua canal. |  | IMBIRIKANI |  | Water, Irrigation, Environment and Natural Resources | Water & Irrigation | Water & Irrigation | 2018-06-30 | 2018-07-01 | 2019-06-01 |  | 8000000 | 8000000 | 8000000 | CGK | N/A | 8000000 | 0 | 0 | 0% |  | 8000000 | 8000000 | Completed | [6 empty] | No |  | Environmental | No | Propose budget for screening | No | Propose budget for screening | Yes | Fesibility studies and design
277 | Construction of water tank and piping at Leing’ati | Construction of water tank and piping | Increase access to safe and affordable water | Water Storage tank constructed |  | Construction of water tank and piping at Leing’ati |  | IMBIRIKANI |  | Water, Irrigation, Environment and Natural Resources | Water & Irrigation | Water & Irrigation | 2018-06-30 | 2018-07-01 | 2019-06-01 |  | 3000000 | 3000000 | 3000000 | CGK | N/A | 3000000 | 0 | 0 | 0% |  | 3000000 | 3000000 | Completed | [6 empty] | No |  | Environmental | No | Propose budget for screening | No | Propose budget for screening | Yes | Fesibility studies and design
278 | Kiserian (Lokiu) water tank | Construction of water tank | Increase access to safe and affordable water | Water Storage tank constructed |  | Kiserian (Lokiu) water tank |  | IMBIRIKANI |  | Water, Irrigation, Environment and Natural Resources | Water & Irrigation | Water & Irrigation | 2018-06-30 | 2018-07-01 | 2019-06-01 |  | 3000000 | 3000000 | 3000000 | CGK | N/A | 3000000 | 0 | 0 | 0% |  | 3000000 | 3000000 | Completed | [6 empty] | No |  | Environmental | No | Propose budget for screening | No | Propose budget for screening | Yes | Fesibility studies and design
279 | Sompet borehole | Drilling and equipping | Increase access to safe and affordable water | Borehole drilled and equipped |  | Sompet borehole |  | KIMANA |  | Water, Irrigation, Environment and Natural Resources | Water & Irrigation | Water & Irrigation | 2018-06-30 | 2018-07-01 | 2019-06-01 |  | 7000000 | 7000000 | 7000000 | CGK | N/A | 7000000 | 0 | 0 | 0% |  | 7000000 | 7000000 | Completed | [6 empty] | No |  | Environmental | No | Propose budget for screening | No | Propose budget for screening | Yes | Fesibility studies and design
280 | Elerai Kimana borehole | Drilling and equipping | Increase access to safe and affordable water | Borehole drilled and equipped |  | Elerai Kimana borehole |  | KIMANA |  | Water, Irrigation, Environment and Natural Resources | Water & Irrigation | Water & Irrigation | 2018-06-30 | 2018-07-01 | 2019-06-01 |  | 7000000 | 7000000 | 7000000 | CGK | N/A | 7000000 | 0 | 0 | 0% |  | 7000000 | 7000000 | Completed | [6 empty] | No |  | Environmental | No | Propose budget for screening | No | Propose budget for screening | Yes | Fesibility studies and design
281 | Ngama Pri school | Drilling and Equipping of Borehole | Increase access to safe and affordable water | Borehole drilled and equipped |  | Ngama Pri school |  | KUKU |  | Water, Irrigation, Environment and Natural Resources | Water & Irrigation | Water & Irrigation | 2018-06-30 | 2018-07-01 | 2019-06-01 |  | 6000000 | 6000000 | 6000000 | CGK | N/A | 6000000 | 0 | 0 | 0% |  | 6000000 | 6000000 | Stalled | 40% | 40% | Inadequate finances | 2019 | 6 | 6000000 | No | Defer | Financial | No | Propose budget for screening | No | Propose budget for screening | Yes | Fesibility studies and design
282 | Oloishiro Canal | Canal intake construction | Increase area under irrigation | Canal constructed |  | Oloishiro Canal |  | ROMBO |  | Water, Irrigation, Environment and Natural Resources | Water & Irrigation | Water & Irrigation | 2018-06-30 | 2018-07-01 | 2019-06-01 |  | 4000000 | 4000000 | 4000000 | CGK | N/A | 4000000 | 0 | 0 | 0% |  | 4000000 | 4000000 | Completed | [6 empty] | No |  | Environmental | No | Propose budget for screening | No | Propose budget for screening | Yes | Fesibility studies and design
283 | Entarara Health Centre Borehole | Construction of 100m3 tank, pump and pipping (source to the tank-0.8km and tank to the community 8km) | Increase access to safe and affordable water | Storage tank constructed |  | Entarara Health Centre Borehole |  | ROMBO |  | Water, Irrigation, Environment and Natural Resources | Water & Irrigation | Water & Irrigation | 2018-06-30 | 2018-07-01 | 2019-06-01 |  | 4000000 | 4000000 | 4000000 | CGK | N/A | 4000000 | 0 | 0 | 0% |  | 4000000 | 4000000 | Completed | [6 empty] | No |  | Environmental | No | Propose budget for screening | No | Propose budget for screening | Yes | Fesibility studies and design
284 | Canaan canal intake | Canal intake construction | Increase area under irrigation | Canal constructed |  | Canaan canal intake |  | ROMBO |  | Water, Irrigation, Environment and Natural Resources | Water & Irrigation | Water & Irrigation | 2018-06-30 | 2018-07-01 | 2019-06-01 |  | 4000000 | 4000000 | 4000000 | CGK | N/A | 4000000 | 0 | 0 | 0% |  | 4000000 | 4000000 | Completed | [6 empty] | No |  | Environmental | No | Propose budget for screening | No | Propose budget for screening | Yes | Fesibility studies and design
285 | Olkatetemai borehole | Equiping and Repair | Increase access to safe and affordable water | Borehole equipped |  | Olkatetemai borehole |  | KENYAWA POKA |  | Water, Irrigation, Environment and Natural Resources | Water & Irrigation | Water & Irrigation | 2018-06-30 | 2018-07-01 | 2019-06-01 |  | 3000000 | 3000000 | 3000000 | CGK | N/A | 3000000 | 0 | 0 | 0% |  | 3000000 | 3000000 | Completed | [6 empty] | No |  | Environmental | No | Propose budget for screening | No | Propose budget for screening | Yes | Fesibility studies and design
286 | Oltinka borehole | Equiping and Repair | Increase access to safe and affordable water | Borehole equipped |  | Oltinka borehole |  | KENYAWA POKA |  | Water, Irrigation, Environment and Natural Resources | Water & Irrigation | Water & Irrigation | 2018-06-30 | 2018-07-01 | 2019-06-01 |  | 3000000 | 3000000 | 3000000 | CGK | N/A | 3000000 | 0 | 0 | 0% |  | 3000000 | 3000000 | Completed | [6 empty] | No |  | Environmental | No | Propose budget for screening | No | Propose budget for screening | Yes | Fesibility studies and design
287 | Oloikara borehole | Equiping and Repair | Increase access to safe and affordable water | Borehole equipped |  | Oloikara borehole |  | KENYAWA POKA |  | Water, Irrigation, Environment and Natural Resources | Water & Irrigation | Water & Irrigation | 2018-06-30 | 2018-07-01 | 2019-06-01 |  | 2000000 | 2000000 | 2000000 | CGK | N/A | 2000000 | 0 | 0 | 0% |  | 2000000 | 2000000 | Completed | [6 empty] | No |  | Environmental | No | Propose budget for screening | No | Propose budget for screening | Yes | Fesibility studies and design
288 | Naningoi borehole | Equiping and Repair | Increase access to safe and affordable water | Borehole equipped |  | Naningoi borehole |  | KENYAWA POKA |  | Water, Irrigation, Environment and Natural Resources | Water & Irrigation | Water & Irrigation | 2018-06-30 | 2018-07-01 | 2019-06-01 |  | 2000000 | 2000000 | 2000000 | CGK | N/A | 2000000 | 0 | 0 | 0% |  | 2000000 | 2000000 | Completed | [6 empty] | No |  | Environmental | No | Propose budget for screening | No | Propose budget for screening | Yes | Fesibility studies and design
289 | Ilderekes borehole | Drilling and equiping | Increase access to safe and affordable water | Borehole drillled and equipped |  | Ilderekes borehole |  | KENYAWA POKA |  | Water, Irrigation, Environment and Natural Resources | Water & Irrigation | Water & Irrigation | 2018-06-30 | 2018-07-01 | 2019-06-01 |  | 7000000 | 7000000 | 7000000 | CGK | N/A | 7000000 | 0 | 0 | 0% |  | 7000000 | 7000000 | Completed | [6 empty] | No |  | Environmental | No | Propose budget for screening | No | Propose budget for screening | Yes | Fesibility studies and design
290 | A.I.C Ilmungush pri | Piping | Increase access to safe and affordable water | Pipeline constructed |  | A.I.C Ilmungush pri |  | IMARORO |  | Water, Irrigation, Environment and Natural Resources | Water & Irrigation | Water & Irrigation | 2018-06-30 | 2018-07-01 | 2019-06-01 |  | 3000000 | 3000000 | 3000000 | CGK | N/A | 3000000 | 0 | 0 | 0% |  | 3000000 | 3000000 | Completed | [6 empty] | No |  | Environmental | No | Propose budget for screening | No | Propose budget for screening | Yes | Fesibility studies and design
291 | Enkigiri borehole | Equiping of borehole | Increase access to safe and affordable water | Borehole equipped |  | Enkigiri borehole |  | KAPUTIEI NORTH |  | Water, Irrigation, Environment and Natural Resources | Water & Irrigation | Water & Irrigation | 2018-06-30 | 2018-07-01 | 2019-06-01 |  | 3000000 | 3000000 | 3000000 | CGK | N/A | 3000000 | 0 | 0 | 0% |  | 3000000 | 3000000 | Completed | [6 empty] | No |  | Environmental | No | Propose budget for screening | No | Propose budget for screening | Yes | Fesibility studies and design
292 | Impiron borehole | Equipping with Pipes, storage tank and a pump | Increase access to safe and affordable water | Borehole equipped |  | Impiron borehole |  | Dalalekutuk |  | Water, Irrigation, Environment and Natural Resources | Water & Irrigation | Water & Irrigation | 2019-06-30 | 2019-07-01 | 2020-06-01 |  | 4000000 | 4000000 | 4000000 | CGK | N/A | 4000000 | 0 | 0 | 0% |  | 4000000 | 4000000 | Completed | [6 empty] | No |  | Environmental | No | Propose budget for screening | No | Propose budget for screening | Yes | Fesibility studies and design
293 | Inkuseron borehole | Equipping with Pipes, storage tank and a pump | Increase access to safe and affordable water | Borehole equipped |  | Inkuseron borehole |  | Dalalekutuk |  | Water, Irrigation, Environment and Natural Resources | Water & Irrigation | Water & Irrigation | 2019-06-30 | 2019-07-01 | 2020-06-01 |  | 3000000 | 3000000 | 3000000 | CGK | N/A | 3000000 | 0 | 0 | 0% |  | 3000000 | 3000000 | Completed | [6 empty] | No |  | Environmental | No | Propose budget for screening | No | Propose budget for screening | Yes | Fesibility studies and design
294 | Elerai borehole | Construction of a 10 liters storage tank | Increase access to safe and affordable water | Storage tank constructed |  | Elerai borehole |  | Dalalekutuk |  | Water, Irrigation, Environment and Natural Resources | Water & Irrigation | Water & Irrigation | 2019-06-30 | 2019-07-01 | 2020-06-01 |  | 700000 | 700000 | 700000 | CGK | N/A | 700000 | 0 | 0 | 0% |  | 700000 | 700000 | Completed | [6 empty] | No |  | Environmental | No | Propose budget for screening | No | Propose budget for screening | Yes | Fesibility studies and design
295 | Nareto borehole | Construction of two storage tanks | Increase access to safe and affordable water | Storage tank constructed |  | Nareto borehole |  | Dalalekutuk |  | Water, Irrigation, Environment and Natural Resources | Water & Irrigation | Water & Irrigation | 2019-06-30 | 2019-07-01 | 2020-06-01 |  | 1000000 | 1000000 | 1000000 | CGK | N/A | 1000000 | 0 | 0 | 0% |  | 1000000 | 1000000 | Completed | [6 empty] | No |  | Environmental | No | Propose budget for screening | No | Propose budget for screening | Yes | Fesibility studies and design
296 | Iltareto Borehole | Equipping with Pipes, storage tank and a pump | Increase access to safe and affordable water | Borehole equipped |  | Iltareto Borehole |  | Dalalekutuk |  | Water, Irrigation, Environment and Natural Resources | Water & Irrigation | Water & Irrigation | 2019-06-30 | 2019-07-01 | 2020-06-01 |  | 4900000 | 4900000 | 4900000 | CGK | N/A | 4900000 | 0 | 0 | 0% |  | 4900000 | 4900000 | Completed | [6 empty] | No |  | Environmental | No | Propose budget for screening | No | Propose budget for screening | Yes | Fesibility studies and design
297 | Bondeni community borehole | Construction of Bondeni community Borehole | Increase access to safe and affordable water | Borehole drilled and equipped |  | Bondeni community borehole |  | Entonet |  | Water, Irrigation, Environment and Natural Resources | Water & Irrigation | Water & Irrigation | 2019-06-30 | 2019-07-01 | 2020-06-01 |  | 7000000 | 7000000 | 7000000 | CGK | N/A | 7000000 | 0 | 0 | 0% |  | 7000000 | 7000000 | Completed | [6 empty] | No |  | Environmental | No | Propose budget for screening | No | Propose budget for screening | Yes | Fesibility studies and design
298 | Paranae Boys Sec School Water Project | Storage tank and pipping | Increase access to safe and affordable water | Storage tank constructed |  | Paranae Boys Sec School Water Project |  | Ildamat |  | Water, Irrigation, Environment and Natural Resources | Water & Irrigation | Water & Irrigation | 2019-06-30 | 2019-07-01 | 2020-06-01 |  | 5000000 | 5000000 | 5000000 | CGK | N/A | 5000000 | 0 | 0 | 0% |  | 5000000 | 5000000 | Completed | [6 empty] | No |  | Environmental | No | Propose budget for screening | No | Propose budget for screening | Yes | Fesibility studies and design
299 | Naboisho Watering Point | Storage tank and pipping from Oliorum to Naboisho | Increase access to safe and affordable water | Storage tank constructed |  | Naboisho Watering Point |  | Ildamat |  | Water, Irrigation, Environment and Natural Resources | Water & Irrigation | Water & Irrigation | 2019-06-30 | 2019-07-01 | 2020-06-01 |  | 4000000 | 4000000 | 4000000 | CGK | N/A | 4000000 | 0 | 0 | 0% |  | 4000000 | 4000000 | Completed | [6 empty] | No |  | Environmental | No | Propose budget for screening | No | Propose budget for screening | Yes | Fesibility studies and design
300 | Ormiton borehole | Rehabilitation of the borehole | Increase access to safe and affordable water | Borehole rehabilitated |  | Ormiton borehole |  | Ildamat |  | Water, Irrigation, Environment and Natural Resources | Water & Irrigation | Water & Irrigation | 2019-06-30 | 2019-07-01 | 2020-06-01 |  | 1500000 | 1500000 | 1500000 | CGK | N/A | 1500000 | 0 | 0 | 0% |  | 1500000 | 1500000 | Completed | [6 empty] | No |  | Environmental | No | Propose budget for screening | No | Propose budget for screening | Yes | Fesibility studies and design
301 | Dumping site in Kajiado town | Relocating,fencing, earth work and clearing of the old dump site | Improve management and conservation of the environment | Dumpsite decommissioned |  | Dumping site in Kajiado town |  | Ildamat |  | Water, Irrigation, Environment and Natural Resources | Environment, Natural Resources and Climate Change | Environment, Natural Resources and Climate Change | 2019-06-30 | 2019-07-01 | 2020-06-01 |  | 5800000 | 5800000 | 5800000 | CGK | N/A | 5800000 | 0 | 0 | 0% |  | 5800000 | 5800000 | Completed | [6 empty] | No |  | Environmental | No | Propose budget for screening | No | Propose budget for screening | Yes | Fesibility studies and design
302 | Tikoishi water borehole | Repair of a borehole | Increase access to safe and affordable water | Borehole rehabilitated |  | Tikoishi water borehole |  | Ildamat |  | Water, Irrigation, Environment and Natural Resources | Water & Irrigation | Water & Irrigation | 2019-06-30 | 2019-07-01 | 2020-06-01 |  | 1000000 | 1000000 | 1000000 | CGK | N/A | 1000000 | 0 | 0 | 0% |  | 1000000 | 1000000 | Completed | [6 empty] | No |  | Environmental | No | Propose budget for screening | No | Propose budget for screening | Yes | Fesibility studies and design
303 | Oltepesi storage tank | Construction of a new storage tank at Oltepesi centre | Increase access to safe and affordable water | Storage tank constructed |  | Oltepesi storage tank |  | Iloodokilani |  | Water, Irrigation, Environment and Natural Resources | Water & Irrigation | Water & Irrigation | 2019-06-30 | 2019-07-01 | 2020-06-01 |  | 1000000 | 1000000 | 1000000 | CGK | N/A | 1000000 | 0 | 0 | 0% |  | 1000000 | 1000000 | Completed | [6 empty] | No |  | Environmental | No | Propose budget for screening | No | Propose budget for screening | Yes | Fesibility studies and design
304 | Kudu Storage Tank | Rehabilitation of Water Storage Tank | Increase access to safe and affordable water | Storage tank rehabilitated |  | Kudu Storage Tank |  | Iloodokilani |  | Water, Irrigation, Environment and Natural Resources | Water & Irrigation | Water & Irrigation | 2019-06-30 | 2019-07-01 | 2020-06-01 |  | 600000 | 600000 | 600000 | CGK | N/A | 600000 | 0 | 0 | 0% |  | 600000 | 600000 | Completed | [6 empty] | No |  | Environmental | No | Propose budget for screening | No | Propose budget for screening | Yes | Fesibility studies and design
305 | Oltepesi-Oiti piping | Piping from Oltepesi to Oiti (10Km) and installation of 50m3 tank | Increase access to safe and affordable water | Pipeline constructed |  | Oltepesi-Oiti piping |  | Imaroro |  | Water, Irrigation, Environment and Natural Resources | Water & Irrigation | Water & Irrigation | 2019-06-30 | 2019-07-01 | 2020-06-01 |  | 11500000 | 11500000 | 11500000 | CGK | N/A | 11500000 | 0 | 0 | 0% |  | 11500000 | 11500000 | Completed | [6 empty] | No |  | Environmental | No | Propose budget for screening | No | Propose budget for screening | Yes | Fesibility studies and design
306 | Imaroro- Elang'ata Nanyokie Primary piping | Piping from Imaroro borehole to Elangata Nanyokie primary school (4Km) | Increase access to safe and affordable water | Pipeline constructed |  | Imaroro- Elang'ata Nanyokie Primary piping |  | Imaroro |  | Water, Irrigation, Environment and Natural Resources | Water & Irrigation | Water & Irrigation | 2019-06-30 | 2019-07-01 | 2020-06-01 |  | 3500000 | 3500000 | 3500000 | CGK | N/A | 3500000 | 0 | 0 | 0% |  | 3500000 | 3500000 | Completed | [6 empty] | No |  | Environmental | No | Propose budget for screening | No | Propose budget for screening | Yes | Fesibility studies and design
307 | Noosilale borehole | Construction of a tank at Noosilale borehole | Increase access to safe and affordable water | Storage tank constructed |  | Noosilale borehole |  | Imbirikani |  | Water, Irrigation, Environment and Natural Resources | Water & Irrigation | Water & Irrigation | 2019-06-30 | 2019-07-01 | 2020-06-01 |  | 3000000 | 3000000 | 3000000 | CGK | N/A | 3000000 | 0 | 0 | 0% |  | 3000000 | 3000000 | Completed | [6 empty] | No |  | Environmental | No | Propose budget for screening | No | Propose budget for screening | Yes | Fesibility studies and design
308 | Orngosua water tank | Renovation of water tank | Increase access to safe and affordable water | Water Storage tank rehabilitated |  | Orngosua water tank |  | Imbirikani |  | Water, Irrigation, Environment and Natural Resources | Water & Irrigation | Water & Irrigation | 2019-06-30 | 2019-07-01 | 2020-06-01 |  | 1000000 | 1000000 | 1000000 | CGK | N/A | 1000000 | 0 | 0 | 0% |  | 1000000 | 1000000 | Completed | [6 empty] | No |  | Environmental | No | Propose budget for screening | No | Propose budget for screening | Yes | Fesibility studies and design
309 | Inkoisuk water tank | Construction of water tank | Increase access to safe and affordable water | Storage tank constructed |  | Inkoisuk water tank |  | Imbirikani |  | Water, Irrigation, Environment and Natural Resources | Water & Irrigation | Water & Irrigation | 2019-06-30 | 2019-07-01 | 2020-06-01 |  | 3000000 | 3000000 | 3000000 | CGK | N/A | 3000000 | 0 | 0 | 0% |  | 3000000 | 3000000 | Stalled | 40% | 40% | Inadequate finances | 2020 | 6 | 3000000 | No | Defer | Environmental | No | Propose budget for screening | No | Propose budget for screening | Yes | Fesibility studies and design
310 | Enkirgirri borahole | Completion of drilling and equipping of Enkirgirri borehole | Increase access to safe and affordable water | Borehole drilled and equipped |  | Enkirgirri borahole |  | Kaputie North |  | Water, Irrigation, Environment and Natural Resources | Water & Irrigation | Water & Irrigation | 2019-06-30 | 2019-07-01 | 2020-06-01 |  | 4000000 | 4000000 | 4000000 | CGK | N/A | 4000000 | 0 | 0 | 0% |  | 4000000 | 4000000 | Completed | [6 empty] | No |  | Environmental | No | Propose budget for screening | No | Propose budget for screening | Yes | Fesibility studies and design
311 | Ilmukutani pipeline | Extension of pipeline to Imao | Increase access to safe and affordable water | Pipeline constructed |  | Ilmukutani pipeline |  | Kenyewa/Poka |  | Water, Irrigation, Environment and Natural Resources | Water & Irrigation | Water & Irrigation | 2019-06-30 | 2019-07-01 | 2020-06-01 |  | 6000000 | 6000000 | 6000000 | CGK | N/A | 6000000 | 0 | 0 | 0% |  | 6000000 | 6000000 | Completed | [6 empty] | No |  | Environmental | No | Propose budget for screening | No | Propose budget for screening | Yes | Fesibility studies and design
312 | Losukuroi Borehole | Drilling and equipping | Increase access to safe and affordable water | Borehole drilled and equipped |  | Losukuroi Borehole |  | Kenyewa/Poka |  | Water, Irrigation, Environment and Natural Resources | Water & Irrigation | Water & Irrigation | 2019-06-30 | 2019-07-01 | 2020-06-01 |  | 7000000 | 7000000 | 7000000 | CGK | N/A | 7000000 | 0 | 0 | 0% |  | 7000000 | 7000000 | Stalled | 40% | 40% | Inadequate finances | 2020 | 6 | 7000000 | No | Defer | Financial | No | Propose budget for screening | No | Propose budget for screening | Yes | Fesibility studies and design
313 | Elerai Borehole | Piping 3Km of Elerai community BH | Increase access to safe and affordable water | Pipeline constructed |  | Elerai Borehole |  | Kimana |  | Water, Irrigation, Environment and Natural Resources | Water & Irrigation | Water & Irrigation | 2019-06-30 | 2019-07-01 | 2020-06-01 |  | 3000000 | 3000000 | 3000000 | CGK | N/A | 3000000 | 0 | 0 | 0% |  | 3000000 | 3000000 | Completed | [6 empty] | No |  | Environmental | No | Propose budget for screening | No | Propose budget for screening | Yes | Fesibility studies and design
314 | Sombet water | Piping 3Km of Sombet community BH | Increase access to safe and affordable water | Pipeline constructed |  | Sombet water |  | Kimana |  | Water, Irrigation, Environment and Natural Resources | Water & Irrigation | Water & Irrigation | 2019-06-30 | 2019-07-01 | 2020-06-01 |  | 3000000 | 3000000 | 3000000 | CGK | N/A | 3000000 | 0 | 0 | 0% |  | 3000000 | 3000000 | Completed | [6 empty] | No |  | Environmental | No | Propose budget for screening | No | Propose budget for screening | Yes | Fesibility studies and design
315 | Oseki Borehole | Drilling and equipping of Oseki Borehole | Increase access to safe and affordable water | Borehole drilled and equipped |  | Oseki Borehole |  | Kitengela |  | Water, Irrigation, Environment and Natural Resources | Water & Irrigation | Water & Irrigation | 2019-06-30 | 2019-07-01 | 2020-06-01 |  | 7000000 | 7000000 | 7000000 | CGK | N/A | 7000000 | 0 | 0 | 0% |  | 7000000 | 7000000 | Stalled | 40% | 40% | Inadequate finances | 2020 | 6 | 7000000 | No | Defer | Financial | No | Propose budget for screening | No | Propose budget for screening | Yes | Fesibility studies and design
316 | Oloopon Community borehole | Drilling and equipping Oloopon community borehole | Increase access to safe and affordable water | Borehole drilled and equipped |  | Oloopon Community borehole |  | Kuku |  | Water, Irrigation, Environment and Natural Resources | Water & Irrigation | Water & Irrigation | 2019-06-30 | 2019-07-01 | 2020-06-01 |  | 6500000 | 6500000 | 6500000 | CGK | N/A | 6500000 | 0 | 0 | 0% |  | 6500000 | 6500000 | Stalled | 40% | 40% | Borehole caved in | 2020 | 6 | 6500000 | No | Defer | Financial | No | Propose budget for screening | No | Propose budget for screening | Yes | Fesibility studies and design
317 | Nkumama Borehole | Construction, equiping, electrification of Nkumama communty BH | Increase access to safe and affordable water | Borehole drilled and equipped |  | Nkumama Borehole |  | Kuku |  | Water, Irrigation, Environment and Natural Resources | Water & Irrigation | Water & Irrigation | 2019-06-30 | 2019-07-01 | 2020-06-01 |  | 7000000 | 7000000 | 7000000 | CGK | N/A | 7000000 | 0 | 0 | 0% |  | 7000000 | 7000000 | Completed | [6 empty] | No |  | Environmental | No | Propose budget for screening | No | Propose budget for screening | Yes | Fesibility studies and design
318 | Moilo Borehole | Construction of Moilo community BH | Increase access to safe and affordable water | Borehole drilled and equipped |  | Moilo Borehole |  | Kuku |  | Water, Irrigation, Environment and Natural Resources | Water & Irrigation | Water & Irrigation | 2019-06-30 | 2019-07-01 | 2020-06-01 |  | 7000000 | 7000000 | 7000000 | CGK | N/A | 7000000 | 0 | 0 | 0% |  | 7000000 | 7000000 | Stalled |  |  | Inadequate finances | 2020 | 6 | 7000000 | No | Defer | Financial | No | Propose budget for screening | No | Propose budget for screening | Yes | Fesibility studies and design
319 | Ebirika - Oldorko pipeline | Construction of water Pipeline | Increase access to safe and affordable water | Pipeline constructed |  | Ebirika - Oldorko pipeline |  | Magadi |  | Water, Irrigation, Environment and Natural Resources | Water & Irrigation | Water & Irrigation | 2019-06-30 | 2019-07-01 | 2020-06-01 |  | 3000000 | 3000000 | 3000000 | CGK | N/A | 3000000 | 0 | 0 | 0% |  | 3000000 | 3000000 | Completed | [6 empty] | No |  | Environmental | No | Propose budget for screening | No | Propose budget for screening | Yes | Fesibility studies and design
320 | Karaanja rock catchment | Repair and piping | Increase access to safe and affordable water | Rock catchment rehabilitated |  | Karaanja rock catchment |  | Magadi |  | Water, Irrigation, Environment and Natural Resources | Water & Irrigation | Water & Irrigation | 2019-06-30 | 2019-07-01 | 2020-06-01 |  | 500000 | 500000 | 500000 | CGK | N/A | 500000 | 0 | 0 | 0% |  | 500000 | 500000 | Completed | [6 empty] | No |  | Environmental | No | Propose budget for screening | No | Propose budget for screening | Yes | Fesibility studies and design
321 | Oloolairukok rock catchment | Construction of rock catchment | Increase access to safe and affordable water | Rock catchment constructed |  | Oloolairukok rock catchment |  | Magadi |  | Water, Irrigation, Environment and Natural Resources | Water & Irrigation | Water & Irrigation | 2019-06-30 | 2019-07-01 | 2020-06-01 |  | 2000000 | 2000000 | 2000000 | CGK | N/A | 2000000 | 0 | 0 | 0% |  | 2000000 | 2000000 | Completed | [6 empty] | No |  | Environmental | No | Propose budget for screening | No | Propose budget for screening | Yes | Fesibility studies and design
322 | Emugur water project | Desiltation and piping | Increase access to safe and affordable water | Pan desilted |  | Emugur water project |  | Magadi |  | Water, Irrigation, Environment and Natural Resources | Water & Irrigation | Water & Irrigation | 2019-06-30 | 2019-07-01 | 2020-06-01 |  | 2000000 | 2000000 | 2000000 | CGK | N/A | 2000000 | 0 | 0 | 0% |  | 2000000 | 2000000 | Completed | [6 empty] | No |  | Environmental | No | Propose budget for screening | No | Propose budget for screening | Yes | Fesibility studies and design
323 | Eseki borehole | Drilling of a new borehole | Increase access to safe and affordable water | Borehole drilled and equipped |  | Eseki borehole |  | Matapato North |  | Water, Irrigation, Environment and Natural Resources | Water & Irrigation | Water & Irrigation | 2019-06-30 | 2019-07-01 | 2020-06-01 |  | 3000000 | 3000000 | 3000000 | CGK | N/A | 3000000 | 0 | 0 | 0% |  | 3000000 | 3000000 | Completed | [6 empty] | No |  | Environmental | No | Propose budget for screening | No | Propose budget for screening | Yes | Fesibility studies and design
324 | Olmotiany borehole | Purchasing of a borehole genset | Increase access to safe and affordable water | Borehole rehabilitated |  | Olmotiany borehole |  | Matapato North |  | Water, Irrigation, Environment and Natural Resources | Water & Irrigation | Water & Irrigation | 2019-06-30 | 2019-07-01 | 2020-06-01 |  | 2000000 | 2000000 | 2000000 | CGK | N/A | 2000000 | 0 | 0 | 0% |  | 2000000 | 2000000 | Completed | [6 empty] | No |  | Environmental | No | Propose budget for screening | No | Propose budget for screening | Yes | Fesibility studies and design
325 | Loltiamiloi borehole | Equipping of the borehole | Increase access to safe and affordable water | Borehole equipped |  | Loltiamiloi borehole |  | Matapato South |  | Water, Irrigation, Environment and Natural Resources | Water & Irrigation | Water & Irrigation | 2019-06-30 | 2019-07-01 | 2020-06-01 |  | 4000000 | 4000000 | 4000000 | CGK | N/A | 4000000 | 0 | 0 | 0% |  | 4000000 | 4000000 | Completed | [6 empty] | No |  | Environmental | No | Propose budget for screening | No | Propose budget for screening | Yes | Fesibility studies and design
326 | Meto secondary school borehole | Drilling and equipping borehole | Increase access to safe and affordable water | Borehole drilled and equipped |  | Meto secondary school borehole |  | Matapato South |  | Water, Irrigation, Environment and Natural Resources | Water & Irrigation | Water & Irrigation | 2019-06-30 | 2019-07-01 | 2020-06-01 |  | 7000000 | 7000000 | 7000000 | CGK | N/A | 7000000 | 0 | 0 | 0% |  | 7000000 | 7000000 | Completed | [6 empty] | No |  | Environmental | No | Propose budget for screening | No | Propose budget for screening | Yes | Fesibility studies and design
327 | Embarbal borehole | Drilling and equiping embarbal borehole | Increase access to safe and affordable water | Borehole drilled and equipped |  | Embarbal borehole |  | Mosiro |  | Water, Irrigation, Environment and Natural Resources | Water & Irrigation | Water & Irrigation | 2019-06-30 | 2019-07-01 | 2020-06-01 |  | 7000000 | 7000000 | 7000000 | CGK | N/A | 7000000 | 0 | 0 | 0% |  | 7000000 | 7000000 | Completed | [6 empty] | No |  | Environmental | No | Propose budget for screening | No | Propose budget for screening | Yes | Fesibility studies and design
328 | Mariani and Embarbal water pan | Rehabilitation of Mariani and Embarbal water pan | Increase access to safe and affordable water | Water pan rehabilitated |  | Mariani and Embarbal water pan |  | Mosiro |  | Water, Irrigation, Environment and Natural Resources | Water & Irrigation | Water & Irrigation | 2019-06-30 | 2019-07-01 | 2020-06-01 |  | 2500000 | 2500000 | 2500000 | CGK | N/A | 2500000 | 0 | 0 | 0% |  | 2500000 | 2500000 | Completed | [6 empty] | No |  | Environmental | No | Propose budget for screening | No | Propose budget for screening | Yes | Fesibility studies and design
329 | Lemelepo Water Project | Installation of solar panels for 48,000 cubic metres | Increase access to safe and affordable water | Borehole solarized |  | Lemelepo Water Project |  | Olkeri |  | Water, Irrigation, Environment and Natural Resources | Water & Irrigation | Water & Irrigation | 2019-06-30 | 2019-07-01 | 2020-06-01 |  | 4000000 | 4000000 | 4000000 | CGK | N/A | 4000000 | 0 | 0 | 0% |  | 4000000 | 4000000 | Completed | [6 empty] | No |  | Environmental | No | Propose budget for screening | No | Propose budget for screening | Yes | Fesibility studies and design
330 | Oloika Borehole | Drilling and equipping, solar panel installation, overhead tank (100,000Lts) | Increase access to safe and affordable water | Borehole drilled and equipped |  | Oloika Borehole |  | Olkeri |  | Water, Irrigation, Environment and Natural Resources | Water & Irrigation | Water & Irrigation | 2019-06-30 | 2019-07-01 | 2020-06-01 |  | 7000000 | 7000000 | 7000000 | CGK | N/A | 7000000 | 0 | 0 | 0% |  | 7000000 | 7000000 | Completed | [6 empty] | No |  | Environmental | No | Propose budget for screening | No | Propose budget for screening | Yes | Fesibility studies and design
331 | Olkeri Borehole (Chief's camp) | Drilling and equipping and installation of solar panels | Increase access to safe and affordable water | Borehole drilled and equipped |  | Olkeri Borehole (Chief's camp) |  | Olkeri |  | Water, Irrigation, Environment and Natural Resources | Water & Irrigation | Water & Irrigation | 2019-06-30 | 2019-07-01 | 2020-06-01 |  | 7000000 | 7000000 | 7000000 | CGK | N/A | 7000000 | 0 | 0 | 0% |  | 7000000 | 7000000 | Stalled | 40% | 40% | Inadequate finances | 2020 | 6 | 7000000 | No | Defer | Financial | No | Propose budget for screening | No | Propose budget for screening | Yes | Fesibility studies and design
332 | Mutongu Borehole | Installation of Solar panel for pumping | Increase access to safe and affordable water | Borehole solarized |  | Mutongu Borehole |  | Oloolua |  | Water, Irrigation, Environment and Natural Resources | Water & Irrigation | Water & Irrigation | 2019-06-30 | 2019-07-01 | 2020-06-01 |  | 3500000 | 3500000 | 3500000 | CGK | N/A | 3500000 | 0 | 0 | 0% |  | 3500000 | 3500000 | Completed | [6 empty] | No |  | Environmental | No | Propose budget for screening | No | Propose budget for screening | Yes | Fesibility studies and design
333 | Kianugu borehole | Installation of Solar panel for pumping | Increase access to safe and affordable water | Borehole solarized |  | Kianugu borehole |  | Oloolua |  | Water, Irrigation, Environment and Natural Resources | Water & Irrigation | Water & Irrigation | 2019-06-30 | 2019-07-01 | 2020-06-01 |  | 3500000 | 3500000 | 3500000 | CGK | N/A | 3500000 | 0 | 0 | 0% |  | 3500000 | 3500000 | Completed | [6 empty] | No |  | Environmental | No | Propose budget for screening | No | Propose budget for screening | Yes | Fesibility studies and design
334 | Olempuya Borehole | Drilling and equipping of Olempuya Borehole at Ole Mpuya near Ole Mardadi home | Increase access to safe and affordable water | Borehole drilled and equipped |  | Olempuya Borehole |  | Oloosirkon/Sholinke |  | Water, Irrigation, Environment and Natural Resources | Water & Irrigation | Water & Irrigation | 2019-06-30 | 2019-07-01 | 2020-06-01 |  | 7000000 | 7000000 | 7000000 | CGK | N/A | 7000000 | 0 | 0 | 0% |  | 7000000 | 7000000 | Completed | [6 empty] | No |  | Environmental | No | Propose budget for screening | No | Propose budget for screening | Yes | Fesibility studies and design
335 | Esiret dam | Desilting of Esiret dam | Increase access to safe and affordable water | Dam desilted |  | Esiret dam |  | Purko |  | Water, Irrigation, Environment and Natural Resources | Water & Irrigation | Water & Irrigation | 2019-06-30 | 2019-07-01 | 2020-06-01 |  | 5000000 | 5000000 | 5000000 | CGK | N/A | 5000000 | 0 | 0 | 0% |  | 5000000 | 5000000 | Completed | [6 empty] | No |  | Environmental | No | Propose budget for screening | No | Propose budget for screening | Yes | Fesibility studies and design
336 | Ilngosuani borehole | Piping of water from Ilngosuani borehole to Esilanke Oltepesi pump and construction of 50,000 litres tank | Increase access to safe and affordable water | Pipeline constructed |  | Ilngosuani borehole |  | Purko |  | Water, Irrigation, Environment and Natural Resources | Water & Irrigation | Water & Irrigation | 2019-06-30 | 2019-07-01 | 2020-06-01 |  | 6000000 | 6000000 | 6000000 | CGK | N/A | 6000000 | 0 | 0 | 0% |  | 6000000 | 6000000 | Completed | [6 empty] | No |  | Environmental | No | Propose budget for screening | No | Propose budget for screening | Yes | Fesibility studies and design
337 | Njukini community Borehole | Equiping and completion of Njukini community borehole | Increase access to safe and affordable water | Borehole drilled and equipped |  | Njukini community Borehole |  | Rombo |  | Water, Irrigation, Environment and Natural Resources | Water & Irrigation | Water & Irrigation | 2019-06-30 | 2019-07-01 | 2020-06-01 |  | 2000000 | 2000000 | 2000000 | CGK | N/A | 2000000 | 0 | 0 | 0% |  | 2000000 | 2000000 | Completed | [6 empty] | No |  | Environmental | No | Propose budget for screening | No | Propose budget for screening | Yes | Fesibility studies and design
338 | Enchurrai community borehole | Construction and equiping of Enchurrai Borehole | Increase access to safe and affordable water | Borehole drilled and equipped |  | Enchurrai community borehole |  | Rombo |  | Water, Irrigation, Environment and Natural Resources | Water & Irrigation | Water & Irrigation | 2019-06-30 | 2019-07-01 | 2020-06-01 |  | 7000000 | 7000000 | 7000000 | CGK | N/A | 7000000 | 0 | 0 | 0% |  | 7000000 | 7000000 | Completed | [6 empty] | No |  | Environmental | No | Propose budget for screening | No | Propose budget for screening | Yes | Fesibility studies and design
339 | Oltiasilalei water project | Piping and electrification of Oltiasilale borehole | Increase access to safe and affordable water | Pipeline constructed |  | Oltiasilalei water project |  | Rombo |  | Water, Irrigation, Environment and Natural Resources | Water & Irrigation | Water & Irrigation | 2019-06-30 | 2019-07-01 | 2020-06-01 |  | 2500000 | 2500000 | 2500000 | CGK | N/A | 2500000 | 0 | 0 | 0% |  | 2500000 | 2500000 | Completed | [6 empty] | No |  | Environmental | No | Propose budget for screening | No | Propose budget for screening | Yes | Fesibility studies and design
340 | Maroroi water project | Extension of pipeline of Maroroi water project | Increase access to safe and affordable water | Pipeline constructed |  | Maroroi water project |  | Rombo |  | Water, Irrigation, Environment and Natural Resources | Water & Irrigation | Water & Irrigation | 2019-06-30 | 2019-07-01 | 2020-06-01 |  | 2500000 | 2500000 | 2500000 | CGK | N/A | 2500000 | 0 | 0 | 0% |  | 2500000 | 2500000 | Completed | [6 empty] | No |  | Environmental | No | Propose budget for screening | No | Propose budget for screening | Yes | Fesibility studies and design
341 | Kibaoni water project | Piping of water at Kibaoni water project | Increase access to safe and affordable water | Pipeline constructed |  | Kibaoni water project |  | Rombo |  | Water, Irrigation, Environment and Natural Resources | Water & Irrigation | Water & Irrigation | 2019-06-30 | 2019-07-01 | 2020-06-01 |  | 1000000 | 1000000 | 1000000 | CGK | N/A | 1000000 | 0 | 0 | 0% |  | 1000000 | 1000000 | Completed | [6 empty] | No |  | Environmental | No | Propose budget for screening | No | Propose budget for screening | Yes | Fesibility studies and design
342 | Kikelelwa water project | Pping of water at Kikelelwa water project | Increase access to safe and affordable water | Pipeline constructed |  | Kikelelwa water project |  | Rombo |  | Water, Irrigation, Environment and Natural Resources | Water & Irrigation | Water & Irrigation | 2019-06-30 | 2019-07-01 | 2020-06-01 |  | 1000000 | 1000000 | 1000000 | CGK | N/A | 1000000 | 0 | 0 | 0% |  | 1000000 | 1000000 | Completed | [6 empty] | No |  | Environmental | No | Propose budget for screening | No | Propose budget for screening | Yes | Fesibility studies and design
343 | Ongata Rongai Pri School | Water havesting, construction of a tank and installation of gutters | Increase access to safe and affordable water | Water harvesting system constructed |  | Ongata Rongai Pri School |  | Nkaimurunya |  | Water, Irrigation, Environment and Natural Resources | Water & Irrigation | Water & Irrigation | 2019-06-30 | 2019-07-01 | 2020-06-01 |  | 1000000 | 1000000 | 1000000 | CGK | N/A | 1000000 | 0 | 0 | 0% |  | 1000000 | 1000000 | Completed | [6 empty] | No |  | Environmental | No | Propose budget for screening | No | Propose budget for screening | Yes | Fesibility studies and design
344 | Nadonkajijik water | Construction of a water tank at Nadonkajijik | Increase access to safe and affordable water | Storage tank constructed |  | Nadonkajijik water |  | Imbirikani |  | Water, Irrigation, Environment and Natural Resources | Water & Irrigation | Water & Irrigation | 2019-06-30 | 2019-07-01 | 2020-06-01 |  | 3000000 | 3000000 | 3000000 | CGK | N/A | 3000000 | 0 | 0 | 0% |  | 3000000 | 3000000 | Completed | [6 empty] | No |  | Environmental | No | Propose budget for screening | No | Propose budget for screening | Yes | Fesibility studies and design
345 | Nasipa water project | Construction of a new tank and piping | Increase access to safe and affordable water | Storage tank constructed |  | Nasipa water project |  | Imbirikani |  | Water, Irrigation, Environment and Natural Resources | Water & Irrigation | Water & Irrigation | 2019-06-30 | 2019-07-01 | 2020-06-01 |  | 4000000 | 4000000 | 4000000 | CGK | N/A | 4000000 | 0 | 0 | 0% |  | 4000000 | 4000000 | Completed | [6 empty] | No |  | Environmental | No | Propose budget for screening | No | Propose budget for screening | Yes | Fesibility studies and design
346 | Kibiko Water Borehole | Drilling ,equipping and piping | Increase access to safe and affordable water | Borehole drilled and equipped |  | Kibiko Water Borehole |  | Ewuaso |  | Water, Irrigation, Environment and Natural Resources | Water & Irrigation | Water & Irrigation | 2019-06-30 | 2019-07-01 | 2020-06-01 |  | 7000000 | 7000000 | 7000000 | CGK | N/A | 7000000 | 0 | 0 | 0% |  | 7000000 | 7000000 | Completed | [6 empty] | No |  | Environmental | No | Propose budget for screening | No | Propose budget for screening | Yes | Fesibility studies and design
347 | Enkoireroi Water Project | Drilling ,equipping and piping | Increase access to safe and affordable water | Borehole drilled and equipped |  | Enkoireroi Water Project |  | Ewuaso |  | Water, Irrigation, Environment and Natural Resources | Water & Irrigation | Water & Irrigation | 2019-06-30 | 2019-07-01 | 2020-06-01 |  | 7000000 | 7000000 | 7000000 | CGK | N/A | 7000000 | 0 | 0 | 0% |  | 7000000 | 7000000 | Completed | [6 empty] | No |  | Environmental | No | Propose budget for screening | No | Propose budget for screening | Yes | Fesibility studies and design
348 | Olokirdingai Water Project | Piping about 3km | Increase access to safe and affordable water | Pipeline constructed |  | Olokirdingai Water Project |  | Ewuaso |  | Water, Irrigation, Environment and Natural Resources | Water & Irrigation | Water & Irrigation | 2019-06-30 | 2019-07-01 | 2020-06-01 |  | 5000000 | 5000000 | 5000000 | CGK | N/A | 5000000 | 0 | 0 | 0% |  | 5000000 | 5000000 | Completed | [6 empty] | No |  | Environmental | No | Propose budget for screening | No | Propose budget for screening | Yes | Fesibility studies and design
349 | Nkaimurunya modern tree nurseries | Construction and fencing of a modern tree nurseries | Improve management and conservation of the environment | Tree nursery established |  | Nkaimurunya modern tree nurseries |  | Nkaimurunya |  | Water, Irrigation, Environment and Natural Resources | Environment, Natural Resources and Climate Change | Environment, Natural Resources and Climate Change | 2019-06-30 | 2019-07-01 | 2020-06-01 |  | 2800000 | 2800000 | 2800000 | CGK | N/A | 2800000 | 0 | 0 | 0% |  | 2800000 | 2800000 | Completed | [6 empty] | No |  | Environmental | No | Propose budget for screening | No | Propose budget for screening | Yes | Fesibility studies and design
350 | Recreational park/green zone | Fencing , landscaping, construction of public toilets,office block | Improve management and conservation of the environment | Recreational park constructed |  | Recreational park/green zone |  | Nkaimurunya |  | Water, Irrigation, Environment and Natural Resources | Environment, Natural Resources and Climate Change | Environment, Natural Resources and Climate Change | 2019-06-30 | 2019-07-01 | 2020-06-01 |  | 5000000 | 5000000 | 5000000 | CGK | N/A | 5000000 | 0 | 0 | 0% |  | 5000000 | 5000000 | Completed | [6 empty] | No |  | Environmental | Yes | Climate proofing | Yes | Propose budget for screening | Yes | Fesibility studies and design
351 | Oldonyorok/ Kerema-Ilbisil water pipeline | Water reticulation; rehabilitation of pipelines and infrastructure development | Increase access to safe and affordable water | Pipeline constructed |  | Oldonyorok/ Kerema-Ilbisil water pipeline | Kajiado Central and East | Ildamat; Matapato North and Kitengela |  | Water, Irrigation, Environment and Natural Resources | Water & Irrigation | Water & Irrigation | 2019-06-30 | 2019-07-01 | 2020-06-01 |  | 20000000 | 20000000 | 20000000 | CGK | N/A | 20000000 | 0 | 0 | 0% |  | 20000000 | 20000000 | Stalled | 0% | 0% | Inadequate finances | 2020 | 6 | 20000000 | No | Defer | Environmental | Yes | Climate proofing | Yes | Propose budget for screening | Yes | Fesibility studies and design
352 | Kitengela town water supply | Water reticulation | Increase access to safe and affordable water | Water reticulation done |  | Kitengela town water supply | Kajiado East | Kitengela |  | Water, Irrigation, Environment and Natural Resources | Water & Irrigation | Water & Irrigation | 2019-06-30 | 2019-07-01 | 2020-06-01 |  | 37000000 | 37000000 | 37000000 | CGK | N/A | 37000000 | 0 | 0 | 0% |  | 37000000 | 37000000 | Completed | [6 empty] | No |  | Environmental | No | Propose budget for screening | No | Propose budget for screening | Yes | Fesibility studies and design
353 | Water Supply services | Acquisition of 1 No.Water bowsers | Increase access to safe and affordable water | Water bowser purchased |  | Water Supply services | County HQ | County HQ |  | Water, Irrigation, Environment and Natural Resources | Water & Irrigation | Water & Irrigation | 2019-06-30 | 2019-07-01 | 2020-06-01 |  | 9000000 | 9000000 | 9000000 | CGK | N/A | 9000000 | 0 | 0 | 0% |  | 9000000 | 9000000 | Stalled | 0% | 0% | Inadequate finances | 2020 | 6 | 9000000 | No | Defer | Financial | No | Propose budget for screening | No | Propose budget for screening | Yes | Fesibility studies and design
354 | Ngong Dumpsite | Relocation and land reclamation of Ngong Dumpsite; Kitengela and Kajiado | Improve management and conservation of the environment | Dumpsite decommissioned |  | Ngong Dumpsite | Kajiado North | Ngong |  | Water, Irrigation, Environment and Natural Resources | Environment, Natural Resources and Climate Change | Environment, Natural Resources and Climate Change | 2019-06-30 | 2019-07-01 | 2020-06-01 |  | 50000000 | 50000000 | 50000000 | CGK | N/A | 50000000 | 0 | 0 | 0% |  | 50000000 | 50000000 | Completed | [6 empty] | No |  | Environmental | No | Propose budget for screening | No | Propose budget for screening | Yes | Fesibility studies and design
355 | Isisira Dam | Drilling and Equipping | Increase access to safe and affordable water | Borehole drilled and equipped |  | Isisira Dam | Imaroro | Ilmungush |  | Water, Irrigation, Environment and Natural Resources | Water & Irrigation | Water & Irrigation | 2020-06-30 | 2020-07-01 | 2021-06-01 |  | 6000000 | 6000000 | 6000000 | CGK | N/A | 6000000 | 0 | 0 | 0% |  | 6000000 | 6000000 | Completed | [6 empty] | No |  | Environmental | No | Propose budget for screening | No | Propose budget for screening | Yes | Fesibility studies and design
356 | Kibaoni Borehole | Piping from Kibaoni toward Illasit town | Increase access to safe and affordable water | Pipeline constructed |  | Kibaoni Borehole | Rombo | Entarara |  | Water, Irrigation, Environment and Natural Resources | Water & Irrigation | Water & Irrigation | 2020-06-30 | 2020-07-01 | 2021-06-01 |  | 2000000 | 2000000 | 2000000 | CGK | N/A | 2000000 | 0 | 0 | 0% |  | 2000000 | 2000000 | Completed | [6 empty] | No |  | Environmental | No | Propose budget for screening | No | Propose budget for screening | Yes | Fesibility studies and design
357 | Olmapinu Water Borehole | Drilling and equipping | Increase access to safe and affordable water | Borehole drilled and equipped |  | Olmapinu Water Borehole | Rombo | Njukini |  | Water, Irrigation, Environment and Natural Resources | Water & Irrigation | Water & Irrigation | 2020-06-30 | 2020-07-01 | 2021-06-01 |  | 7000000 | 7000000 | 7000000 | CGK | N/A | 7000000 | 0 | 0 | 0% |  | 7000000 | 7000000 | Completed | [6 empty] | No |  | Environmental | No | Propose budget for screening | No | Propose budget for screening | Yes | Fesibility studies and design
358 | Ensukuta mashambani water pipeline | Pipeline maintenance | Increase access to safe and affordable water | Pipeline rehabilitated |  | Ensukuta mashambani water pipeline | Rombo | Rombo |  | Water, Irrigation, Environment and Natural Resources | Water & Irrigation | Water & Irrigation | 2020-06-30 | 2020-07-01 | 2021-06-01 |  | 1500000 | 1500000 | 1500000 | CGK | N/A | 1500000 | 0 | 0 | 0% |  | 1500000 | 1500000 | Completed | [6 empty] | No |  | Environmental | No | Propose budget for screening | No | Propose budget for screening | Yes | Fesibility studies and design
359 | Mariani borehole | Equipping | Increase access to safe and affordable water | Borehole equipped |  | Mariani borehole | Mosiro | Embarbal |  | Water, Irrigation, Environment and Natural Resources | Water & Irrigation | Water & Irrigation | 2020-06-30 | 2020-07-01 | 2021-06-01 |  | 3000000 | 3000000 | 3000000 | CGK | N/A | 3000000 | 0 | 0 | 0% |  | 3000000 | 3000000 | Completed | [6 empty] | No |  | Environmental | No | Propose budget for screening | No | Propose budget for screening | Yes | Fesibility studies and design
360 | Oldorko Centre Water tank | Piping from Olkunono borehole through Mosiro Market, Mosiro Dispensary to the masonry tank at Odorko centre | Increase access to safe and affordable water | Pipeline constructed |  | Oldorko Centre Water tank | Mosiro | Oldorko |  | Water, Irrigation, Environment and Natural Resources | Water & Irrigation | Water & Irrigation | 2020-06-30 | 2020-07-01 | 2021-06-01 |  | 3000000 | 3000000 | 3000000 | CGK | N/A | 3000000 | 0 | 0 | 0% |  | 3000000 | 3000000 | Completed | [6 empty] | No |  | Environmental | No | Propose budget for screening | No | Propose budget for screening | Yes | Fesibility studies and design
361 | Oldorko Centre Water tank | Piping and renovation of masonry water tank at Oldorko Centre | Increase access to safe and affordable water | Pipeline constructed |  | Oldorko Centre Water tank | Mosiro | Oldepe |  | Water, Irrigation, Environment and Natural Resources | Water & Irrigation | Water & Irrigation | 2020-06-30 | 2020-07-01 | 2021-06-01 |  | 3000000 | 3000000 | 3000000 | CGK | N/A | 3000000 | 0 | 0 | 0% |  | 3000000 | 3000000 | Completed | [6 empty] | No |  | Environmental | No | Propose budget for screening | No | Propose budget for screening | Yes | Fesibility studies and design
362 | Imarriani & Embarbal water pan | Completion of Imarriani and Embarbal water pan project | Increase access to safe and affordable water | Water pan constructed |  | Imarriani & Embarbal water pan | Mosiro | Embarbal |  | Water, Irrigation, Environment and Natural Resources | Water & Irrigation | Water & Irrigation | 2020-06-30 | 2020-07-01 | 2021-06-01 |  | 6500000 | 6500000 | 6500000 | CGK | N/A | 6500000 | 0 | 0 | 0% |  | 6500000 | 6500000 | Completed | [6 empty] | No |  | Environmental | No | Propose budget for screening | No | Propose budget for screening | Yes | Fesibility studies and design
363 | Oloosilale Borehole | Drilling and Equipping | Increase access to safe and affordable water | Borehole drilled and equipped |  | Oloosilale Borehole | Matapato South | Kumpa |  | Water, Irrigation, Environment and Natural Resources | Water & Irrigation | Water & Irrigation | 2020-06-30 | 2020-07-01 | 2021-06-01 |  | 7000000 | 7000000 | 7000000 | CGK | N/A | 7000000 | 0 | 0 | 0% |  | 7000000 | 7000000 | Completed | [6 empty] | No |  | Environmental | No | Propose budget for screening | No | Propose budget for screening | Yes | Fesibility studies and design
364 | Oloitil Isoitok Borehole | Drilling | Increase access to safe and affordable water | Borehole drilled and equipped |  | Oloitil Isoitok Borehole | Matapato South | Meto |  | Water, Irrigation, Environment and Natural Resources | Water & Irrigation | Water & Irrigation | 2020-06-30 | 2020-07-01 | 2021-06-01 |  | 2000000 | 2000000 | 2000000 | CGK | N/A | 2000000 | 0 | 0 | 0% |  | 2000000 | 2000000 | Completed | [6 empty] | No |  | Environmental | No | Propose budget for screening | No | Propose budget for screening | Yes | Fesibility studies and design
365 | Lenchani Borehole | Rehabilitation | Increase access to safe and affordable water | Borehole rehabilitated |  | Lenchani Borehole | Matapato South | Oldonyio-Orok |  | Water, Irrigation, Environment and Natural Resources | Water & Irrigation | Water & Irrigation | 2020-06-30 | 2020-07-01 | 2021-06-01 |  | 3000000 | 3000000 | 3000000 | CGK | N/A | 3000000 | 0 | 0 | 0% |  | 3000000 | 3000000 | Completed | [6 empty] | No |  | Environmental | No | Propose budget for screening | No | Propose budget for screening | Yes | Fesibility studies and design
366 | Eluanata Borehole | Building of Water tank, trough and piping | Increase access to safe and affordable water | Storage tank constructed |  | Eluanata Borehole | Matapato South | Eluanata |  | Water, Irrigation, Environment and Natural Resources | Water & Irrigation | Water & Irrigation | 2020-06-30 | 2020-07-01 | 2021-06-01 |  | 2000000 | 2000000 | 2000000 | CGK | N/A | 2000000 | 0 | 0 | 0% |  | 2000000 | 2000000 | Completed | [6 empty] | No |  | Environmental | No | Propose budget for screening | No | Propose budget for screening | Yes | Fesibility studies and design
367 | Olasiti Borehole | Completion | Increase access to safe and affordable water | Borehole drilled and equipped |  | Olasiti Borehole | Matapato South | Oldonyio-Orok |  | Water, Irrigation, Environment and Natural Resources | Water & Irrigation | Water & Irrigation | 2020-06-30 | 2020-07-01 | 2021-06-01 |  | 4000000 | 4000000 | 4000000 | CGK | N/A | 4000000 | 0 | 0 | 0% |  | 4000000 | 4000000 | Completed | [6 empty] | No |  | Environmental | No | Propose budget for screening | No | Propose budget for screening | Yes | Fesibility studies and design
368 | Maisikiria Borehole | Drilling and Equipping | Increase access to safe and affordable water | Borehole drilled and equipped |  | Maisikiria Borehole | Matapato North | Ruanche |  | Water, Irrigation, Environment and Natural Resources | Water & Irrigation | Water & Irrigation | 2020-06-30 | 2020-07-01 | 2021-06-01 |  | 6000000 | 6000000 | 6000000 | CGK | N/A | 6000000 | 0 | 0 | 0% |  | 6000000 | 6000000 | Completed | [6 empty] | No |  | Environmental | No | Propose budget for screening | No | Propose budget for screening | Yes | Fesibility studies and design
369 | Indonyio Borehole | Construction of storage tanks and cattle troughs | Increase access to safe and affordable water | Storage tank constructed |  | Indonyio Borehole | Matapato North | Ruanche |  | Water, Irrigation, Environment and Natural Resources | Water & Irrigation | Water & Irrigation | 2020-06-30 | 2020-07-01 | 2021-06-01 |  | 2000000 | 2000000 | 2000000 | CGK | N/A | 2000000 | 0 | 0 | 0% |  | 2000000 | 2000000 | Completed | [6 empty] | No |  | Environmental | No | Propose budget for screening | No | Propose budget for screening | Yes | Fesibility studies and design
370 | Rongai Tank | Construction of 100 Metre Cubit Water Tank | Increase access to safe and affordable water | Storage tank constructed |  | Rongai Tank | Entonet Lenkism | Olchorro |  | Water, Irrigation, Environment and Natural Resources | Water & Irrigation | Water & Irrigation | 2020-06-30 | 2020-07-01 | 2021-06-01 |  | 5000000 | 5000000 | 5000000 | CGK | N/A | 5000000 | 0 | 0 | 0% |  | 5000000 | 5000000 | Completed | [6 empty] | No |  | Environmental | No | Propose budget for screening | No | Propose budget for screening | Yes | Fesibility studies and design
371 | Esokota Water Towers | Piping and Construction of Tanks | Increase access to safe and affordable water | Pipeline constructed |  | Esokota Water Towers | Ildamat | Esokota |  | Water, Irrigation, Environment and Natural Resources | Water & Irrigation | Water & Irrigation | 2020-06-30 | 2020-07-01 | 2021-06-01 |  | 4000000 | 4000000 | 4000000 | CGK | N/A | 4000000 | 0 | 0 | 0% |  | 4000000 | 4000000 | Completed | [6 empty] | No |  | Environmental | No | Propose budget for screening | No | Propose budget for screening | Yes | Fesibility studies and design
372 | Orkaria Community Borehole | Drilling and Equipping | Increase access to safe and affordable water | Borehole drilled and equipped |  | Orkaria Community Borehole | Kuku | Kuku |  | Water, Irrigation, Environment and Natural Resources | Water & Irrigation | Water & Irrigation | 2020-06-30 | 2020-07-01 | 2021-06-01 |  | 6000000 | 6000000 | 6000000 | CGK | N/A | 6000000 | 0 | 0 | 0% |  | 6000000 | 6000000 | Completed | [6 empty] | No |  | Environmental | No | Propose budget for screening | No | Propose budget for screening | Yes | Fesibility studies and design
373 | Oltemwai Communtiy Borehole | Drilling and Equipping | Increase access to safe and affordable water | Borehole drilled and equipped |  | Oltemwai Communtiy Borehole | Kuku | Elangata enkima |  | Water, Irrigation, Environment and Natural Resources | Water & Irrigation | Water & Irrigation | 2020-06-30 | 2020-07-01 | 2021-06-01 |  | 6000000 | 6000000 | 6000000 | CGK | N/A | 6000000 | 0 | 0 | 0% |  | 6000000 | 6000000 | Completed | [6 empty] | No |  | Environmental | No | Propose budget for screening | No | Propose budget for screening | Yes | Fesibility studies and design
374 | Iltilal Water Tank | Purchase and installation | Increase access to safe and affordable water | Storage tank constructed |  | Iltilal Water Tank | Kuku | Olorika |  | Water, Irrigation, Environment and Natural Resources | Water & Irrigation | Water & Irrigation | 2020-06-30 | 2020-07-01 | 2021-06-01 |  | 2500000 | 2500000 | 2500000 | CGK | N/A | 2500000 | 0 | 0 | 0% |  | 2500000 | 2500000 | Completed | [6 empty] | No |  | Environmental | No | Propose budget for screening | No | Propose budget for screening | Yes | Fesibility studies and design
375 | Orpura Community Borehole | Drilling and Equipping | Increase access to safe and affordable water | Borehole drilled and equipped |  | Orpura Community Borehole | Kuku | Iltilal |  | Water, Irrigation, Environment and Natural Resources | Water & Irrigation | Water & Irrigation | 2020-06-30 | 2020-07-01 | 2021-06-01 |  | 6000000 | 6000000 | 6000000 | CGK | N/A | 6000000 | 0 | 0 | 0% |  | 6000000 | 6000000 | Completed | [6 empty] | No |  | Environmental | No | Propose budget for screening | No | Propose budget for screening | Yes | Fesibility studies and design
376 | Kuku Pipeline Extension | Extension of Pipeline | Increase access to safe and affordable water | Pipeline constructed |  | Kuku Pipeline Extension | Kuku | Iltilal |  | Water, Irrigation, Environment and Natural Resources | Water & Irrigation | Water & Irrigation | 2020-06-30 | 2020-07-01 | 2021-06-01 |  | 1500000 | 1500000 | 1500000 | CGK | N/A | 1500000 | 0 | 0 | 0% |  | 1500000 | 1500000 | Completed | [6 empty] | No |  | Environmental | No | Propose budget for screening | No | Propose budget for screening | Yes | Fesibility studies and design
377 | Emesasu Pipeline | Extension of Pipeline | Increase access to safe and affordable water | Pipeline constructed |  | Emesasu Pipeline | Kuku | Elangata enkima |  | Water, Irrigation, Environment and Natural Resources | Water & Irrigation | Water & Irrigation | 2020-06-30 | 2020-07-01 | 2021-06-01 |  | 1000000 | 1000000 | 1000000 | CGK | N/A | 1000000 | 0 | 0 | 0% |  | 1000000 | 1000000 | Completed | [6 empty] | No |  | Environmental | No | Propose budget for screening | No | Propose budget for screening | Yes | Fesibility studies and design
378 | BulBul Borehole | Equipping Borehole | Increase access to safe and affordable water | Borehole equipped |  | BulBul Borehole | Oloolua | BulBul |  | Water, Irrigation, Environment and Natural Resources | Water & Irrigation | Water & Irrigation | 2020-06-30 | 2020-07-01 | 2021-06-01 |  | 4000000 | 4000000 | 4000000 | CGK | N/A | 4000000 | 0 | 0 | 0% |  | 4000000 | 4000000 | Completed | [6 empty] | No |  | Environmental | No | Propose budget for screening | No | Propose budget for screening | Yes | Fesibility studies and design
379 | Lekurruki Borehole | Sinking, Istallationof pump and Solar Panel | Increase access to safe and affordable water | Borehole drilled and equipped |  | Lekurruki Borehole | Olkeri | Lekuruki |  | Water, Irrigation, Environment and Natural Resources | Water & Irrigation | Water & Irrigation | 2020-06-30 | 2020-07-01 | 2021-06-01 |  | 7000000 | 7000000 | 7000000 | CGK | N/A | 7000000 | 0 | 0 | 0% |  | 7000000 | 7000000 | Completed | [6 empty] | No |  | Environmental | No | Propose budget for screening | No | Propose budget for screening | Yes | Fesibility studies and design
380 | Olkeri Water Project | Installation of Pipes | Increase access to safe and affordable water | Pipeline constructed |  | Olkeri Water Project | Olkeri | Olkeri |  | Water, Irrigation, Environment and Natural Resources | Water & Irrigation | Water & Irrigation | 2020-06-30 | 2020-07-01 | 2021-06-01 |  | 1000000 | 1000000 | 1000000 | CGK | N/A | 1000000 | 0 | 0 | 0% |  | 1000000 | 1000000 | Completed | [6 empty] | No |  | Environmental | No | Propose budget for screening | No | Propose budget for screening | Yes | Fesibility studies and design
381 | Merisho Water Project | Installation of Pipes | Increase access to safe and affordable water | Pipeline constructed |  | Merisho Water Project | Olkeri | Merisho |  | Water, Irrigation, Environment and Natural Resources | Water & Irrigation | Water & Irrigation | 2020-06-30 | 2020-07-01 | 2021-06-01 |  | 1000000 | 1000000 | 1000000 | CGK | N/A | 1000000 | 0 | 0 | 0% |  | 1000000 | 1000000 | Completed | [6 empty] | No |  | Environmental | No | Propose budget for screening | No | Propose budget for screening | Yes | Fesibility studies and design
382 | Kware Drainage | Installation of culverts and digging of drainage trenches | Restore degraded land and soil | Storm water drainage constructed |  | Kware Drainage | Nkaimurunya |  |  | Water, Irrigation, Environment and Natural Resources | Water & Irrigation | Water & Irrigation | 2020-06-30 | 2020-07-01 | 2021-06-01 |  | 3500000 | 3500000 | 3500000 | CGK | N/A | 3500000 | 0 | 0 | 0% |  | 3500000 | 3500000 | Stalled | 0% | 0% | Transferred to Public Works Department | 2021 | 6 | 3500000 | No | Defer | Financial | No | Propose budget for screening | No | Propose budget for screening | Yes | Fesibility studies and design
383 | Sololo road and Kiboko Lane | Installation of culverts and digging of drainage trenches | Increase access to safe and affordable water | Storm water drainage constructed |  | Sololo road and Kiboko Lane | Nkaimurunya |  |  | Water, Irrigation, Environment and Natural Resources | Water & Irrigation | Water & Irrigation | 2020-06-30 | 2020-07-01 | 2021-06-01 |  | 3000000 | 3000000 | 3000000 | CGK | N/A | 3000000 | 0 | 0 | 0% |  | 3000000 | 3000000 | Stalled | 0% | 0% | Transferred to Public Works Department | 2021 | 6 | 3000000 | No | Defer | Financial | No | Propose budget for screening | No | Propose budget for screening | Yes | Fesibility studies and design
384 | Tree Nurseries | Completion of Tree Nurseries | Improve management and conservation of the environment | Tree nursery established |  | Tree Nurseries | Nkaimurunya |  |  | Water, Irrigation, Environment and Natural Resources | Environment, Natural Resources and Climate Change | Environment, Natural Resources and Climate Change | 2020-06-30 | 2020-07-01 | 2021-06-01 |  | 1500000 | 1500000 | 1500000 | CGK | N/A | 1500000 | 0 | 0 | 0% |  | 1500000 | 1500000 | Completed | [6 empty] | No |  | Environmental | No | Propose budget for screening | No | Propose budget for screening | Yes | Fesibility studies and design
385 | Gitugutah Borehole | Drilling and Equipping & Fencing | Increase access to safe and affordable water | Borehole drilled and equipped |  | Gitugutah Borehole | Nkaimurunya |  |  | Water, Irrigation, Environment and Natural Resources | Water & Irrigation | Water & Irrigation | 2020-06-30 | 2020-07-01 | 2021-06-01 |  | 7000000 | 7000000 | 7000000 | CGK | N/A | 7000000 | 0 | 0 | 0% |  | 7000000 | 7000000 | Completed | [6 empty] | No |  | Environmental | No | Propose budget for screening | No | Propose budget for screening | Yes | Fesibility studies and design
386 | Enkii Water | Piping to Lower Tikondo 3km | Increase access to safe and affordable water | Pipeline constructed |  | Enkii Water | Kimana | Kimana |  | Water, Irrigation, Environment and Natural Resources | Water & Irrigation | Water & Irrigation | 2020-06-30 | 2020-07-01 | 2021-06-01 |  | 2000000 | 2000000 | 2000000 | CGK | N/A | 2000000 | 0 | 0 | 0% |  | 2000000 | 2000000 | Completed | [6 empty] | No |  | Environmental | No | Propose budget for screening | No | Propose budget for screening | Yes | Fesibility studies and design
387 | Ingusuani Water Project | Piping and Construction of a tank to Esilanke Oltepesi Dam | Increase access to safe and affordable water | Pipeline constructed |  | Ingusuani Water Project | Purko |  |  | Water, Irrigation, Environment and Natural Resources | Water & Irrigation | Water & Irrigation | 2020-06-30 | 2020-07-01 | 2021-06-01 |  | 4000000 | 4000000 | 4000000 | CGK | N/A | 4000000 | 0 | 0 | 0% |  | 4000000 | 4000000 | Completed | [6 empty] | No |  | Environmental | No | Propose budget for screening | No | Propose budget for screening | Yes | Fesibility studies and design
388 | Olmanie Borehole Water Project | Drilling and Equipping | Increase access to safe and affordable water | Borehole drilled and equipped |  | Olmanie Borehole Water Project | Purko |  |  | Water, Irrigation, Environment and Natural Resources | Water & Irrigation | Water & Irrigation | 2020-06-30 | 2020-07-01 | 2021-06-01 |  | 5000000 | 5000000 | 5000000 | CGK | N/A | 5000000 | 0 | 0 | 0% |  | 5000000 | 5000000 | Completed | [6 empty] | No |  | Environmental | No | Propose budget for screening | No | Propose budget for screening | Yes | Fesibility studies and design
389 | Waste Bins | Purchase of waste bins | Improve management and conservation of the environment | Waste bins purchased |  | Waste Bins | Kitengela | Ilkeek Lemedungi |  | Water, Irrigation, Environment and Natural Resources | Environment, Natural Resources and Climate Change | Environment, Natural Resources and Climate Change | 2020-06-30 | 2020-07-01 | 2021-06-01 |  | 1000000 | 1000000 | 1000000 | CGK | N/A | 1000000 | 0 | 0 | 0% |  | 1000000 | 1000000 | Completed | [6 empty] | No |  | Environmental | No | Propose budget for screening | No | Propose budget for screening | Yes | Fesibility studies and design
390 | Morifat,Naironde, Iyaarat and Intashat water Pipelines | Installation of pipelines | Increase access to safe and affordable water | Pipeline constructed |  | Morifat,Naironde, Iyaarat and Intashat water Pipelines | Ewuaso Kedong | Kimuka |  | Water, Irrigation, Environment and Natural Resources | Water & Irrigation | Water & Irrigation | 2020-06-30 | 2020-07-01 | 2021-06-01 |  | 15500000 | 15500000 | 15500000 | CGK | N/A | 15500000 | 0 | 0 | 0% |  | 15500000 | 15500000 | Completed | [6 empty] | No |  | Environmental | No | Propose budget for screening | No | Propose budget for screening | Yes | Fesibility studies and design
391 | Loodoariak Water Source | Water Source Expansion | Improve water quality by reducing pollution | Spring protected |  | Loodoariak Water Source | Keekonyokie | Keekonyokie Central |  | Water, Irrigation, Environment and Natural Resources | Water & Irrigation | Water & Irrigation | 2020-06-30 | 2020-07-01 | 2021-06-01 |  | 2000000 | 2000000 | 2000000 | CGK | N/A | 2000000 | 0 | 0 | 0% |  | 2000000 | 2000000 | Completed | [6 empty] | No |  | Environmental | No | Propose budget for screening | No | Propose budget for screening | Yes | Fesibility studies and design
392 | Ilchalai Water Project | Piping, Construction of water kiosks and water Tank | Increase access to safe and affordable water | Pipeline constructed |  | Ilchalai Water Project | Mbirikani/Eselenkei | Oltiasika |  | Water, Irrigation, Environment and Natural Resources | Water & Irrigation | Water & Irrigation | 2020-06-30 | 2020-07-01 | 2021-06-01 |  | 7000000 | 7000000 | 7000000 | CGK | N/A | 7000000 | 0 | 0 | 0% |  | 7000000 | 7000000 | Completed | [6 empty] | No |  | Environmental | No | Propose budget for screening | No | Propose budget for screening | Yes | Fesibility studies and design
393 | Lemasusu Water Tank | Installation of Water tank | Increase access to safe and affordable water | Storage tank constructed |  | Lemasusu Water Tank | Mbirikani/Eselenkei | Oltiasika |  | Water, Irrigation, Environment and Natural Resources | Water & Irrigation | Water & Irrigation | 2020-06-30 | 2020-07-01 | 2021-06-01 |  | 3000000 | 3000000 | 3000000 | CGK | N/A | 3000000 | 0 | 0 | 0% |  | 3000000 | 3000000 | Completed | [6 empty] | No |  | Environmental | No | Propose budget for screening | No | Propose budget for screening | Yes | Fesibility studies and design
394 | Kiserian Water Project | Water tank and water troughs | Increase access to safe and affordable water | Storage tank constructed |  | Kiserian Water Project | Mbirikani/Eselenkei | Eselenkei |  | Water, Irrigation, Environment and Natural Resources | Water & Irrigation | Water & Irrigation | 2020-06-30 | 2020-07-01 | 2021-06-01 |  | 4000000 | 4000000 | 4000000 | CGK | N/A | 4000000 | 0 | 0 | 0% |  | 4000000 | 4000000 | Completed | [6 empty] | No |  | Environmental | No | Propose budget for screening | No | Propose budget for screening | Yes | Fesibility studies and design
395 | Oltotoi Water Project | Piping, Construction of a tank and water trough | Increase access to safe and affordable water | Pipeline constructed |  | Oltotoi Water Project | Mbirikani/Eselenkei | Eselenkei |  | Water, Irrigation, Environment and Natural Resources | Water & Irrigation | Water & Irrigation | 2020-06-30 | 2020-07-01 | 2021-06-01 |  | 5000000 | 5000000 | 5000000 | CGK | N/A | 5000000 | 0 | 0 | 0% |  | 5000000 | 5000000 | Completed | [6 empty] | No |  | Environmental | No | Propose budget for screening | No | Propose budget for screening | Yes | Fesibility studies and design
396 | Elerai Sajiloni Borehole | Drilling and Equipping | Increase access to safe and affordable water | Borehole drilled and equipped |  | Elerai Sajiloni Borehole | Dalalekutuk | Sajiloni |  | Water, Irrigation, Environment and Natural Resources | Water & Irrigation | Water & Irrigation | 2020-06-30 | 2020-07-01 | 2021-06-01 |  | 7000000 | 7000000 | 7000000 | CGK | N/A | 7000000 | 0 | 0 | 0% |  | 7000000 | 7000000 | Completed | [6 empty] | No |  | Environmental | No | Propose budget for screening | No | Propose budget for screening | Yes | Fesibility studies and design
397 | Kenya Bureau of Statistics Borehole | Equipping and building of a raised tank | Increase access to safe and affordable water | Borehole equipped |  | Kenya Bureau of Statistics Borehole | Oloosirkon/Sholinke |  |  | Water, Irrigation, Environment and Natural Resources | Water & Irrigation | Water & Irrigation | 2020-06-30 | 2020-07-01 | 2021-06-01 |  | 4000000 | 4000000 | 4000000 | CGK | N/A | 4000000 | 0 | 0 | 0% |  | 4000000 | 4000000 | Completed | [6 empty] | No |  | Environmental | No | Propose budget for screening | No | Propose budget for screening | Yes | Fesibility studies and design
398 | NPC Borehole | Water piping to residence | Increase access to safe and affordable water | Pipeline constructed |  | NPC Borehole | Oloosirkon/Sholinke |  |  | Water, Irrigation, Environment and Natural Resources | Water & Irrigation | Water & Irrigation | 2020-06-30 | 2020-07-01 | 2021-06-01 |  | 3000000 | 3000000 | 3000000 | CGK | N/A | 3000000 | 0 | 0 | 0% |  | 3000000 | 3000000 | Completed | [6 empty] | No |  | Environmental | No | Propose budget for screening | No | Propose budget for screening | Yes | Fesibility studies and design
399 | Gichagi Water Tanks | Repair of Gichagi Water Towers, purchase and Installation of Caphill Water tank tower, Repair and replacement of water pipes Scheme 305 | Increase access to safe and affordable water | Storage tanks rehabilitated |  | Gichagi Water Tanks | Ngong | Gichagi |  | Water, Irrigation, Environment and Natural Resources | Water & Irrigation | Water & Irrigation | 2020-06-30 | 2020-07-01 | 2021-06-01 |  | 3500000 | 3500000 | 3500000 | CGK | N/A | 3500000 | 0 | 0 | 0% |  | 3500000 | 3500000 | Completed | [6 empty] | No |  | Environmental | No | Propose budget for screening | No | Propose budget for screening | Yes | Fesibility studies and design
400 | Mathare Water Tower | Construction of Water Tower | Increase access to safe and affordable water | Water tower constructed |  | Mathare Water Tower | Ngong | Mathare |  | Water, Irrigation, Environment and Natural Resources | Water & Irrigation | Water & Irrigation | 2020-06-30 | 2020-07-01 | 2021-06-01 |  | 1500000 | 1500000 | 1500000 | CGK | N/A | 1500000 | 0 | 0 | 0% |  | 1500000 | 1500000 | Completed | [6 empty] | No |  | Environmental | No | Propose budget for screening | No | Propose budget for screening | Yes | Fesibility studies and design
401 | 14Km Borehole | Equipping | Increase access to safe and affordable water | Borehole equipped |  | 14Km Borehole | Kenyawa Poka |  |  | Water, Irrigation, Environment and Natural Resources | Water & Irrigation | Water & Irrigation | 2020-06-30 | 2020-07-01 | 2021-06-01 |  | 4000000 | 4000000 | 4000000 | CGK | N/A | 4000000 | 0 | 0 | 0% |  | 4000000 | 4000000 | Completed | [6 empty] | No |  | Environmental | No | Propose budget for screening | No | Propose budget for screening | Yes | Fesibility studies and design
402 | Ilmao water Pipeline | Drilling and equipping | Increase access to safe and affordable water | Borehole drilled and equipped |  | Ilmao water Pipeline | Kenyawa Poka |  |  | Water, Irrigation, Environment and Natural Resources | Water & Irrigation | Water & Irrigation | 2020-06-30 | 2020-07-01 | 2021-06-01 |  | 7000000 | 7000000 | 7000000 | CGK | N/A | 7000000 | 0 | 0 | 0% |  | 7000000 | 7000000 | Completed | [6 empty] | No |  | Environmental | No | Propose budget for screening | No | Propose budget for screening | Yes | Fesibility studies and design
403 | KJD County/ Water Trust Fund | County contribution for Mashuuru-Imaroro-Noulturesh water pipeline | Increase access to safe and affordable water | Pipeline constructed |  | KJD County/ Water Trust Fund | Imaroro | Mashuru-Imaroro |  | Water, Irrigation, Environment and Natural Resources | Water & Irrigation | Water & Irrigation | 2020-06-30 | 2020-07-01 | 2021-06-01 |  | 12100000 | 12100000 | 12100000 | CGK | N/A | 12100000 | 0 | 0 | 0% |  | 12100000 | 12100000 | Completed | [6 empty] | No |  | Environmental | Yes | Climate proofing | Yes | Implementation Environmental Management Plan | Yes | Fesibility studies and design
404 | Decommissioning of Ngong Dumpsite | Removal and rehabilitaion of site into a park | Improve management and conservation of the environment | Dumpsite decommissioned |  | Decommissioning of Ngong Dumpsite | Ngong | Ngong |  | Water, Irrigation, Environment and Natural Resources | Environment, Natural Resources and Climate Change | Environment, Natural Resources and Climate Change | 2020-06-30 | 2020-07-01 | 2021-06-01 |  | 50000000 | 50000000 | 50000000 | CGK | N/A | 50000000 | 0 | 0 | 0% |  | 50000000 | 50000000 | Completed | [6 empty] | No |  | Environmental | Yes | Climate proofing | Yes | Implementation Environmental Management Plan | Yes | Fesibility studies and design
405 | Oloolaiser Solarization Project (Phase 1) | Installation of solar pumping systems | Increase access to safe and affordable water | Borehole solarized |  | Oloolaiser Solarization Project (Phase 1) | Ongata Rongai | Oloolaiser |  | Water, Irrigation, Environment and Natural Resources | Water & Irrigation | Water & Irrigation | 2020-06-30 | 2020-07-01 | 2021-06-01 |  | 30000000 | 30000000 | 30000000 | CGK | N/A | 30000000 | 0 | 0 | 0% |  | 30000000 | 30000000 | Stalled | 0% | 0% | Inadequate finances | 2021 | 6 | 30000000 | No | Defer | Financial | No | Propose budget for screening | No | Propose budget for screening | Yes | Fesibility studies and design
406 | Rehabilitation/ equipping of boreholes -solar powered | Installation of solar pumping systems | Increase access to safe and affordable water | Boreholes rehabilitated |  | Rehabilitation/ equipping of boreholes -solar powered | Countywide | Countywide |  | Water, Irrigation, Environment and Natural Resources | Water & Irrigation | Water & Irrigation | 2020-06-30 | 2020-07-01 | 2021-06-01 |  | 20000000 | 20000000 | 20000000 | CGK | N/A | 20000000 | 0 | 0 | 0% |  | 20000000 | 20000000 | Completed | [6 empty] | No |  | Environmental | No | Propose budget for screening | No | Propose budget for screening | Yes | Fesibility studies and design
407 | Emarti water pan | Rehabilitation of the water pan | Increase access to safe and affordable water | Water pan rehabilitated |  | Emarti water pan | Kajiado Central | Matapato North |  | Water, Irrigation, Environment and Natural Resources | Water Services | Water Services | 2021-06-30 | 2021-07-01 | 2022-06-01 |  | 5000000 | 5000000 | 5000000 | CGK | N/A | 5000000 | 0 | 0 | 0% | 0 | 5000000 | 5000000 | Completed | [6 empty] | No |  | Environmental | No | Propose budget for screening | No | Propose budget for screening | Yes | Fesibility studies and design
408 | Emashini borehole | Driling and Equipping | Increase access to safe and affordable water | Borehole drilled and equipped |  | Emashini borehole | Kajiado Central | Matapato North |  | Water, Irrigation, Environment and Natural Resources | Water Services | Water Services | 2021-06-30 | 2021-07-01 | 2022-06-01 |  | 7000000 | 7000000 | 7000000 | CGK | N/A | 7000000 | 0 | 0 | 0% | 0 | 7000000 | 7000000 | Completed | [6 empty] | No |  | Environmental | No | Propose budget for screening | No | Propose budget for screening | Yes | Fesibility studies and design
409 | Oloontana- Oloirien borehole | Drilling and equipping | Increase access to safe and affordable water | Borehole drilled and equipped |  | Oloontana- Oloirien borehole | Kajiado West | Keekonyokie |  | Water, Irrigation, Environment and Natural Resources | Water Services | Water Services | 2021-06-30 | 2021-07-01 | 2022-06-01 |  | 7000000 | 7000000 | 7000000 | CGK | N/A | 7000000 | 0 | 0 | 0% | 0 | 7000000 | 7000000 | Stalled | 0% | 0% | Inadequate finances | 2022 | 6 | 7000000 | No | Defer | Financial | No | Propose budget for screening | No | Propose budget for screening | Yes | Fesibility studies and design
410 | Oldepe Borehole | Drilling & equipping | Increase access to safe and affordable water | Borehole drilled & equipped |  | Oldepe Borehole | Kajiado West | Mosiro |  | Water, Irrigation, Environment and Natural Resources | Water Services | Water Services | 2021-06-30 | 2021-07-01 | 2022-06-01 |  | 7000000 | 7000000 | 7000000 | CGK | N/A | 7000000 | 0 | 0 | 0% | 0 | 7000000 | 7000000 | Completed | [6 empty] | No |  | Environmental | No | Propose budget for screening | No | Propose budget for screening | Yes | Fesibility studies and design
411 | Kalesirwa Furrow | Construction of furrows | Increase area under irrigation | Furrow constructed |  | Kalesirwa Furrow | Kajiado South | Mbirikani/ Eselenkei |  | Water, Irrigation, Environment and Natural Resources | Water Services | Water Services | 2021-06-30 | 2021-07-01 | 2022-06-01 |  | 5000000 | 5000000 | 5000000 | CGK | N/A | 5000000 | 0 | 0 | 0% | 0 | 5000000 | 5000000 | Stalled | 0% | 0% | Inadequate finances | 2022 | 6 | 5000000 | No | Defer | Financial | No | Propose budget for screening | No | Propose budget for screening | Yes | Fesibility studies and design
412 | Nalepo borehole | Drilling and equipping | Increase access to safe and affordable water | Borehole drilled and equipped |  | Nalepo borehole | Kajiado Central | Dalalekutuk |  | Water, Irrigation, Environment and Natural Resources | Water Services | Water Services | 2021-06-30 | 2021-07-01 | 2022-06-01 |  | 7000000 | 7000000 | 7000000 | CGK | N/A | 7000000 | 0 | 0 | 0% | 0 | 7000000 | 7000000 | Completed | [6 empty] | No |  | Environmental | No | Propose budget for screening | No | Propose budget for screening | Yes | Fesibility studies and design
413 | Olenarau borehole | Drilling and equipping | Increase access to safe and affordable water | Borehole drilled and equipped |  | Olenarau borehole | Kajiado Central | Dalalekutuk |  | Water, Irrigation, Environment and Natural Resources | Water Services | Water Services | 2021-06-30 | 2021-07-01 | 2022-06-01 |  | 7000000 | 7000000 | 7000000 | CGK | N/A | 7000000 | 0 | 0 | 0% | 0 | 7000000 | 7000000 | Completed | [6 empty] | No |  | Environmental | No | Propose budget for screening | No | Propose budget for screening | Yes | Fesibility studies and design
414 | Olderkesi borehole | Drilling & equipping | Increase access to safe and affordable water | Borehole drillled and equipped |  | Olderkesi borehole | Kajiado Central | Ildamat |  | Water, Irrigation, Environment and Natural Resources | Water Services | Water Services | 2021-06-30 | 2021-07-01 | 2022-06-01 |  | 7000000 | 7000000 | 7000000 | CGK | N/A | 7000000 | 0 | 5068994 | 72.41% | 5068994 | 1931006 | 1931006 | Completed | [6 empty] | No |  | Environmental | No | Propose budget for screening | No | Propose budget for screening | Yes | Fesibility studies and design
415 | Samai water project | Extension of pipeline | Increase access to safe and affordable water | Pipeline constructed |  | Samai water project | Kajiado South | Kuku |  | Water, Irrigation, Environment and Natural Resources | Water Services | Water Services | 2021-06-30 | 2021-07-01 | 2022-06-01 |  | 5000000 | 5000000 | 5000000 | CGK | N/A | 5000000 | 0 | 0 | 0% | 0 | 5000000 | 5000000 | Completed | [6 empty] | No |  | Environmental | No | Propose budget for screening | No | Propose budget for screening | Yes | Fesibility studies and design
416 | Olootuka water project | Piping | Increase access to safe and affordable water | Pipeline constructed |  | Olootuka water project | Kajiado Central | Matapato South |  | Water, Irrigation, Environment and Natural Resources | Water Services | Water Services | 2021-06-30 | 2021-07-01 | 2022-06-01 |  | 5000000 | 5000000 | 5000000 | CGK | N/A | 5000000 | 0 | 4998266 | 99.97% | 4998266 | 1734 | 1734 | Completed | [6 empty] | No |  | Environmental | No | Propose budget for screening | No | Propose budget for screening | Yes | Fesibility studies and design
417 | Olololua borehole | Equipping | Increase access to safe and affordable water | Borehole equipped |  | Olololua borehole | Kajiado East | Kenyawa/ Poka |  | Water, Irrigation, Environment and Natural Resources | Water Services | Water Services | 2021-06-30 | 2021-07-01 | 2022-06-01 |  | 5000000 | 5000000 | 5000000 | CGK | N/A | 5000000 | 0 | 0 | 0% | 0 | 5000000 | 5000000 | Completed | [6 empty] | No |  | Environmental | No | Propose budget for screening | No | Propose budget for screening | Yes | Fesibility studies and design
418 | Olmanie borehole | Piping and construction of water trough | Increase access to safe and affordable water | Pipeline constructed |  | Olmanie borehole | Kajiado Central | Purko |  | Water, Irrigation, Environment and Natural Resources | Water Services | Water Services | 2021-06-30 | 2021-07-01 | 2022-06-01 |  | 5000000 | 5000000 | 5000000 | CGK | N/A | 5000000 | 0 | 0 | 0% | 0 | 5000000 | 5000000 | Completed | [6 empty] | No |  | Environmental | No | Propose budget for screening | No | Propose budget for screening | Yes | Fesibility studies and design
419 | Osuji-Kerema-Bissil Water Project (Counter-funding for WSTF) | Pipeline and watering facilities - Counterfunding with WSTF | Increase access to safe and affordable water | Pipeline constructed |  | Osuji-Kerema-Bissil Water Project (Counter-funding for WSTF) | Kajiado Central | Matapato North |  | Water, Irrigation, Environment and Natural Resources | Water Services | Water Services | 2021-06-30 | 2021-07-01 | 2022-06-01 |  | 15000000 | 15000000 | 15000000 | CGK | N/A | 15000000 | 0 | 0 | 0% | 0 | 15000000 | 15000000 | Stalled | 0% | 0% | Inadequate finances | 2022 | 6 | 15000000 | No | Defer | Financial | Yes | Climate proofing | Yes | Implementation Environmental Management Plan | Yes | Fesibility studies and design
420 | Ilkesumeti - Enkoireroi - Oltinka Water Supply Project | Pipeline extension, Rehabilitations & other infrastructure | Increase access to safe and affordable water | Pipeline constructed |  | Ilkesumeti - Enkoireroi - Oltinka Water Supply Project | Kajiado West | Ewuaso Kedong |  | Water, Irrigation, Environment and Natural Resources | Water Services | Water Services | 2021-06-30 | 2021-07-01 | 2022-06-01 |  | 10000000 | 10000000 | 10000000 | CGK | N/A | 10000000 | 0 | 0 | 0% | 0 | 10000000 | 10000000 | Stalled | 0% | 0% | Inadequate finances | 2022 | 6 | 10000000 | No | Defer | Financial | No | Propose budget for screening | No | Propose budget for screening | Yes | Fesibility studies and design
421 | Decomissioning of Ngong Dumpsite | Environmental protection works; landscaping; control of storm water and leachate control | Improve management and conservation of the environment | Dumpsite decommissioned |  | Decomissioning of Ngong Dumpsite | Kajiado North | Ngong |  | Water, Irrigation, Environment and Natural Resources | Environment, Natural Resources and Climate Change | Environment, Natural Resources and Climate Change | 2021-06-30 | 2021-07-01 | 2022-06-01 |  | 80000000 | 80000000 | 80000000 | CGK | N/A | 80000000 | 0 | 70999745 | 88.75% | 70999745 | 9000255 | 9000255 | Completed | [6 empty] | No |  | Environmental | No | Propose budget for screening | No | Propose budget for screening | Yes | Fesibility studies and design
422 | Embarbal borehole | Water piping; installation of generator | Increase access to safe and affordable water | Pipeline constructed |  | Embarbal borehole | Kajiado West | Mosiro |  | Water, Irrigation, Environment and Natural Resources | Water Services | Water Services | 2022-06-30 | 2022-07-01 | 2023-06-01 |  | 3500000 | 3500000 | 3500000 | CGK | N/A | 3500000 | 0 | 0 | 0% | 0 | 3500000 | 3500000 | Completed | [6 empty] | No |  | Environmental | No | Propose budget for screening | No | Propose budget for screening | Yes | Fesibility studies and design
423 | Mosiro Health Centre Borehole | Drilling and equipping of a borehole | Increase access to safe and affordable water | Borehole drilled and equipped |  | Mosiro Health Centre Borehole | Kajiado West | Mosiro |  | Water, Irrigation, Environment and Natural Resources | Water Services | Water Services | 2022-06-30 | 2022-07-01 | 2023-06-01 |  | 7000000 | 7000000 | 7000000 | CGK | N/A | 7000000 | 0 | 0 | 0% | 0 | 7000000 | 7000000 | Completed | [6 empty] | No |  | Environmental | No | Propose budget for screening | No | Propose budget for screening | Yes | Fesibility studies and design
424 | Imurutot Health Borehole | Drilling and equiping of Borehole | Increase access to safe and affordable water | Borehole drilled and equipped |  | Imurutot Health Borehole | Kajiado South | Entonet/Lenkism |  | Water, Irrigation, Environment and Natural Resources | Water Services | Water Services | 2022-06-30 | 2022-07-01 | 2023-06-01 |  | 6000000 | 6000000 | 6000000 | CGK | N/A | 6000000 | 0 | 0 | 0% | 0 | 6000000 | 6000000 | Completed | [6 empty] | No |  | Environmental | No | Propose budget for screening | No | Propose budget for screening | Yes | Fesibility studies and design
425 | Jerusalem Water Tank | Construction of a water Tank | Increase access to safe and affordable water | Storage tank constructed |  | Jerusalem Water Tank | Kajiado West | Ewuaso Oonkidongi |  | Water, Irrigation, Environment and Natural Resources | Water Services | Water Services | 2022-06-30 | 2022-07-01 | 2023-06-01 |  | 3000000 | 3000000 | 3000000 | CGK | N/A | 3000000 | 0 | 0 | 0% | 0 | 3000000 | 3000000 | Completed | [6 empty] | No |  | Environmental | No | Propose budget for screening | No | Propose budget for screening | Yes | Fesibility studies and design
426 | Oloosuyian borehole | Rehabilitation of borehole | Increase access to safe and affordable water | Borehole rehabilitated |  | Oloosuyian borehole | Kajiado Central | Ildamat |  | Water, Irrigation, Environment and Natural Resources | Water Services | Water Services | 2022-06-30 | 2022-07-01 | 2023-06-01 |  | 5000000 | 5000000 | 5000000 | CGK | N/A | 5000000 | 0 | 0 | 0% | 0 | 5000000 | 5000000 | Completed | [6 empty] | No |  | Environmental | No | Propose budget for screening | No | Propose budget for screening | Yes | Fesibility studies and design
427 | Ole kilil borehole | Instalation of Solar Panels | Increase access to safe and affordable water | Borehole solarized |  | Ole kilil borehole | Kajiado West | Mosiro |  | Water, Irrigation, Environment and Natural Resources | Water Services | Water Services | 2022-06-30 | 2022-07-01 | 2023-06-01 |  | 2000000 | 2000000 | 2000000 | CGK | N/A | 2000000 | 0 | 0 | 0% | 0 | 2000000 | 2000000 | Completed | [6 empty] | No |  | Environmental | No | Propose budget for screening | No | Propose budget for screening | Yes | Fesibility studies and design
428 | Olomayiana dam | Scooping of Soil | Increase access to safe and affordable water | Dam desilted |  | Olomayiana dam | Kajiado East | Kaputie North |  | Water, Irrigation, Environment and Natural Resources | Water Services | Water Services | 2022-06-30 | 2022-07-01 | 2023-06-01 |  | 1000000 | 1000000 | 1000000 | CGK | N/A | 1000000 | 0 | 0 | 0% | 0 | 1000000 | 1000000 | Completed | [6 empty] | No |  | Environmental | No | Propose budget for screening | No | Propose budget for screening | Yes | Fesibility studies and design
429 | Olomayiana dam | Fencing of Olomayina Dam | Improve water quality by reducing pollution | Dam fenced |  | Olomayiana dam | Kajiado East | Kaputie North |  | Water, Irrigation, Environment and Natural Resources | Water Services | Water Services | 2022-06-30 | 2022-07-01 | 2023-06-01 |  | 1500000 | 1500000 | 1500000 | CGK | N/A | 1500000 | 0 | 0 | 0% | 0 | 1500000 | 1500000 | Completed | [6 empty] | No |  | Environmental | No | Propose budget for screening | No | Propose budget for screening | Yes | Fesibility studies and design
430 | Kimana town water reticulation | Piping of water 4kms (Chemichemi to town) | Increase access to safe and affordable water | Water reticulation done |  | Kimana town water reticulation | Kajiado South | Kimana |  | Water, Irrigation, Environment and Natural Resources | Water Services | Water Services | 2022-06-30 | 2022-07-01 | 2023-06-01 |  | 3000000 | 3000000 | 3000000 | CGK | N/A | 3000000 | 0 | 0 | 0% | 0 | 3000000 | 3000000 | Completed | [6 empty] | No |  | Environmental | No | Propose budget for screening | No | Propose budget for screening | Yes | Fesibility studies and design
431 | Kwa Kuku | Furrawing and cementing from Chemichemi to Gathua | Increase area under irrigation | Furrow constructed |  | Kwa Kuku | Kajiado South | Kimana |  | Water, Irrigation, Environment and Natural Resources | Water Services | Water Services | 2022-06-30 | 2022-07-01 | 2023-06-01 |  | 3000000 | 3000000 | 3000000 | CGK | N/A | 3000000 | 0 | 0 | 0% | 0 | 3000000 | 3000000 | Completed | [6 empty] | No |  | Environmental | No | Propose budget for screening | No | Propose budget for screening | Yes | Fesibility studies and design
432 | Eluwai-Kiwanjani C Borehole | Drilling and equipping of a borehole | Increase access to safe and affordable water | Borehole drilled and equipped |  | Eluwai-Kiwanjani C Borehole | Kajiado South | Kuku |  | Water, Irrigation, Environment and Natural Resources | Water Services | Water Services | 2022-06-30 | 2022-07-01 | 2023-06-01 |  | 7000000 | 7000000 | 7000000 | CGK | N/A | 7000000 | 0 | 0 | 0% | 0 | 7000000 | 7000000 | Completed | [6 empty] | No |  | Environmental | No | Propose budget for screening | No | Propose budget for screening | Yes | Fesibility studies and design
433 | Marlal Nyanjani Pipeline | Renovation of pipeline | Increase access to safe and affordable water | Pipeline rehabilitated |  | Marlal Nyanjani Pipeline | Kajiado South | Kuku |  | Water, Irrigation, Environment and Natural Resources | Water Services | Water Services | 2022-06-30 | 2022-07-01 | 2023-06-01 |  | 2000000 | 2000000 | 2000000 | CGK | N/A | 2000000 | 0 | 0 | 0% | 0 | 2000000 | 2000000 | Completed | [6 empty] | No |  | Environmental | No | Propose budget for screening | No | Propose budget for screening | Yes | Fesibility studies and design
434 | Emurua dikir Borehole | Drilling and equiping of Bore hole | Increase access to safe and affordable water | Borehole drilled and equipped |  | Emurua dikir Borehole | Kajiado Central | Matapato North |  | Water, Irrigation, Environment and Natural Resources | Water Services | Water Services | 2022-06-30 | 2022-07-01 | 2023-06-01 |  | 7000000 | 7000000 | 7000000 | CGK | N/A | 7000000 | 0 | 0 | 0% | 0 | 7000000 | 7000000 | Completed | [6 empty] | No |  | Environmental | No | Propose budget for screening | No | Propose budget for screening | Yes | Fesibility studies and design
435 | Oloomporo -Inkiwanjani borehole | Drilling and equiping | Increase access to safe and affordable water | Borehole drilled and equipped |  | Oloomporo -Inkiwanjani borehole | Kajiado Central | Matapato South |  | Water, Irrigation, Environment and Natural Resources | Water Services | Water Services | 2022-06-30 | 2022-07-01 | 2023-06-01 |  | 7000000 | 7000000 | 7000000 | CGK | N/A | 7000000 | 0 | 0 | 0% | 0 | 7000000 | 7000000 | Completed | [6 empty] | No |  | Environmental | No | Propose budget for screening | No | Propose budget for screening | Yes | Fesibility studies and design
436 | Olekimaki Borehole | Purchase of Generator | Increase access to safe and affordable water | Generator installed |  | Olekimaki Borehole | Kajiado Central | Matapato South |  | Water, Irrigation, Environment and Natural Resources | Water Services | Water Services | 2022-06-30 | 2022-07-01 | 2023-06-01 |  | 2000000 | 2000000 | 2000000 | CGK | N/A | 2000000 | 0 | 0 | 0% | 0 | 2000000 | 2000000 | Completed | [6 empty] | No |  | Environmental | No | Propose budget for screening | No | Propose budget for screening | Yes | Fesibility studies and design
437 | Enkaroni borehole | Repair and replacement of pumping equipment | Increase access to safe and affordable water | Borehole rehabilitated |  | Enkaroni borehole | Kajiado Central | Purko |  | Water, Irrigation, Environment and Natural Resources | Water Services | Water Services | 2022-06-30 | 2022-07-01 | 2023-06-01 |  | 2000000 | 2000000 | 2000000 | CGK | N/A | 2000000 | 0 | 0 | 0% | 0 | 2000000 | 2000000 | Completed | [6 empty] | No |  | Environmental | No | Propose budget for screening | No | Propose budget for screening | Yes | Fesibility studies and design
438 | Oloorisheta borehole | Piping from Oloorisheta to Kumpa center (3Km) and a tank | Increase access to safe and affordable water | Pipeline constructed |  | Oloorisheta borehole | Kajiado Central | Purko |  | Water, Irrigation, Environment and Natural Resources | Water Services | Water Services | 2022-06-30 | 2022-07-01 | 2023-06-01 |  | 4000000 | 4000000 | 4000000 | CGK | N/A | 4000000 | 0 | 0 | 0% | 0 | 4000000 | 4000000 | Completed | [6 empty] | No |  | Environmental | No | Propose budget for screening | No | Propose budget for screening | Yes | Fesibility studies and design
439 | Kibaoni borehole | Drilling and equipping | Increase access to safe and affordable water | Borehole drilled and equipped |  | Kibaoni borehole | Kajiado South | Rombo |  | Water, Irrigation, Environment and Natural Resources | Water Services | Water Services | 2022-06-30 | 2022-07-01 | 2023-06-01 |  | 2000000 | 2000000 | 2000000 | CGK | N/A | 2000000 | 0 | 0 | 0% | 0 | 2000000 | 2000000 | Completed | [6 empty] | No |  | Environmental | No | Propose budget for screening | No | Propose budget for screening | Yes | Fesibility studies and design
440 | Enkamuriaki water project | Drilling and equipping | Increase access to safe and affordable water | Borehole drilled and equipped |  | Enkamuriaki water project | Kajiado East | Oloosirkon/Sholinke |  | Water, Irrigation, Environment and Natural Resources | Water Services | Water Services | 2022-06-30 | 2022-07-01 | 2023-06-01 |  | 4800000 | 4800000 | 4800000 | CGK | N/A | 4800000 | 0 | 0 | 0% | 0 | 4800000 | 4800000 | Completed | [6 empty] | No |  | Environmental | No | Propose budget for screening | No | Propose budget for screening | Yes | Fesibility studies and design
441 | NPC Piping | Piping and maintenance 4KM pipeline | Increase access to safe and affordable water | Pipeline rehabilitated |  | NPC Piping | Kajiado East | Oloosirkon/Sholinke |  | Water, Irrigation, Environment and Natural Resources | Water Services | Water Services | 2022-06-30 | 2022-07-01 | 2023-06-01 |  | 4000000 | 4000000 | 4000000 | CGK | N/A | 4000000 | 0 | 0 | 0% | 0 | 4000000 | 4000000 | Completed | [6 empty] | No |  | Environmental | No | Propose budget for screening | No | Propose budget for screening | Yes | Fesibility studies and design
442 | Imbirikani Water Project | Piping and equiping | Increase access to safe and affordable water | Pipeline constructed |  | Imbirikani Water Project | Kajiado South | Imbirikani |  | Water, Irrigation, Environment and Natural Resources | Water Services | Water Services | 2022-06-30 | 2022-07-01 | 2023-06-01 |  | 5000000 | 5000000 | 5000000 | CGK | N/A | 5000000 | 0 | 0 | 0% | 0 | 5000000 | 5000000 | Completed | [6 empty] | No |  | Environmental | No | Propose budget for screening | No | Propose budget for screening | Yes | Fesibility studies and design
443 | Ilchalai Water Tank | Construction of WaterTank | Increase access to safe and affordable water | Water tank constructed |  | Ilchalai Water Tank | Kajiado South | Imbirikani |  | Water, Irrigation, Environment and Natural Resources | Water Services | Water Services | 2022-06-30 | 2022-07-01 | 2023-06-01 |  | 4000000 | 4000000 | 4000000 | CGK | N/A | 4000000 | 0 | 0 | 0% | 0 | 4000000 | 4000000 | Completed | [6 empty] | No |  | Environmental | No | Propose budget for screening | No | Propose budget for screening | Yes | Fesibility studies and design
444 | Olkina water project | Piping and equiping | Increase access to safe and affordable water | Pipeline constructed |  | Olkina water project | Kajiado South | Imbirikani |  | Water, Irrigation, Environment and Natural Resources | Water Services | Water Services | 2022-06-30 | 2022-07-01 | 2023-06-01 |  | 5000000 | 5000000 | 5000000 | CGK | N/A | 5000000 | 0 | 0 | 0% | 0 | 5000000 | 5000000 | Completed | [6 empty] | No |  | Environmental | No | Propose budget for screening | No | Propose budget for screening | Yes | Fesibility studies and design
445 | Mokinyo water Piping | Piping and equiping | Increase access to safe and affordable water | Pipeline constructed |  | Mokinyo water Piping | Kajiado West | Magadi |  | Water, Irrigation, Environment and Natural Resources | Water Services | Water Services | 2022-06-30 | 2022-07-01 | 2023-06-01 |  | 1200000 | 1200000 | 1200000 | CGK | N/A | 1200000 | 0 | 0 | 0% | 0 | 1200000 | 1200000 | Completed | [6 empty] | No |  | Environmental | No | Propose budget for screening | No | Propose budget for screening | Yes | Fesibility studies and design
446 | Adra Dam marantawua | Dam Maintainace | Increase access to safe and affordable water | Dam rehabilitated |  | Adra Dam marantawua | Kajiado West | Magadi |  | Water, Irrigation, Environment and Natural Resources | Water Services | Water Services | 2022-06-30 | 2022-07-01 | 2023-06-01 |  | 2500000 | 2500000 | 2500000 | CGK | N/A | 2500000 | 0 | 0 | 0% | 0 | 2500000 | 2500000 | Completed | [6 empty] | No |  | Environmental | No | Propose budget for screening | No | Propose budget for screening | Yes | Fesibility studies and design
447 | Kaaranja Rock Catchment | Construction of water catchment | Increase access to safe and affordable water | Rock catchment constructed |  | Kaaranja Rock Catchment | Kajiado West | Magadi |  | Water, Irrigation, Environment and Natural Resources | Water Services | Water Services | 2022-06-30 | 2022-07-01 | 2023-06-01 |  | 1800000 | 1800000 | 1800000 | CGK | N/A | 1800000 | 0 | 0 | 0% | 0 | 1800000 | 1800000 | Completed | [6 empty] | No |  | Environmental | No | Propose budget for screening | No | Propose budget for screening | Yes | Fesibility studies and design
448 | Kayior Borehole | Repair and Maintainance | Increase access to safe and affordable water | Borehole rehabilitated |  | Kayior Borehole | Kajiado West | Magadi |  | Water, Irrigation, Environment and Natural Resources | Water Services | Water Services | 2022-06-30 | 2022-07-01 | 2023-06-01 |  | 4000000 | 4000000 | 4000000 | CGK | N/A | 4000000 | 0 | 0 | 0% | 0 | 4000000 | 4000000 | Completed | [6 empty] | No |  | Environmental | No | Propose budget for screening | No | Propose budget for screening | Yes | Fesibility studies and design
449 | Isinet Public Toilet | Construction of public toilets | Increase access to adequate and equitable sanitation and hygiene | Public toilets constructed |  | Isinet Public Toilet | Kajiado South | Imbirikani |  | Water, Irrigation, Environment and Natural Resources | Water Services | Water Services | 2022-06-30 | 2022-07-01 | 2023-06-01 |  | 4000000 | 4000000 | 4000000 | CGK | N/A | 4000000 | 0 | 0 | 0% | 0 | 4000000 | 4000000 | Completed | [6 empty] | No |  | Environmental | No | Propose budget for screening | No | Propose budget for screening | Yes | Fesibility studies and design
450 | Loodariak water source | Rehabilitation and maintainance of water source | Increase access to safe and affordable water | Spring rehabilitated |  | Loodariak water source | Kajiado West | Keekonyokie |  | Water, Irrigation, Environment and Natural Resources | Water Services | Water Services | 2022-06-30 | 2022-07-01 | 2023-06-01 |  | 5000000 | 5000000 | 5000000 | CGK | N/A | 5000000 | 0 | 0 | 0% | 0 | 5000000 | 5000000 | Completed | [6 empty] | No |  | Environmental | No | Propose budget for screening | No | Propose budget for screening | Yes | Fesibility studies and design
451 | Ilmasin water project | Installation and equipping of solar system | Increase access to safe and affordable water | Borehole solarized |  | Ilmasin water project | Kajiado West | Keekonyokie |  | Water, Irrigation, Environment and Natural Resources | Water Services | Water Services | 2022-06-30 | 2022-07-01 | 2023-06-01 |  | 5000000 | 5000000 | 5000000 | CGK | N/A | 5000000 | 0 | 0 | 0% | 0 | 5000000 | 5000000 | Completed | [6 empty] | No |  | Environmental | No | Propose budget for screening | No | Propose budget for screening | Yes | Fesibility studies and design
452 | Mathare water project | Installation and equipping of solar system, piping and kiosk | Increase access to safe and affordable water | Borehole equipped |  | Mathare water project | Kajiado North | Ngong |  | Water, Irrigation, Environment and Natural Resources | Water Services | Water Services | 2022-06-30 | 2022-07-01 | 2023-06-01 |  | 3000000 | 3000000 | 3000000 | CGK | N/A | 3000000 | 0 | 0 | 0% | 0 | 3000000 | 3000000 | Completed | [6 empty] | No |  | Environmental | No | Propose budget for screening | No | Propose budget for screening | Yes | Fesibility studies and design
453 | Water Services Trust Fund | Pipeline and watering facilities - Counterfund for WSTF proposed projects | Increase access to safe and affordable water | Pipeline constructed |  | Water Services Trust Fund | Countywide | Countywide |  | Water, Irrigation, Environment and Natural Resources | Water Services | Water Services | 2022-06-30 | 2022-07-01 | 2023-06-01 |  | 19200000 | 19200000 | 19200000 | CGK & WSTF | Water Sector Trust Fund (WSTF) |  |  | 0 | 0% | 0 | 19200000 | 19200000 | Completed | [6 empty] | No |  | Environmental | Yes | Climate proofing | Yes | Implementation Environmental Management Plan | Yes | Fesibility studies and design
454 | Oldonyorok Water and Sewerage Company Boreholes | Water reticulation | Increase access to safe and affordable water | Water reticulation done |  | Oldonyorok Water and Sewerage Company Boreholes | Kajiado Central | Matapato South |  | Water, Irrigation, Environment and Natural Resources | Water Services | Water Services | 2022-06-30 | 2022-07-01 | 2023-06-01 |  | 6000000 | 6000000 | 6000000 | CGK | N/A | 6000000 | 0 | 0 | 0% | 0 | 6000000 | 6000000 | Completed | [6 empty] | No |  | Environmental | No | Propose budget for screening | No | Propose budget for screening | Yes | Fesibility studies and design
455 | Water Services Providers funding (Oloolaiser, Oldonyorok, Olkejuado and Norturesh water services and sewerage companies) | Transfers to support operations WSPs for pending bills | Increase access to safe and affordable water | Water service provision improved |  | Water Services Providers funding (Oloolaiser, Oldonyorok, Olkejuado and Norturesh water services and sewerage companies) | Countywide | Countywide |  | Water, Irrigation, Environment and Natural Resources | Water Services | Water Services | 2022-06-30 | 2022-07-01 | 2023-06-01 |  | 30000000 | 30000000 | 30000000 | CGK | N/A | 30000000 | 0 | 0 | 0% | 0 | 30000000 | 30000000 | Completed | [6 empty] | No |  | Environmental | No | Propose budget for screening | No | Propose budget for screening | Yes | Fesibility studies and design
456 | Construction of Oloosuyian elevated tank | Construction of an elevated steel tank and pipeline | Increase access to safe and affordable water | Water tank constructed |  | Construction of Oloosuyian elevated tank | Kajiado Central | Ildamat |  | Water, Irrigation, Environment and Natural Resources | Water Services | Water Services | 2022-06-30 | 2022-07-01 | 2023-06-01 |  | 10000000 | 10000000 | 10000000 | CGK | N/A | 10000000 | 0 | 0 | 0% | 0 | 10000000 | 10000000 | Completed | [6 empty] | No |  | Environmental | No | Propose budget for screening | No | Propose budget for screening | Yes | Fesibility studies and design
457 | Solarization of Tikoishi borehole | Borehole solarization | Increase access to safe and affordable water | Borehole solarized |  | Solarization of Tikoishi borehole | Kajiado Central | Ildamat |  | Water, Irrigation, Environment and Natural Resources | Water Services | Water Services | 2022-06-30 | 2022-07-01 | 2023-06-01 |  | 1600000 | 1600000 | 1600000 | CGK | N/A | 1600000 | 0 | 0 | 0% | 0 | 1600000 | 1600000 | Completed | [6 empty] | No |  | Environmental | No | Propose budget for screening | No | Propose budget for screening | Yes | Fesibility studies and design
458 | Solarization of Oloosurutia- Nkoroi Borehole | Borehole solarization | Increase access to safe and affordable water | Borehole solarized |  | Solarization of Oloosurutia- Nkoroi Borehole | Kajiado North | Olkeri |  | Water, Irrigation, Environment and Natural Resources | Water Services | Water Services | 2022-06-30 | 2022-07-01 | 2023-06-01 |  | 3500000 | 3500000 | 3500000 | CGK | N/A | 3500000 | 0 | 0 | 0% | 0 | 3500000 | 3500000 | Completed | [6 empty] | No |  | Environmental | No | Propose budget for screening | No | Propose budget for screening | Yes | Fesibility studies and design
459 | Solarization of Iltilal Borehole | Borehole solarization | Increase access to safe and affordable water | Borehole solarized |  | Solarization of Iltilal Borehole | Kajiado South | Kuku |  | Water, Irrigation, Environment and Natural Resources | Water Services | Water Services | 2022-06-30 | 2022-07-01 | 2023-06-01 |  | 2000000 | 2000000 | 2000000 | CGK | N/A | 2000000 | 0 | 0 | 0% | 0 | 2000000 | 2000000 | Completed | [6 empty] | No |  | Environmental | No | Propose budget for screening | No | Propose budget for screening | Yes | Fesibility studies and design
460 | Solarization of Water Office Borehole | Borehole solarization | Increase access to safe and affordable water | Borehole solarized |  | Solarization of Water Office Borehole | Kajiado Central | Dalalekutuk |  | Water, Irrigation, Environment and Natural Resources | Water Services | Water Services | 2022-06-30 | 2022-07-01 | 2023-06-01 |  | 2900000 | 2900000 | 2900000 | CGK | N/A | 2900000 | 0 | 0 | 0% | 0 | 2900000 | 2900000 | Completed | [6 empty] | No |  | Environmental | No | Propose budget for screening | No | Propose budget for screening | Yes | Fesibility studies and design
461 | Rehabilitation of Lemelepo Borehole | Borehole rehabilitation | Increase access to safe and affordable water | Borehole rehabilitated |  | Rehabilitation of Lemelepo Borehole | Kajiado South | Olkeri |  | Water, Irrigation, Environment and Natural Resources | Water Services | Water Services | 2022-06-30 | 2022-07-01 | 2023-06-01 |  | 800000 | 800000 | 800000 | CGK | N/A | 800000 | 0 | 0 | 0% | 0 | 800000 | 800000 | Completed | [6 empty] | No |  | Environmental | No | Propose budget for screening | No | Propose budget for screening | Yes | Fesibility studies and design
462 | Rehabilitation of Kilonito Borehole | Borehole rehabilitation | Increase access to safe and affordable water | Borehole rehabilitated |  | Rehabilitation of Kilonito Borehole | Kajiado West | Iloodokilani |  | Water, Irrigation, Environment and Natural Resources | Water Services | Water Services | 2022-06-30 | 2022-07-01 | 2023-06-01 |  | 2500000 | 2500000 | 2500000 | CGK | N/A | 2500000 | 0 | 0 | 0% | 0 | 2500000 | 2500000 | Completed | [6 empty] | No |  | Environmental | No | Propose budget for screening | No | Propose budget for screening | Yes | Fesibility studies and design
463 | Rehabilitation of Namunyak borehole | Borehole rehabilitation & completion | Increase access to safe and affordable water | Borehole rehabilitated |  | Rehabilitation of Namunyak borehole | Kajiado East | Kaputiei North |  | Water, Irrigation, Environment and Natural Resources | Water Services | Water Services | 2022-06-30 | 2022-07-01 | 2023-06-01 |  | 2500000 | 2500000 | 2500000 | CGK | N/A | 2500000 | 0 | 0 | 0% | 0 | 2500000 | 2500000 | Completed | [6 empty] | No |  | Environmental | No | Propose budget for screening | No | Propose budget for screening | Yes | Fesibility studies and design
464 | Rehabilitation of Olmakau Community Borehole | Borehole rehabilitation | Increase access to safe and affordable water | Borehole rehabilitated |  | Rehabilitation of Olmakau Community Borehole | Kajiado Central | Matapato South |  | Water, Irrigation, Environment and Natural Resources | Water Services | Water Services | 2022-06-30 | 2022-07-01 | 2023-06-01 |  | 1900000 | 1900000 | 1900000 | CGK | N/A | 1900000 | 0 | 0 | 0% | 0 | 1900000 | 1900000 | Completed | [6 empty] | No |  | Environmental | No | Propose budget for screening | No | Propose budget for screening | Yes | Fesibility studies and design
465 | Rehabilitation of Olosurutia Kaurai Community Borehole | Borehole rehabilitation | Increase access to safe and affordable water | Borehole rehabilitated |  | Rehabilitation of Olosurutia Kaurai Community Borehole | Kajiado West | Keekonyokie |  | Water, Irrigation, Environment and Natural Resources | Water Services | Water Services | 2022-06-30 | 2022-07-01 | 2023-06-01 |  | 1500000 | 1500000 | 1500000 | CGK | N/A | 1500000 | 0 | 0 | 0% | 0 | 1500000 | 1500000 | Completed | [6 empty] | No |  | Environmental | No | Propose budget for screening | No | Propose budget for screening | Yes | Fesibility studies and design
466 | Rehabilitation of Lerujat Borehole | Borehole rehabilitation | Increase access to safe and affordable water | Borehole rehabilitated |  | Rehabilitation of Lerujat Borehole | Kajiado West | Ewuaso Kedong |  | Water, Irrigation, Environment and Natural Resources | Water Services | Water Services | 2022-06-30 | 2022-07-01 | 2023-06-01 |  | 1500000 | 1500000 | 1500000 | CGK | N/A | 1500000 | 0 | 0 | 0% | 0 | 1500000 | 1500000 | Stalled | 0% | 0% | Inadequate finances | 2023 | 6 | 1500000 | No | Defer | Financial | No | Propose budget for screening | No | Propose budget for screening | Yes | Fesibility studies and design
467 | Equipping of Ilmisigiyio Borehole | Borehole Equipping | Increase access to safe and affordable water | Borehole equipped |  | Equipping of Ilmisigiyio Borehole | Kajiado Central | Matapato North |  | Water, Irrigation, Environment and Natural Resources | Water Services | Water Services | 2022-06-30 | 2022-07-01 | 2023-06-01 |  | 5000000 | 5000000 | 5000000 | CGK | N/A | 5000000 | 0 | 0 | 0% | 0 | 5000000 | 5000000 | Completed | [6 empty] | No |  | Environmental | No | Propose budget for screening | No | Propose budget for screening | Yes | Fesibility studies and design
468 | Rehabilitation of Enkutoto | Borehole rehabilitation | Increase access to safe and affordable water | Borehole rehabilitated |  | Rehabilitation of Enkutoto | Kajiado Central | Matapato North |  | Water, Irrigation, Environment and Natural Resources | Water Services | Water Services | 2022-06-30 | 2022-07-01 | 2023-06-01 |  | 4500000 | 4500000 | 4500000 | CGK | N/A | 4500000 | 0 | 0 | 0% | 0 | 4500000 | 4500000 | Completed | [6 empty] | No |  | Environmental | No | Propose budget for screening | No | Propose budget for screening | Yes | Fesibility studies and design
469 | Equipping of Referral Hospital Borehole | Borehole Equipping | Increase access to safe and affordable water | Borehole equipped |  | Equipping of Referral Hospital Borehole | Kajiado Central | Ildamat |  | Water, Irrigation, Environment and Natural Resources | Water Services | Water Services | 2022-06-30 | 2022-07-01 | 2023-06-01 |  | 4800000 | 4800000 | 4800000 | CGK | N/A | 4800000 | 0 | 0 | 0% | 0 | 4800000 | 4800000 | Completed | [6 empty] | No |  | Environmental | No | Propose budget for screening | No | Propose budget for screening | Yes | Fesibility studies and design
470 | Climate Change Fund | Funding of climate change resilience and assessment as per the workplan | Improve management and conservation of the environment |  |  | Climate Change Fund | Countywide | Countywide |  | Water, Irrigation, Environment and Natural Resources | Environment, Natural Resources and Climate Change | Environment, Natural Resources and Climate Change | 2022-06-30 | 2022-07-01 | 2023-06-01 |  | 10000000 | 10000000 | 10000000 | CGK & FLLoCA | FLLoCA | 10000000 | 0 | 0 | 0% | 0 | 10000000 | 10000000 | Completed | [6 empty] | No |  | Environmental | Yes | Climate proofing | Yes | Implementation Environmental Management Plan | Yes | Fesibility studies and design
471 | Climate Change Fund | World Bank credit to finance Locally-Led Climate Action Program, (FLLoCA) | Improve management and conservation of the environment |  |  | Climate Change Fund | Countywide | Countywide |  | Water, Irrigation, Environment and Natural Resources | Environment, Natural Resources and Climate Change | Environment, Natural Resources and Climate Change | 2022-06-30 | 2022-07-01 | 2023-06-01 |  | 125000000 | 125000000 | 125000000 | CGK & FLLoCA | FLLoCA | 125000000 | 0 | 0 | 0% | 0 | 125000000 | 125000000 | Completed | [6 empty] | No |  | Environmental | Yes | Climate proofing | Yes | Implementation Environmental Management Plan | Yes | Fesibility studies and design
472 | Loolopon west community borehole | Drillling and equipping | Increase access to safe and affordable water | Borehole drilled and equipped |  | Loolopon west community borehole | Kajiado South | Kuku |  | Water, Irrigation, Environment and Natural Resources | Water Services | Water Services | 2023-06-30 | 2023-07-01 | 2024-06-01 |  | 7000000 | 7000000 | 6743176 | CGK | N/A | 7000000 | 0 | 1987428 | 28.39% | 1987428 | 4755748 | 5012572 | Stalled | 30% | 30% | Borehole caved in | 2024 | 6 | 5012572 | No | Defer | Financial | No | Propose budget for screening | No | Propose budget for screening | Yes | Fesibility studies and design
473 | Sompet Borehole | Borehole solar equipping and piping | Increase access to safe and affordable water | Borehole equipped |  | Sompet Borehole | Kajiado South | Kimana |  | Water, Irrigation, Environment and Natural Resources | Water Services | Water Services | 2023-06-30 | 2023-07-01 | 2024-06-01 |  | 4000000 | 4000000 | 3991861 | CGK | N/A | 4000000 | 0 | 3991861 | 99.8% | 3991861 | 0 | 8139 | Completed | [6 empty] | No |  | Environmental | No | Propose budget for screening | No | Propose budget for screening | Yes | Fesibility studies and design
474 | Namelock borehole | Pipeline extension | Increase access to safe and affordable water | Pipeline constructed |  | Namelock borehole | Kajiado South | Kimana |  | Water, Irrigation, Environment and Natural Resources | Water Services | Water Services | 2023-06-30 | 2023-07-01 | 2024-06-01 |  | 3000000 | 3000000 | 2972500 | CGK | N/A | 3000000 | 0 | 2972500 | 99.08% | 2972500 | 0 | 27500 | Completed | [6 empty] | No |  | Environmental | No | Propose budget for screening | No | Propose budget for screening | Yes | Fesibility studies and design
475 | Enkariak Ronkena Borehole | Construction of tank | Increase access to safe and affordable water | Storage tank constructed |  | Enkariak Ronkena Borehole | Kajiado South | Kimana |  | Water, Irrigation, Environment and Natural Resources | Water Services | Water Services | 2023-06-30 | 2023-07-01 | 2024-06-01 |  | 2500000 | 2500000 | 2500000 | CGK | N/A | 2500000 | 0 | 0 | 0% | 0 | 2500000 | 2500000 | Completed | [6 empty] | No |  | Environmental | No | Propose budget for screening | No | Propose budget for screening | Yes | Fesibility studies and design
476 | Oldonyo Oibor borehole | Pipeline extension | Increase access to safe and affordable water | Pipeline constructed |  | Oldonyo Oibor borehole | Kajiado South | Kimana |  | Water, Irrigation, Environment and Natural Resources | Water Services | Water Services | 2023-06-30 | 2023-07-01 | 2024-06-01 |  | 3000000 | 3000000 | 3000000 | CGK | N/A | 3000000 | 0 | 2999799 | 99.99% | 2999799 | 201 | 201 | Completed | [6 empty] | No |  | Environmental | No | Propose budget for screening | No | Propose budget for screening | Yes | Fesibility studies and design
477 | Isinet Borehole | Piping of Inkoropil water 1KM | Increase access to safe and affordable water | Pipeline constructed |  | Isinet Borehole | Kajiado South | Imbirikani/Eselenkei |  | Water, Irrigation, Environment and Natural Resources | Water Services | Water Services | 2023-06-30 | 2023-07-01 | 2024-06-01 |  | 1000000 | 1000000 | 999630 | CGK | N/A | 1000000 | 0 | 999630 | 99.96% | 999630 | 0 | 370 | Completed | [6 empty] | No |  | Environmental | No | Propose budget for screening | No | Propose budget for screening | Yes | Fesibility studies and design
478 | Orkina Water Project | Completion of water project | Increase access to safe and affordable water |  |  | Orkina Water Project | Kajiado South | Imbirikani/Eselenkei |  | Water, Irrigation, Environment and Natural Resources | Water Services | Water Services | 2023-06-30 | 2023-07-01 | 2024-06-01 |  | 3000000 | 3000000 | 3000000 | CGK | N/A | 3000000 | 0 | 2996466 | 99.88% | 2996466 | 3534 | 3534 | Completed | [6 empty] | No |  | Environmental | No | Propose budget for screening | No | Propose budget for screening | Yes | Fesibility studies and design
479 | Ibarueti Water Project | Construction of water tank | Increase access to safe and affordable water | Storage tank constructed |  | Ibarueti Water Project | Kajiado South | Imbirikani/Eselenkei |  | Water, Irrigation, Environment and Natural Resources | Water Services | Water Services | 2023-06-30 | 2023-07-01 | 2024-06-01 |  | 3000000 | 3000000 | 2998143 | CGK | N/A | 3000000 | 0 | 1948792 | 64.96% | 1948792 | 1049351 | 1051208 | Completed | [6 empty] | No |  | Environmental | No | Propose budget for screening | No | Propose budget for screening | Yes | Fesibility studies and design
480 | Enchilishili borehole | Construction of water tank | Increase access to safe and affordable water | Storage tank constructed |  | Enchilishili borehole | Kajiado South | Imbirikani/Eselenkei |  | Water, Irrigation, Environment and Natural Resources | Water Services | Water Services | 2023-06-30 | 2023-07-01 | 2024-06-01 |  | 3000000 | 3000000 | 3000000 | CGK | N/A | 3000000 | 0 | 0 | 0% | 0 | 3000000 | 3000000 | Completed | [6 empty] | No |  | Environmental | No | Propose budget for screening | No | Propose budget for screening | Yes | Fesibility studies and design
481 | Nabulaa borehole | Piping of Nabulaa borehole | Increase access to safe and affordable water | Pipeline constructed |  | Nabulaa borehole | Kajiado South | Imbirikani/Eselenkei |  | Water, Irrigation, Environment and Natural Resources | Water Services | Water Services | 2023-06-30 | 2023-07-01 | 2024-06-01 |  | 1000000 | 1000000 | 999920 | CGK | N/A | 1000000 | 0 | 999920 | 99.99% | 999920 | 0 | 80 | Completed | [6 empty] | No |  | Environmental | No | Propose budget for screening | No | Propose budget for screening | Yes | Fesibility studies and design
482 | Oltinka borehole | Borehole rehabilitation and 3km pipeline solarization | Increase access to safe and affordable water | Borehole rehabilitated |  | Oltinka borehole | Kajiado South | Entonet/Lenkism |  | Water, Irrigation, Environment and Natural Resources | Water Services | Water Services | 2023-06-30 | 2023-07-01 | 2024-06-01 |  | 2000000 | 2000000 | 1999956 | CGK | N/A | 2000000 | 0 | 1999956 | 100% | 1999956 | 0 | 44 | Completed | [6 empty] | No |  | Environmental | No | Propose budget for screening | No | Propose budget for screening | Yes | Fesibility studies and design
483 | Olepolos borehole | Solarization | Increase access to safe and affordable water | Borehole solarized |  | Olepolos borehole | Kajiado South | Entonet/Lenkism |  | Water, Irrigation, Environment and Natural Resources | Water Services | Water Services | 2023-06-30 | 2023-07-01 | 2024-06-01 |  | 3000000 | 3000000 | 2981316 | CGK | N/A | 3000000 | 0 | 2981316 | 99.38% | 2981316 | 0 | 18684 | Completed | [6 empty] | No |  | Environmental | No | Propose budget for screening | No | Propose budget for screening | Yes | Fesibility studies and design
484 | Enchurrai pipeline | Borehole solarization and 2km pipeline | Increase access to safe and affordable water | Borehole solarized |  | Enchurrai pipeline | Kajiado South | Rombo |  | Water, Irrigation, Environment and Natural Resources | Water Services | Water Services | 2023-06-30 | 2023-07-01 | 2024-06-01 |  | 3000000 | 3000000 | 3000000 | CGK | N/A | 3000000 | 0 | 0 | 0% | 0 | 3000000 | 3000000 | Completed | [6 empty] | No |  | Environmental | No | Propose budget for screening | No | Propose budget for screening | Yes | Fesibility studies and design
485 | Kikelelwa water tower | Tower and tanks | Increase access to safe and affordable water | Water tank constructed |  | Kikelelwa water tower | Kajiado South | Rombo |  | Water, Irrigation, Environment and Natural Resources | Water Services | Water Services | 2023-06-30 | 2023-07-01 | 2024-06-01 |  | 3000000 | 3000000 | 2979576 | CGK | N/A | 3000000 | 0 | 0 | 0% | 0 | 2979576 | 3000000 | Completed | [6 empty] | No |  | Environmental | No | Propose budget for screening | No | Propose budget for screening | Yes | Fesibility studies and design
486 | Parsinti borehole | Drilling and Equipping | Increase access to safe and affordable water | Borehole drilled and equipped |  | Parsinti borehole | Kajiado East | Imaroro |  | Water, Irrigation, Environment and Natural Resources | Water Services | Water Services | 2023-06-30 | 2023-07-01 | 2024-06-01 |  | 6000000 | 6000000 | 5719189 | CGK | N/A | 6000000 | 0 | 0 | 0% | 6000000 | 5719189 | 6000000 | Completed | [6 empty] | No |  | Environmental | No | Propose budget for screening | No | Propose budget for screening | Yes | Fesibility studies and design
487 | Olosukuroi borehole | Borehole solar equipping | Increase access to safe and affordable water | Borehole equipped |  | Olosukuroi borehole | Kajiado East | Kenyewa/Poka |  | Water, Irrigation, Environment and Natural Resources | Water Services | Water Services | 2023-06-30 | 2023-07-01 | 2024-06-01 |  | 3000000 | 3000000 | 3000000 | CGK | N/A | 3000000 | 0 | 0 | 0% | 0 | 3000000 | 3000000 | Stalled | 0% | 0% | Inadequate finances | 2024 | 6 | 3000000 | No | Defer | Financial | No | Propose budget for screening | No | Propose budget for screening | Yes | Fesibility studies and design
488 | Birika borehole | Solarization | Increase access to safe and affordable water | Borehole solarized |  | Birika borehole | Kajiado East | Kitengela |  | Water, Irrigation, Environment and Natural Resources | Water Services | Water Services | 2023-06-30 | 2023-07-01 | 2024-06-01 |  | 3000000 | 3000000 | 3000000 | CGK | N/A | 3000000 | 0 | 2993206 | 99.77% | 2993206 | 6794 | 6794 | Completed | [6 empty] | No |  | Environmental | No | Propose budget for screening | No | Propose budget for screening | Yes | Fesibility studies and design
489 | Imariani Borehole | Drilling and Solar Equipping/ Pipeline from Enakishomi to Imariani | Increase access to safe and affordable water | Borehole drilled and equipped |  | Imariani Borehole | Kajiado West | Mosiro |  | Water, Irrigation, Environment and Natural Resources | Water Services | Water Services | 2023-06-30 | 2023-07-01 | 2024-06-01 |  | 7000000 | 7000000 | 6697350 | CGK | N/A | 7000000 | 0 | 1838484 | 26.26% | 1838484 | 4858866 | 5161516 | Completed | [6 empty] | No |  | Environmental | No | Propose budget for screening | No | Propose budget for screening | Yes | Fesibility studies and design
490 | Ward boreholes | Solarization of boreholes - Enaibor - Kiushin,Enaibor - sugumen, Nkukuon, Olokeri and Eiti | Increase access to safe and affordable water | Boreholes solarized |  | Ward boreholes | Kajiado West | Mosiro |  | Water, Irrigation, Environment and Natural Resources | Water Services | Water Services | 2023-06-30 | 2023-07-01 | 2024-06-01 |  | 8000000 | 8000000 | 8000000 | CGK | N/A | 8000000 | 0 | 7100012 | 88.75% | 7100012 | 899988 | 899988 | Completed | [6 empty] | No |  | Environmental | No | Propose budget for screening | No | Propose budget for screening | Yes | Fesibility studies and design
491 | Pakase Water Pipeline | Rehabilitation | Increase access to safe and affordable water | Pipeline rehabilitated |  | Pakase Water Pipeline | Kajiado West | Magadi |  | Water, Irrigation, Environment and Natural Resources | Water Services | Water Services | 2023-06-30 | 2023-07-01 | 2024-06-01 |  | 2000000 | 2000000 | 2000000 | CGK | N/A | 2000000 | 0 | 0 | 0% | 0 | 2000000 | 2000000 | Completed | [6 empty] | No |  | Environmental | No | Propose budget for screening | No | Propose budget for screening | Yes | Fesibility studies and design
492 | Oldonyo - Nyokie Emugur rock carchment | Excavation construction of a storage tank | Increase access to safe and affordable water | Storage tank constructed |  | Oldonyo - Nyokie Emugur rock carchment | Kajiado West | Magadi |  | Water, Irrigation, Environment and Natural Resources | Water Services | Water Services | 2023-06-30 | 2023-07-01 | 2024-06-01 |  | 2500000 | 2500000 | 2493188 | CGK | N/A | 2500000 | 0 | 2493188 | 99.73% | 2493188 | 0 | 6812 | Completed | [6 empty] | No |  | Environmental | No | Propose budget for screening | No | Propose budget for screening | Yes | Fesibility studies and design
493 | Suswa- Intinyika water piping | Piping of water from Suswa to Orgumi | Increase access to safe and affordable water | Pipeline constructed |  | Suswa- Intinyika water piping | Kajiado West | Ewuaso |  | Water, Irrigation, Environment and Natural Resources | Water Services | Water Services | 2023-06-30 | 2023-07-01 | 2024-06-01 |  | 4000000 | 4000000 | 3999680 | CGK | N/A | 4000000 | 0 | 3279942 | 82% | 3279942 | 719738 | 720058 | Completed | [6 empty] | No |  | Environmental | No | Propose budget for screening | No | Propose budget for screening | Yes | Fesibility studies and design
494 | Tikoishi borehole | Borehole solar equipping | Increase access to safe and affordable water | Borehole equipped |  | Tikoishi borehole | Kajiado West | Iloodokilani |  | Water, Irrigation, Environment and Natural Resources | Water Services | Water Services | 2023-06-30 | 2023-07-01 | 2024-06-01 |  | 2500000 | 2500000 | 2500000 | CGK | N/A | 2500000 | 0 | 0 | 0% | 0 | 2500000 | 2500000 | Completed | [6 empty] | No |  | Environmental | No | Propose budget for screening | No | Propose budget for screening | Yes | Fesibility studies and design
495 | Oltepesi pipeline | Extension of water pipeline and construction of water tank | Increase access to safe and affordable water | Pipeline constructed |  | Oltepesi pipeline | Kajiado West | Keekonyokie |  | Water, Irrigation, Environment and Natural Resources | Water Services | Water Services | 2023-06-30 | 2023-07-01 | 2024-06-01 |  | 1000000 | 1000000 | 1000000 | CGK | N/A | 1000000 | 0 | 475600 | 47.56% | 475600 | 524400 | 524400 | Completed | [6 empty] | No |  | Environmental | No | Propose budget for screening | No | Propose budget for screening | Yes | Fesibility studies and design
496 | Olekimaki borehole | Storage house and purchase of generator | Increase access to safe and affordable water | Borehole rehabilitated |  | Olekimaki borehole | Kajiado Central | Matapato South |  | Water, Irrigation, Environment and Natural Resources | Water Services | Water Services | 2023-06-30 | 2023-07-01 | 2024-06-01 |  | 4000000 | 4000000 | 3998358 | CGK | N/A | 4000000 | 0 | 3998357.6 | 99.96% | 3998357.6 | 0.4 | 1642.4 | Completed | [6 empty] | No |  | Environmental | No | Propose budget for screening | No | Propose budget for screening | Yes | Fesibility studies and design
497 | Maisikiria BH | Drilling and sollar equipping | Increase access to safe and affordable water | Borehole drilled and equipped |  | Maisikiria BH | Kajiado Central | Matapato North |  | Water, Irrigation, Environment and Natural Resources | Water Services | Water Services | 2023-06-30 | 2023-07-01 | 2024-06-01 |  | 8000000 | 8000000 | 8000000 | CGK | N/A | 8000000 | 0 | 7659564.68 | 95.74% | 7659564.68 | 340435.32 | 340435.32 | Completed | [6 empty] | No |  | Environmental | No | Propose budget for screening | No | Propose budget for screening | Yes | Fesibility studies and design
498 | Ilngosuani Borehole | Laying of 3 Km Pipeline, solar equipping and Booster pump, installation of 2 no. 10,000ltrs water tank and watering facilities | Increase access to safe and affordable water | Pipeline constructed |  | Ilngosuani Borehole | Kajiado Central | Purko |  | Water, Irrigation, Environment and Natural Resources | Water Services | Water Services | 2023-06-30 | 2023-07-01 | 2024-06-01 |  | 6500000 | 6500000 | 6297350 | CGK | N/A | 6500000 | 0 | 2071753 | 31.87% | 2071753 | 4225597 | 4428247 | Completed | [6 empty] | No |  | Environmental | No | Propose budget for screening | No | Propose budget for screening | Yes | Fesibility studies and design
499 | Eluai-Olkejuloseki Pipeline Installation | Drilling and equipping | Increase access to safe and affordable water | Borehole drilled and equipped |  | Eluai-Olkejuloseki Pipeline Installation | Kajiado Central | Purko |  | Water, Irrigation, Environment and Natural Resources | Water Services | Water Services | 2023-06-30 | 2023-07-01 | 2024-06-01 |  | 9000000 | 9000000 | 8727794 | CGK | N/A | 9000000 | 0 | 1251060 | 13.9% | 1251060 | 7476734 | 7748940 | Completed | [6 empty] | No |  | Environmental | No | Propose budget for screening | No | Propose budget for screening | Yes | Fesibility studies and design
500 | Olgos borehole | Rehabilitation of Olgos borehole and piping | Increase access to safe and affordable water | Borehole rehabilitated |  | Olgos borehole | Kajiado Central | Purko |  | Water, Irrigation, Environment and Natural Resources | Water Services | Water Services | 2023-06-30 | 2023-07-01 | 2024-06-01 |  | 5000000 | 5000000 | 5000000 | CGK | N/A | 5000000 | 0 | 0 | 0% | 0 | 5000000 | 5000000 | Completed | [6 empty] | No |  | Environmental | No | Propose budget for screening | No | Propose budget for screening | Yes | Fesibility studies and design
501 | Esukuta Water Tower | Piping (2km), Booster Pump, Solarization and watering facilities | Increase access to safe and affordable water | Pipeline constructed |  | Esukuta Water Tower | Kajiado Central | Ildamat |  | Water, Irrigation, Environment and Natural Resources | Water Services | Water Services | 2023-06-30 | 2023-07-01 | 2024-06-01 |  | 4000000 | 4000000 | 3998172 | CGK | N/A | 4000000 | 0 | 1894628 | 47.37% | 1894628 | 2103544 | 2105372 | Stalled | 40% | 40% | Inadequate finances | 2024 | 6 | 2105372 | No | Defer | Financial | No | Propose budget for screening | No | Propose budget for screening | Yes | Fesibility studies and design
502 | KCB Grounds Toilet | Septik tank; Installation of water tanks | Increase access to adequate and equitable sanitation and hygiene | Septic tank constructed |  | KCB Grounds Toilet | Kajiado Central | Ildamat |  | Water, Irrigation, Environment and Natural Resources | Water Services | Water Services | 2023-06-30 | 2023-07-01 | 2024-06-01 |  | 2000000 | 2000000 | 2000000 | CGK | N/A | 2000000 | 0 | 1965620 | 98.28% | 1965620 | 34380 | 34380 | Completed | [6 empty] | No |  | Environmental | No | Propose budget for screening | No | Propose budget for screening | Yes | Fesibility studies and design
503 | Repair of Water Tanks at Gishagi | Repairs for 4 water tanks (concrete), elaveted steel tank , soloraization and battery | Increase access to safe and affordable water | Water tanks rehabilitated |  | Repair of Water Tanks at Gishagi | Kajiado North | Ngong |  | Water, Irrigation, Environment and Natural Resources | Water Services | Water Services | 2023-06-30 | 2023-07-01 | 2024-06-01 |  | 5000000 | 5000000 | 5000000 | CGK | N/A | 5000000 | 0 | 4996468 | 99.93% | 4996468 | 3532 | 3532 | Completed | [6 empty] | No |  | Environmental | No | Propose budget for screening | No | Propose budget for screening | Yes | Fesibility studies and design
504 | Florida borehole at Mathare | Erection of elevated steel tank , installation of water pump , piping to nearest water kiosk | Increase access to safe and affordable water | Water tank constructed |  | Florida borehole at Mathare | Kajiado North | Ngong |  | Water, Irrigation, Environment and Natural Resources | Water Services | Water Services | 2023-06-30 | 2023-07-01 | 2024-06-01 |  | 4000000 | 4000000 | 4000000 | CGK | N/A | 4000000 | 0 | 0 | 0% | 0 | 4000000 | 4000000 | Completed | [6 empty] | No |  | Environmental | No | Propose budget for screening | No | Propose budget for screening | Yes | Fesibility studies and design
505 | Ngong holding Market next to stadium | Drilling of borehole | Increase access to safe and affordable water | Borehole drilled and equipped |  | Ngong holding Market next to stadium | Kajiado North | Ngong |  | Water, Irrigation, Environment and Natural Resources | Water Services | Water Services | 2023-06-30 | 2023-07-01 | 2024-06-01 |  | 3000000 | 3000000 | 3000000 | CGK | N/A | 3000000 | 0 | 0 | 0% | 0 | 3000000 | 3000000 | Completed | [6 empty] | No |  | Environmental | No | Propose budget for screening | No | Propose budget for screening | Yes | Fesibility studies and design
506 | Mutungu Borehole | Borehole solarization | Increase access to safe and affordable water | Borehole solarized |  | Mutungu Borehole | Kajiado North | Oloolua |  | Water, Irrigation, Environment and Natural Resources | Water Services | Water Services | 2023-06-30 | 2023-07-01 | 2024-06-01 |  | 4500000 | 4500000 | 4499640 | CGK | N/A | 4500000 | 0 | 0 | 0% | 4500000 | 4499640 | 4500000 | Completed | [6 empty] | No |  | Environmental | No | Propose budget for screening | No | Propose budget for screening | Yes | Fesibility studies and design
507 | Embul-bul Borehole/Oloolua B | Borehole solarization | Increase access to safe and affordable water | Borehole solarized |  | Embul-bul Borehole/Oloolua B | Kajiado North | Oloolua |  | Water, Irrigation, Environment and Natural Resources | Water Services | Water Services | 2023-06-30 | 2023-07-01 | 2024-06-01 |  | 4000000 | 4000000 | 4000000 | CGK | N/A | 4000000 | 0 | 3999355.2 | 99.98% | 3999355.2 | 644.8 | 644.8 | Completed | [6 empty] | No |  | Environmental | No | Propose budget for screening | No | Propose budget for screening | Yes | Fesibility studies and design
508 | Matasia Oloika Water Project | 2km pipeline and watering facilities | Increase access to safe and affordable water | Pipeline constructed |  | Matasia Oloika Water Project | Kajiado North | Olkeri |  | Water, Irrigation, Environment and Natural Resources | Water Services | Water Services | 2023-06-30 | 2023-07-01 | 2024-06-01 |  | 3000000 | 3000000 | 2999760 | CGK | N/A | 3000000 | 0 | 0 | 0% | 0 | 2999760 | 3000000 | Completed | [6 empty] | No |  | Environmental | No | Propose budget for screening | No | Propose budget for screening | Yes | Fesibility studies and design
509 | Namelock secondary school pipeline | Pipeline | Increase access to safe and affordable water | Pipeline constructed |  | Namelock secondary school pipeline | Kajiado West | Keekonyokie |  | Water, Irrigation, Environment and Natural Resources | Water Services | Water Services | 2023-06-30 | 2023-07-01 | 2024-06-01 |  | 2500000 | 2500000 | 2500000 | CGK | N/A | 2500000 | 0 | 2499800 | 99.99% | 2499800 | 200 | 200 | Completed | [6 empty] | No |  | Environmental | No | Propose budget for screening | No | Propose budget for screening | Yes | Fesibility studies and design
510 | Rehabilitation and solarization of Isinya borehole | Borehole rehabilitation and solarization | Increase access to safe and affordable water | Borehole rehabilitated |  | Rehabilitation and solarization of Isinya borehole | Kajiado East | Kaputiei North |  | Water, Irrigation, Environment and Natural Resources | Water Services | Water Services | 2023-06-30 | 2023-07-01 | 2024-06-01 |  | 4500000 | 4500000 | 4498335 | CGK | N/A | 4500000 | 0 | 4498335 | 99.96% | 4498335 | 0 | 1665 | Completed | [6 empty] | No |  | Environmental | No | Propose budget for screening | No | Propose budget for screening | Yes | Fesibility studies and design
511 | Rehabilitation of Noltresh pipeline | Pipeline rehabilitation | Increase access to safe and affordable water | Pipeline rehabilitated |  | Rehabilitation of Noltresh pipeline | Kajiado South and East |  |  | Water, Irrigation, Environment and Natural Resources | Water Services | Water Services | 2023-06-30 | 2023-07-01 | 2024-06-01 |  | 7000000 | 7000000 | 7000000 | CGK | N/A | 7000000 | 0 | 6996540 | 99.95% | 6996540 | 3460 | 3460 | Completed | [6 empty] | No |  | Environmental | No | Propose budget for screening | No | Propose budget for screening | Yes | Fesibility studies and design
512 | Rehabilitation of Enkorika borehole | Borehole rehabilitation | Increase access to safe and affordable water | Borehole rehabilitated |  | Rehabilitation of Enkorika borehole | Kajiado central | Dalalekutuk |  | Water, Irrigation, Environment and Natural Resources | Water Services | Water Services | 2023-06-30 | 2023-07-01 | 2024-06-01 |  | 1200000 | 1200000 | 1200000 | CGK | N/A | 1200000 | 0 | 0 | 0% | 0 | 1200000 | 1200000 | Completed | [6 empty] | No |  | Environmental | No | Propose budget for screening | No | Propose budget for screening | Yes | Fesibility studies and design
513 | Rehabilitation of Noonkoben borehole | Borehole rehabilitation | Increase access to safe and affordable water | Borehole rehabilitated |  | Rehabilitation of Noonkoben borehole | Kajiado East | Kenyewa/Poka |  | Water, Irrigation, Environment and Natural Resources | Water Services | Water Services | 2023-06-30 | 2023-07-01 | 2024-06-01 |  | 1200000 | 1200000 | 1200000 | CGK | N/A | 1200000 | 0 | 0 | 0% | 0 | 1200000 | 1200000 | Completed | [6 empty] | No |  | Environmental | No | Propose budget for screening | No | Propose budget for screening | Yes | Fesibility studies and design
514 | Rehabilitation of Ilmariba borehole | Borehole rehabilitation | Increase access to safe and affordable water | Borehole rehabilitated |  | Rehabilitation of Ilmariba borehole | Kajiado Central | Matapato North |  | Water, Irrigation, Environment and Natural Resources | Water Services | Water Services | 2023-06-30 | 2023-07-01 | 2024-06-01 |  | 1200000 | 1200000 | 1200000 | CGK | N/A | 1200000 | 0 | 0 | 0% | 0 | 1200000 | 1200000 | Completed | [6 empty] | No |  | Environmental | No | Propose budget for screening | No | Propose budget for screening | Yes | Fesibility studies and design
515 | Inchoroi borehole | Drilling and equipping of borehole | Increase access to safe and affordable water | Borehole drilled and equipped |  | Inchoroi borehole | Kajiado West | Keekonyokie |  | Water, Irrigation, Environment and Natural Resources | Water Services | Water Services | 2023-06-30 | 2023-07-01 | 2024-06-01 |  | 7000000 | 7000000 | 6699838 | CGK | N/A | 7000000 | 0 | 6699838 | 95.71% | 6699838 | 0 | 300162 | Completed | [6 empty] | No |  | Environmental | No | Propose budget for screening | No | Propose budget for screening | Yes | Fesibility studies and design
516 | Osewan storm management project | Construction of dykes | Restore degraded land and soil | Storm water drainage constructed |  | Osewan storm management project | Kajiado south | Entonet/Lenkism |  | Water, Irrigation, Environment and Natural Resources | Water Services | Water Services | 2023-06-30 | 2023-07-01 | 2024-06-01 |  | 20000000 | 20000000 | 19848180 | CGK | N/A | 20000000 | 0 | 19848006 | 99.24% | 19848006 | 174 | 151994 | Completed | [6 empty] | No |  | Environmental | No | Propose budget for screening | No | Propose budget for screening | Yes | Fesibility studies and design
517 | Water Services Trust Fund/ Kajiado water supply project | Pipeline and watering facilities - Counterfund for WSTF proposed projects | Increase access to safe and affordable water | Pipeline constructed |  | Water Services Trust Fund/ Kajiado water supply project | Countywide | Countywide |  | Water, Irrigation, Environment and Natural Resources | Water Services | Water Services | 2023-06-30 | 2023-07-01 | 2024-06-01 |  | 28000000 | 28000000 | 28000000 | CGK & WSTF | Water Sector Trust Fund (WSTF) |  |  | 28000000 | 100% | 28000000 | 0 | 0 | Completed | [6 empty] | No |  | Environmental | Yes | Climate proofing | Yes | Implementation Environmental Management Plan | Yes | Fesibility studies and design
518 | Kajiado town and county offices water supply | Drilling and equipping of boreholes; installation of solar panels; construction of a raised storage tank (phase 1), piping and roof catchment (office premise) | Increase access to safe and affordable water | Water reticulation done |  | Kajiado town and county offices water supply | Kajiado central | Ildamat/ Dalalekutuk |  | Water, Irrigation, Environment and Natural Resources | Water Services | Water Services | 2023-06-30 | 2023-07-01 | 2024-06-01 |  | 20000000 | 18000000 | 17849732 | CGK | N/A | 18000000 | 0 | 17849732 | 99.17% | 17849732 | 0 | 150268 | Completed | [6 empty] | No |  | Environmental | No | Propose budget for screening | No | Propose budget for screening | Yes | Fesibility studies and design

## Formula Sheet
GOK
Development Partner
GOK & Development Partner
Yes
No
Compete
Cancel
Defer
Completed
Ongoing
Stalled