## Slide 1: KENYA DEVOLUTION SUPPORT PROGRAMME II
GREVIANCE REDRESS MECHANISMS

## Slide 2: Introduction
Kajiado County has established a robust Grievance Redress Mechanism (GRM) under the Kenya Devolution Support Programme Phase II (KDSP II) to ensure transparency, accountability, and community engagement in service delivery.
The GRM provides accessible channels for community members to raise concerns, complaints, or suggestions related to county development projects and services.
The system ensures timely response, fair handling, and respectful resolution of grievances, while protecting complainants’ confidentiality and rights.

## Slide 3: Purpose of GRM in KDSP II Projects
To enhance transparency, accountability, and community trust in county service delivery.
To provide a clear process for handling complaints and feedback related to KDSP II projects.
To improve decision-making by integrating citizen concerns into project implementation.

## Slide 4: How to Submit a Complaint
Channels Available:
PMC secretary: Community members and stakeholders can register their complains with the PMC secretary responsible for their wards.
Walk-in: Community members and stakeholders can visit any County or Ward offices and register their complains in the available complains log book at the GRM desk.
Online: Complaints can be registered in the Kajiado County website complaint portal link or the provided KDSP II website complaint portal.
Written Submission: Submit written complaints at GRM desks at the county or ward offices
Public Forums: During community barazas and project site visits GRM desks or log books will be available for complaints registration

## Slide 5: Follow up Process after Submission of a Complaint
Complaint is received and recorded in the complain log book.
An acknowledgement is issued to the complainant.
Issue is reviewed and actioned by the responsible actors.
Feedback is given within a reasonable timeframe using the contacts recorded by the complainant or meeting if the complain was submitted by a group.
Escalation if necessary to GRM committee at county level

## Slide 6: Complaint handling
Complaints will be handled by the following officers:
1. Ward Level:
Community Project Officers(PMCs Secretary)
GRM Liaison Officer
Citizen participation officers at ward levels.
2. Sub-county Level: Sub-county Citizen Participation Officers
3. County Level:
Departmental Officers
Director citizen participation
Chief Officer : Devolution
NB: It is advisable that all complaints and grievances be handled at the lowest level to avoid delays during project implementation

## Slide 7: Commitment to Confidentiality and Protection
All complaints will be handled with strict confidentiality.
No retaliation for submitting a complaint.
Special attention will be given to vulnerable groups and gender-sensitive issues

## Slide 8: Community awareness on GRM
There has been ongoing awareness campaigns on GRM rights and procedures at community level.
During public participation forum for the KDSP II Project Identification held across three sub counties (South, Central and West), the community, stakeholders and elected PMCs were introduced to GRM principles as essential for project accountability.
Each ward designated a PMC secretary responsible for recording and reporting grievances related to the project within their respective wards throughout the project cycle.
This will support transparency, conflict resolution, and responsiveness to community concerns.
GRM information is also available in local languages, kiswahili, English and Maasai

## Slide 9: Reports and Accountability
GRM Reports will be compiled monthly and quarterly.
The reports will be Shared with the County Secretary and stakeholders.
The reports will be used to improve service delivery and responsiveness through out the programme cycle.

## Slide 10
THANKYOU